## Audit Action Plan
| FINANCIAL YEAR | 17/18 | 2017/2018 AUDIT ACTION PLAN
| Municipality Name | Greater Tzaneen
| Audit Opinion | QUALIFIED
MATTERS AFFECTING AUDIT REPORT
No | Department | Description of Finding | Finding is new or recurring | Root Cause | Action Plan Description | Start Date | Completion Date | Person Responsible | Position | Progress | Internal Audit Comments | Progress to Date
1. | CFO | COMAF 19 - FINDING 1 Prior year expenditure recognized in the current year. INEP Grant | New | Inadequate controls over daily and monthly processing and reconciling of transactions; • Management did not ensure controls are in place over the processing on grant transactions to ensure the accuracy of reporting. | Management will develop and use invoice tracking register which will assist in developing a correct accrual listing. | 01-11-2018 | 31-01-2019 | Mokgadi Sono | Manager Expenditure
2. | CFO | COMAF 61 - FINDING 1 Overstatement of grant revenue and expenditure relating to INEP grant | New | Inadequate controls over daily and monthly processing and reconciling of transactions; • Management did not ensure controls are in place over the processing on grant transactions to ensure the accuracy of reporting. | Management will strengthen controls around the accounting of transactions in the appropriate years affected | 01-12-2018 | 31-03-2019 | Mokgadi Sono | Manager Expenditure
3 | ELECTRICAL ENGINEERING | COMAF 28 - FINDING 1 AOPO: KPI not well defined, verifiable and not useful (Provision of Capital Tools) | Recurring | Management did not review formulated performance targets included in the Service Delivery Budget Implementation Plan (SDBIP) to ensure that they are well defined. Internal control deficiency Financial and Performance Management Management did not review and monitor compliance with applicable laws and regulations. Unit of measure is not specific to which tools will be provided, and as the tools are purchased whenever required | Management must ensure that Project milestones are measurable with progress from one quarter to the next being verifyable | 15-01-2019 | 30-06-2019 | Sam Lelope | Director Electrical Engineering | Project milestones was improved for 18/19 Contains details of what will be procured at year-end
4 | ELECTRICAL ENGINEERING | COMAF 60 - FINDING 1 Reported Performance Information Not Supported by Valid and Accurate POE (% of households with access to electricity) | Recurring | Financial and Performance Management Management did not review that portfolio of evidence loaded on action assist is sufficient, valid accurate and complete to support reported performance information | Management will review the POE to ensure that it supports the reported performance. | 15-01-2019 | 30-06-2019 | Sam Lelope | Director Electrical Engineering | Not possible to source accurate POE for KPI. Management recommends that KPI be redefined.
5 | ENGINEERING SERVICES | COMAF 53 - FINDING 1 Reported Performance Information Not Supported by Valid and Accurate POE (# of households with access to sanitation) | Recurring | Financial and Performance Management Management did not review that portfolio of evidence loaded on action assist is sufficient, valid accurate and complete to support reported performance information | Management will review the POE to ensure that it supports the reported performance. | 15-01-2019 | 30-06-2019 | William Molokomme | Director Engineering Services | GTM will not report about this KPI since it is within the functions of MDM as the WSA. The KPI has been removed from the IDP and not included in the SDBIP from 18/19.
6 | ENGINEERING SERVICES | COMAF 54 - FINDING 1 Reported Performance Information Not Supported by Valid and Accurate POE (# of households with access to water) | Recurring | Financial and Performance Management Management did not review that portfolio of evidence loaded on action assist is sufficient, valid accurate and complete to support reported performance information | Management will review the POE to ensure that it supports the reported performance. | 15-01-2019 | 30-06-2019 | William Molokomme | Director Engineering Services | GTM will not report about this KPI since it is within the functions of MDM as the WSA.The KPI has been removed from the IDP and not included in the SDBIP from 18/19.
7 | ELECTRICAL ENGINEERING | COMAF 55 - FINDING 1 Reported Performance Information Not Supported by Valid and Accurate POE (Electrification of 541 households in Xihoko/Radoo/Thapana/Mavele) | Recurring | Financial and Performance Management Management did not review that portfolio of evidence loaded on action assist is sufficient, valid accurate and complete to support reported performance information | Management will review the POE to ensure that it supports the reported performance. | 15-01-2019 | 30-06-2019 | Sam Lelope | Director Electrical Engineering | Project completed in 2017/18 financial year. Validation of POE is done to ensure that correct POE are used and that they are not duplicated.
8 | CFO | COMAF 80 - FINDING 1 - Reported Performance Information Not Supported by Valid and Accurate POE (% household earnings less than R1 100 with access to free basic waste removal) | Recurring | Financial and Performance Management Management did not review that portfolio of evidence loaded on action assist is sufficient, valid accurate and complete to support reported performance information | Management will review the POE to ensure that it supports the reported performance. | 15-01-2019 | 30-06-2019 | Palesa Makhubela | CFO
9 | CFO | COMAF 57 - FINDING 1 Reported Performance Information Not Supported by Valid, Accurate and Complete POE (% of households earning less than R1 100 served with free basic electricity) | Recurring | Financial and Performance Management Management did not review that portfolio of evidence loaded on action assist is sufficient, valid accurate and complete to support reported performance information | Management will review the POE the ensure that it supports the reported performance. | 15-01-2019 | 30-06-2019 | Palesa Makhubela | CFO
10 | ELECTRICAL ENGINEERING | COMAF 91 - FINDING 1 Reported Performance Information Not Supported by Valid and Accurate POE (Renewal, Repairs and Maintenance on pre-paid meters) | Recurring | Financial and Performance Management Management did not review that portfolio of evidence loaded on action assist is sufficient, valid accurate and complete to support reported performance information | Management will review the POE to ensure that it supports the reported performance. | 15-01-2019 | 30-06-2019 | Sam Lelope | Director Electrical Engineering | Validation of POE is done to ensure that correct POE are used and that they are not duplicated.
11 | ENGINEERING SERVICES | COMAF 79 - FINDING : AOPO KPI D176 Reported Achievements relates to prior financial year | Recurring | Financial and Performance Management Management did not review that portfolio of evidence loaded on action assist is sufficient, valid accurate and complete to support reported performance information | Management will review the POE to ensure that it supports the reported performance. | 15-01-2019 | 30-06-2019 | William Molokomme | Director Engineering Services | The KPI will be reviewed to incorporate the jobs that were sustained from previous financial years
12 | CFO | COMAF 75 - FINDING : Non-compliance in preparation of the Annual Financial Statements | Recurring | Inadequate controls over daily and monthly processing and reconciling of transactions. | Management will ensure that controls are put in place to ensure that the annual financial statements are prepared in accordance to section 122 (1) (a) and (b) of the MFMA. Controls over daily and monthly processing of transactions. | 01-12-2018 | 31-03-2019 | Palesa Makhubela | CFO
13 | CFO | COMAF 8 - FINDING SCM: Deviations do not meet the requirement for a valid deviation and did not comply with PPPF act. | New | Non-compliance with the Municipalities SCM Policy and SCM Regulations | Training will be conducted for key role players and Officials will be trained to comply with SCM processes in line with the deviation requirements. Training started on the 24TH of July 2018 and the 25th of July 2018 and an internal memo was forwarded to all departments to advice officials to comply with SCM processes In line with the deviation requirements. | 01-10-2018 | 0ngoing | Zabel Modjadji | Manager SCM
14 | CFO | COMAF 10 - FINDING : SCM: Procurement without following official competitive bidding process. | New | Non-compliance with the Municipalities SCM Policy and SCM Regulations | Management will ensure that all procurements are done in accordance with the Municipalities SCM Policy Regulations and the PPPF Act. Training will be provided to the relevant Officials to ensure compliance. | 01-10-2018 | Ongoing | Zabel Modjadji | Manager SCM
15 | CFO | COMAF 12 - FINDING : SCM: Supplier did not have the required CIDB grading for the Project. | New | Non-compliance with the Municipalities SCM Policy and SCM Regulations. The Municipality did not ensure that construction contracts are awarded in terms of the CIDB regulation. | Measures will be put in place to ensure that all procurements are done in accordance with the Municipalities SCM Policy Regulations and the PPPF Act. Training will be provided to the relevant Officials to ensure compliance. | 01-10-2018 | Ongoing | Zabel Modjadji | Manager SCM
16 | CFO | COMAF 3 - FINDING : SCM process not followed | Recurring | Non compliance with SCM Regulations. The correct SCM process was not followed. | Training will be conducted for key role players and Officials will be trained to comply with SCM processes in line with the deviation requirements. Training started on the 24TH of July 2018 and the 25th of July 2018 and an internal memo was forwarded to all departments to advice officials to comply with SCM processes In line with the deviation requirements. | 31-08-2018 | Ongoing | Zabel Modjadji | Manager SCM
OTHER IMPORTANT MATTERS
17 | Corporate Services | COMAF 2 - FINDING 2 Disciplinary board not in place | New | None Compliance with Legislation Requirements. The Municipality did not establish a disciplinary board to investigate allegations of financial misconduct and monitor the institution of disciplinary proceedings against an alleged transgressor. | A Disciplinary Board will be established by the end of September 2018. | 31-08-2018 | 30-09-2018 | Walter Shibamba | Director Corporate Services | Disciplinary board has been appointed and council has resolved on the item. Council resolution B 52 (E/C 2018 09 18; C 2018 10 25)
18 | Corporate Services | COMAF 2 - FINDING 1 The Municipality does not have a consequence management policy in place | New | Inadequate measures in place. The Municipality did not establish processes and responsibilities relating to consequence management policy. | A Consequence Management Policy will be finalised in a special Council meeting to be held at the end of September 2018 and implementation will start forthwith. | 30-08-2018 | 30-11-2018 | Walter Shibamba | Director Corporate Services | The Policy has now been approved by Council
19 | CFO | COMAF 22 - FINDING 1 Municipal Standard Chart of Accounts (mSCOA) not implemented | New | Non Compliance with applicable Legislation • Management did not ensure the Municipality complies with Gazette 37577. | Management will: • Engage with National Treasury on obtaining exemption certificates for the delayed implementation of mSCOA, to avoid non-compliance findings. | 01-11-2018 | 31-01-2019 | Palesa Makhubela | CFO
20 | CFO | COMAF 45.1 - FINDING 1 Payment to suppliers not done within 30 days of invoice date. | Recurring | Management did not review and monitor compliance with applicable legislation; Management did not ensure that the Municipality complies with the provisions of Section 62(2)(e) of the MFMA | Management will implement an invoice tracking register to ensure that Section 62 (2) (e) of the MFMA is complied with. | 01-10-2018 | 31-10-2018 | Mokgadi Sono | Manager Expenditure
21 | Corporate Services | COMAF 95 - FINDING 1 Lack of consequence management | New | Insufficient controls to comply with Section 32(2) | A Policy will be approved and implemented to accommodate this oversight. | 30-08-2018 | 30-11-2018 | Walter Shibamba | Director Corporate Services | Consequence Management Policy has now been approved. Disciplinary Board has also been established.
22 | MM | COMAF 1 - FINDING : Non-Compliance with MFMA s62(1) (c) (ii) – No external quality assurance/assessment of the internal audit function conducted | New | Non Compliance with Legislative requirements. Inadequate oversight regarding internal controls. Management did not ensure that the Municipality complies with applicable legislation as well as standards and prescribed norms which affect the Municipality. | Management will ensure that a qualified, independent reviewer from outside the organization is appointed to perform an external quality assurance assessment. | 28-08-2018 | 31-03-2019 | Helen Manyike | Manager Internal Audit
23 | Corporate Services | COMAF 18 - FINDING : Non-Compliance with SALGA Agreement, Acting for longer than 6 months | Recurring | Non compliance with Collective Agreement on Conditions of Service for the Limpopo Division of the SALGABC. | A system of internal control will be develolped to track the periods in which people act in higher positions | Ongoing | Ongoing | Walter Shibamba | Director Corporate Services | HR will on the system to track acting periods. Recruitment for vacant positions to be expidited taking into account cashflow situration. Where circumstances prevent adherence, a report will be submitted to Council.
ADMINISTRATIVE MATTERS
24 | Corporate Services | :COMAF 38 - FINDING : Non-Compliance as employees exceeding threshold were compensated. Overtime. | New | Inadequate review and monitor compliance with the Municipality’s overtime policy. | Council Policy on overtime is under review and will be tabled to Council to align with BCEA. | 01-10-2018 | 31-12-2018 | Walter Shibamba | Director Corporate Servises | Overtime draft policy under review and will be tabled to Council
25 | Corporate Services | COMAF 37 - FINDING : Employee cost: Non - Compliance with leave Policy | New | Inadequate control deficiency | Leave policy will be reviewed and aligned with the Basic Conditions Employment Act | 01-12-2018 | 30-06-2019 | Helen Maake | HR Manager | The Leave Policy is reviewed and will be submitted for final comment in the next special LLF schedueld 20/02/2019
26 | CFO | COMAF 36 - FINDING 1 Staff Leave accrual incorrectly calculated | New | Inadequate control deficiency | Leave policy will be reviewed and aligned with the Basic Conditions Employment Act | 01-12-2018 | 30-06-2019 | Mokgadi Sono | Manager Expenditure
27 | Corporate Services | Failed login attempts are not reviewed | Recurring | Financial and Performance Management: Implement formal controls over IT systems Assurance could not be provided that audit logs were retrieved and failed login attempts, access violations on the Active Directory, PayDay and ProMIS were reviewed | Management will ensure that the Policies work as expected and reviews are as per the User Account Management Policy document during the refurbishment of the entire ICT Infrastructure. Our IT Administrators will be taken for training to address the issues raised on the Payday system. | 01-11-2018 | 31-03-2019 | Tshembani Maluleke | IT Manager | The implementation of the new Server Infrastructure is ongoing and therefore, Active Directory logs can only be retrived when the Windows Servers are upgraded to the latest version. In order to retrieve logs from Payday and ProMIS, IT Staff needs to be trained as the systems are not managed by IT Division but by Finance Department. To completely address the finding, Maangement should decide whether Payday and ProMIS should be managed by IT Division or Finance Deparment as there is a possibility of recurrence.
28 | Corporate Services | IT Service Level Agreement are not being monitored | New | Inadequate control defiencieny.Informal meeting with the Service Provider | Management will ensure that services rendered by the consultants to the Municipality will be monitored and POE will be filed | 01-12-2018 | 31-03-2019 | Tshembani Maluleke | IT Manager | Meetings were held with service providers to ensure that their services are inline with the requirements on the SLA.
29 | Corporate Services | Inadequate firewall management controls | Recurring | The current firewall has numerous configuration challenges which have resulted in limitations in the management of the firewall controls. Moreover, real time alerts were disabled as it rendered challenge in the management of incoming emails. | The municipality will refurbish the ICT Infrastructure, as such, the current firewall will be replaced, then necessary configurations and requirements will be addressed. | 14-01-2019 | 31-03-2019 | Tshembani Maluleke | IT Manager | Firewall currently being impleted and they will be reviewed upon completion of the project.
30 | Corporate Services | Disaster Recovery Plan has not been tested | Recurring | The municipality had challenges with the configuration of the Virtual Private Network (VPN); therefore DRP could not be tested during the period under review. | Test results of the Disaster Recovery Plan will be made available by 3rd quater 2018-19 as there is a project on the pipeline to refurbish all ICT infrastructures and will have a great impact on the DR Plan as all servers will be upgraded to the latest versions to enhance high availability, efficiency and security. | 14-01-2019 | 30-06-2019 | Tshembani Maluleke | IT Manager | The DRP was tested in December 2018.
31 | Corporate Services | Inadequate implementation of backup processes on the Active Directory, ProMIS and PayDay | Recurring | Tests for restoration of backups were not performed due to constant network outages emanating from obsoleteness of our current ICT Infrastructure. | Tests will be performed when the ICT infrastructure is refurbished- service provider appointed | 14-01-2019 | 31-04-2019 | Tshembani Maluleke | IT Manager | Data recovery tests for Active Directory was conducted during the DRP testing.
32 | Corporate Services | Program Change Management policy Inadequately documented | Recurring | Management did not realise the risk of not including the testing of changes when documenting the ICT Program Change Management Policy. | ICT Program Management Policy will be revised to address all key aspect to manage changes and updates made to all Financial System | 14-01-2019 | 31-04-2019 | Tshembani Maluleke | IT Manager | The changes were made on the Policy.
33 | CFO | COMAF 20 - FINDING 1 Debtors with balance of 90 days overdue not issued with notice of discontinuance | New | Management did not analyse reports and proof submitted of actions taken by the service providers. | Management will ensure that there is proper record keeping of all correspondence and audit trails of work executed by service providers. | 01-11-2018 | 31-01-2019 | Rona Viljoen | Manager Revenue | Awaiting appointment of debt collectors as per tender. Overdue accounts 90 days and older should be handed over, credit control notices for up to 90 days only.
34 | CFO | COMAF 21 - FINDING : Understatement of unspent conditional grant liability Grants transfer to Revenue | New | Inadequote controls over daily and monthly processing and reconciling of transactions; • Management did not ensure controls are in place over the processing on grant transactions to ensure the accuracy of reporting. | Controls will be put in place to ensure that the correct Grant allocations are disclosed. | 01-11-2018 | 31-01-2019 | Mokgadi Sono | Manager Expenditure
35 | CFO | COMAF 25 - FINDING : Understatement of unspent conditional grant liability - Part 2 Grants transfer to Revenue | New | Inadequote controls over daily and monthly processing and reconciling of transactions; • Management did not ensure controls are in place over the processing on grant transactions to ensure the accuracy of reporting. | Controls will be put in place to ensure that the correct Grant allocations are disclosed in the AFS. | 01-11-2018 | 31-01-2019 | Mokgadi Sono | Manager Expenditure
36 | CFO | COMAF 7 - FINDING : Payment to suppliers not made within 30 days of invoice date | Recurring | Management did not review and monitor compliance with applicable legislation; Management did not ensure that the Municipality complies with the provisions of Section 62(2)(e)of the MFMA | Management will implement controls to ensure that all relevant legislation including Section 62 (2) (e) of the MFMA is complied with. | 01-10-2018 | Ongoing | Mokgadi Sono | Manager Expenditure
37 | CFO | COMAF 64 - FINDING : No controls in place to prevent UIF expenditure | New | Non-compliance with the Municipalities SCM Policy and SCM regulations. Management did not ensure that SCM processes are followed. | Management will ensure that all procurements are done in accordance with the Municipalities SCM Policy Regulations and the PPPF Act. Training will be provided to the relevant Officials to ensure compliance. | 01-10-2018 | ongoing | Zabel Modjadji | Manager SCM
38 | CFO | COMAF 39 - Long oustanding debtors not handed over for Legal action / collection | Recurring | No measures in place to ensure that the long outstanding debtors are handed over for legal action or collection | Accredited ,reputable Debt book collected company to be appointed with intensive debt recovery programme and also debt book to be analysed and debt sold to service provider in order to enhance revenue recovery | 01-11-2018 | 31-03-2019 | Rona viljoen Palesa Mkahubela | Revenue Manager CFO | Evaluation of tender for debt collection and debt book still pending, should be finalised not later than April 2019.
39 | CFO | COMAF 78 - FINDING 1 Related party disclosure note is understated |  | Financial and performance management Inadequote measures in place to ensure that the related party disclosure note is accurate | Measures will be put in place to ensure that all transactions are reviewed in terms of the necessary delegation of authority. | 01-12-2018 | 31-03-2019 | Zabel Modjadji | Manager SCM
40 | CFO | COMAF 23 - FINDING 1 Other financial liabilities understated Difference between liabilities/loans and amounts in AFS | New | Inadequate measures in place to ensure that the Other financial liabilities disclosed in the Municipality Annual Financial Statements are accurately disclosed. | Controls will be put in place to ensure that the correct Grant income is disclosed in the AFS | 01-11-2018 | 31-01-2019 | Mokgadi Sono | Manager Expenditure
41 | CFO | Consumer deposit review not accurate | New | No measures in place to ensure that the review of consumer deposit is consistent and accurate | Consumer deposit policy will be reviewed and aligned with the formular on financial system to ensure deposit is suffiient to cover average consumption charges | 01-12-2018 | 30-04-2019 | Rona Viljoen | Revenue Manager | Review of consumer deposits to be done end of April 2019. Consumer policy review March 2019.
42 | CFO | Receivables from exchange transaction Presentation and disclosure | New | Financial and performance management The accounting officer did not put measures in place to ensure that the AFS are properly reviewed. | Management will ensure that AFS are properly reviewed. | 01-12-2018 | 30-04-2019 | Rona Viljoen | Revenue Manager | 2019-06-01
43 | Corporate Services | COMAF 66 - FINDING : Non- Compliance with Municipal Systems Act s67(1)(d) No measurement and evaluation of staff performance | New | Management failed to, review and monitor compliance with applicable legislation. | Management will implement a system to monitor, measure and evaluate the performance of staff. | 01-12-2018 | 30-06-2019 | Walter Shibamba | Director Corporate Services | Implementation of Performance Management system for the entire organisation is currently being considered. The matter will be included in the reviewed IDP for 2019/2020.