## MUNICIPAL MANAGER
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MATLALA BS
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2020/2021 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 14 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | Preparation of BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own Funds | (Own/MIG/INEP/DBSA)
Sıra No |  |  |  | Sözleşme No.su | Tahimini Bedel (Euro 1000) |  |  | Satınalma Yöntemi |  |  | Sözleşme İmza Tarihi | Sözleşme Tamamlanma Tarihi
[5 empty] | Toplam | Banka Finansmanı | Belediye Finansmanı
GELIBOLU MUNICIPALITY
OFFICE OF THE MUNICIPAL MANAGER
1 | Electronic Performance Management System | Electronic system procured to manage monthly reporting on SDBIP, Individual KPIs, Auditing of POE and Individual Assessments | Operational |  | 1300000 |  | 1300000 | Own |  |  |  |  | Previous bid expired after BAC referred it back for re-advertisement. | Bid expired | SCM processes are underway
1
2
3
4
5
6
7
8
9
10
3
4 | [14 empty] | December 2010

## BUDGET & TREASURY
Name of Municipality GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MATLALA BS
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2020/2021 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022' | 2022/2023' | 2023/2024' | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own Funds | (Own/MIG/INEP/DBSA)
BUDGET & TREASURY
1 | General valuation roll | Compiling of general valuation roll period 1 Jul 2022 to Jun 2027 | Operational |  | 6m |  | 6m | [5 empty] | 2021-07-01 | 2021-09-01 | Gen valaution roll 2022-01-31 + supplementary for 5 years. | Appointed valuer must deliver new roll end of Jan 2022 for implementation 1 July 2022.
| Meter reading contract | Meterreading services | Operational |  | 3m |  | 3m | [5 empty] | 2021-03-01 | 2021-09-01 | 2024-10-01 | Current servcie provider and new appointed should work together for at least two months for hand-over of project
| Credit Control | Credit control, reconnection and disconenction services | Operational |  | 3m |  | 3m | [5 empty] | 2021-07-21 | 2021-09-21 | 2024-10-01
| GTEDA-298 |  | Office equipment |  |  | 235000 | [5 empty] | GTEDA
CFO-111 | Purchase of critical office furniture | Purchase of critical office furniture
0 | 0 | 0 | [5 empty] | OWN

## ELECTRICAL ENGINEERING SERVICES
Name of Municipality GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MATLALA BS
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2020/2021 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022' | 2022/2023' | 2023/2024' | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
ELECTRICAL ENGINEERING SERVICES
1 | Rebuilding of Deeside 11kv line | Rebuilding of overhead line | Capital |  | 600000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
2 | Rebuilding of Yarmona /Shivulari 11kv line (4km) | Rebuilding of overhead line | Capital |  | 600000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
3 | Rebuilding of Ledzee 11kv lines | Rebuilding of overhead line | Capital |  | 500000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
4 | Rebuilding of Waterbok 11kv lines | Rebuilding of overhead line | Capital |  | 700000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
5 | Rebuilding of Letaba Feeder 33KV line | Rebuilding of overhead line | Capital |  | 1500000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
6 | Refurbishment of the Ebenhezer 33kV Feeder | Refurbishemet of meters | Capital |  | 1500000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Disbursment of funds/ Lockdown | Will resume once funds are disbursed | Will resume once funds are available and meter stocks
7 | Install 33kV voltage regulator on the 33kV Haenertsburg ring | Installation of voltage regulator | Capital |  | 2000000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
8 | Replace 11 kV and 33 kV Auto reclosers per annum (Item B53 6/14) | Installation of Auto reclosers | Capital |  | 1500000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Disbursment of funds/ Lockdown | Will resume once funds are disbursed | Will resume once funds are available and recloser stocks
9 | Prepaid Meters | Installation of pre-paid meters | Capital |  | 300000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Disbursment of funds/ Lockdown | Will resume once funds are disbursed | Will resume once funds are available and meter stocks
10 | Substation Tripping Batteries (Item B53 6/14) | Replacement of substation batteries | Capital |  | 450000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
11 | Replacement of Existing Air Conditioners | Replacement of existing airconditioners | Capital |  | 150000 | Y | N | DBSA |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Disbursment of funds/ Lockdown | Will resume once funds are disbursed | Will resume once funds are available
12 | Electrification of Bakgaga Village | Electrification | Operational |  | 1728000 | Y | N | INEP |  |  |  |  | 2020-07-15 | 2020-08-30 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
13 | Electrification of Senakwe | Electrification | Operational |  | 720000 | Y | N | INEP |  |  |  |  | 2020-07-15 | 2020-08-30 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
14 | Electrification of Senopelwa (Mantshwa) | Electrification | Operational |  | 1620000 | Y | N | INEP |  |  |  |  | 2020-07-15 | 2020-08-30 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
15 | Electrification of Pelana | Electrification | Operational |  | 1350000 | Y | N | INEP |  |  |  |  | 2020-07-15 | 2020-08-30 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
16 | Electrification of Musiphani | Electrification | Operational |  | 1386000 | Y | N | INEP |  |  |  |  | 2020-07-15 | 2020-08-30 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
17 | Electrification of Mavele (Phase 4) | Electrification | Operational |  | 5892000 | Y | N | INEP |  |  |  |  | 2020-07-15 | 2020-08-30 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
18 | Electrification of Sonkwane | Electrification | Operational |  | 1134000 | Y | N | INEP |  |  |  |  | 2020-07-15 | 2020-08-30 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
19 | Electrification of Runnymede | Electrification | Operational |  | 1170000 | Y | N | INEP |  |  |  |  | 2020-07-15 | 2020-08-30 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
20 | Installation of High mast | Highmasts | Operational |  | 1000000 | Y | N | MIG |  |  |  |  | 2020-10-10 | 2020-11-01 | 2021-06-21 | Dependent available of funds from MIG | Waiting for confirmation from MIG | Resume process once funds are available
21 | Sampling and purification of Transformer oil | Sampling and purification of Transformer oil at Various substations | Operational |  | 100000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
22 | Maintenance of substation breakers | Maintenance of breakers at various substations | Operational |  | 350000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
23 | Maintenance of Transformer tap changers | Maintenance of Transformer tap changers | Operational |  | 500000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
24 | Maintenance of Transformers, bushings and Isolators | Maintenance of Transformers, bushings and Isolators at various substations | Operational |  | 500000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
25 | Maintenance of substation protection schemes | Maintenance of substation protection schemes at various substations | Operational |  | 60000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
26 | Maintenance of substation battery systems | Maintenance of substation battery systems at various substations | Operational |  | 25000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
27 | Maintenance of miniature substations | Maintenance of miniature substations at various locations | Operational |  | 250000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
28 | Procurement of 11kV neutral current transformers for 33/11kV substations | Procurement of 11kV neutral current transformers for 33/11kV substations | Operational |  | 100000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
29 | Procurement of Protection relays spares: SCEM cards, Batteries, Protection relays & Auxiliaries | Procurement of Protection relays spares: SCEM cards, Batteries, Protection relays & Auxiliaries | Operational |  | 30000 | N | Y | OWN |  |  |  |  | 2020-07-15 | 2020-08-15 | 2021-06-21 | Insufficient funds | Waiting for approval of budgets | Prioritize work based on requirements
30 | Rebuilding of California 11kv line | Rebuilding of overhead line | Operational |  | 400000 | N | Y | Own |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
30 | Rebuilding of Rapids 11kv line | Rebuilding of overhead line | Operational |  | 400000 | N | Y | Own |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
30 | Rebuilding of Henley to La Cotte 11kv line | Rebuilding of overhead line | Operational |  | 400000 | N | Y | Own |  |  |  |  | 2020-08-15 | 2020-09-01 | 2021-06-30 | Pool of consultant contracts expired/ Covid-19 lockdown | New pool of consultant to be appointed | Fast track the process of appointing a new pool of consultant
31 | Maintenance of Airconditioners in Council Property | Rate based maintenance guided by Specification document | Operational |  | 200000 | N/A | Own Funds | Own |  |  |  | 2020-06-05 | 2020-07-03 | 2020-09-04 | 2023-09-21
EED-87 | High Mast Lights at Nkowankowa | Install Apollo lights | [8 empty] | 750000
EED-88 | High Mast Lights at Petanenge | Install Apollo lights | [8 empty] | 750000
EED-89 | High Mast Lights at Zanghoma/Mariveni | Install Apollo lights | [8 empty] | 750000
EED-90 | High Mast Lights at Moime and Shikwambana | Install Apollo lights | [8 empty] | 750000
EED-91 | High Mast Lights at Lusaka | Install Apollo lights | [8 empty] | 750000
EED-92 | High Mast Lights at Sethong | Install Apollo lights | [8 empty] | 750000
EED-93 | High Mast Lights at Moleketla | Install Apollo lights
EED-106 | Lenyenye Stadium Upgrade Phase 2 | Lenyenye Stadium Upgrade Phase 2
EED-97 | New Electricity Connections (Consumer Contribution) | New Electricity Connections (Consumer Contribution) |  |  | 10000000 |  |  |  | 10000000 | 10000000 | 10000000
Note on M37: Flip: VAT 18/19 and VAT 19/20

## CIVIL ENGINEERING SERVICES
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MATLALA BS
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2020/2021 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022' | 2022/2023' | 2023/2024' | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
CIVIL ENGINEERING SERVICES
ESD-11 |  | Mopye High School Access Road |  |  | 5000000 |  |  | MIG
ESD-11 |  | Mopye High School Access Road |  |  | 5000000 |  |  | MIG
ESD-12 |  | Paving of Nelson Ramodike High School Access road |  |  | 14000000 |  |  | MIG
ESD-13 |  | Tarring of Nkowankowa B Streets | [5 empty] | MIG
ESD-14 |  | Construction of storm water drainage systems |  |  | 0 |  |  | MIG
ESD-15 |  | Tarring Nkowankowa A Codesa and Hani Street |  |  | 4478953 |  |  | MIG
ESD-16 |  | Paving of Topanama Access Road to Serurubele School | [5 empty] | MIG
ESD-17 |  | Paving of Marirone to Motupa Street |  |  | 1380000 |  |  | MIG
ESD-18 |  | Paving of Thapane Street |  |  | 0 |  |  | MIG
ESD-19 |  | Mulati Access road Paving |  |  | 13653118 |  |  | MIG
ESD-21 |  | Tickyline to Makhwibuding Construction of storm water drainage systems. | [5 empty] | MIG
ESD-24 |  | Lenyenye Street paving |  |  | 0 |  |  | MIG
ESD-25 |  | Upgrading of Access Road Mbambamencisi | [5 empty] | MIG
ESD-26 |  | Upgrading of Khujwana to Lenyenye Access Road | [5 empty] | MIG
ESD-27 |  | Upgrading of Zangoma to Mariveni |  |  | 0 |  |  | MIG
ESD-28 |  | Paving of Moseanoka to Cell C Pharare Internal Streets in Ward 28 |  |  | 6029170 |  |  | MIG
ESD-29 |  | Nkowakowa Section D street paving | [5 empty] | MIG
ESD-31 |  | Upgrading of Relela Access Road |  |  | 13953582 |  |  | MIG
ESD-32 |  | Matapa to Leseka Access Road to School |  |  | 15793497 |  |  | MIG
ESD-110 |  | Paving of Risaba, Mnisi, Shando, to Driving school Internal Street in Ward 5 |  |  | 6000000 |  |  | MIG
ESD-297 |  | Paving of Main road from Ndhuna Mandlakazi, Efrika, Zangoma, Mpenyisi to Jamba Cross Internal Street (in Ward 13, Mandlakazi) and Nwamitwa Bridge via Nhlengeleti School to Taxi Rank, Clinic via Lwandlamoni School to Nwamitwa/Mandlakazi Road (in Ward 12) |  |  | 8649730 |  |  | MIG
CSD-22 |  | Purchase of Fleet: 1x waste truck 1 x grader |  |  | 6000000 |  |  | OWN
ESD-86 |  | Fence Nkowankowa cemetery extension |  |  | 1150000 |  |  | OWN
ESD-199 |  | Fence Lenyenye cemetery |  |  | 1150000 |  |  | OWN
PED-30 |  | Purchase of Geographical Information Systems Equipments |  |  | 1000000 |  |  | OWN
CFO-001 |  | Purchase of critical office furniture |  |  | 700000 |  |  | OWN
ESD-107 | Construction of Runnymede Sport Facility Phase 2 | Construction of Runnymede Sport Facility Phase 2
ESD-108 | Construction of Bulamahlo Community hall | Construction of Bulamahlo Community hall
ESD-17 | Rehabilitation of Dan Access road from R36 (Scrapyard) to D5011 (TEBA) | Rehabilitation of Dan Access road from R36 (Scrapyard) to D5011 (TEBA)
ESD-18 | Maweni low level bridge | Construction of low-level bridge
ESD-19 | Construction of Pedestrian Crossing bridges | Construction of Pedestrian bridges
ESD-1 | Upgrading of Nkowakowa B streets from gravel to paving | Upgrading of Nkowakowa B streets from gravel to paving
ESD-2 | Upgrading of Topanama Access Road from gravel to paving | Upgrading of Topanama Access Road from gravel to paving
ESD-3 | Upgrading of Marirone to Motupa Street from gravel to paving | Upgrading of Marirone to Motupa Street from gravel to paving
ESD-4 | Upgrading of Thapane Street from gravel to paving | Upgrading of Thapane Street from gravel to paving
ESD-5 | Upgrading of Mulati Access road from gravel to Paving | Upgrading of Mulati Access road from gravel to Paving
ESD-6 | Construction of Tickyline to Makhwibuding storm water drainage systems. | Construction of Tickyline to Makhwibuding storm water drainage systems.
ESD-7 | Upgrading of Lenyenye Street from gravel to paving | Upgrading of Lenyenye Street from gravel to paving
ESD-8 | Upgrading of Zangoma to Mariveni Road from gravel to paving | Upgrading of Zangoma to Mariveni Road from gravel to paving
ESD-9 | Upgrading of Moseanoka to Cell C Pharare Internal Streets from gravel to paving | Upgrading of Moseanoka to Cell C Pharare Internal Streets from gravel to paving
ESD-10 | Upgrading of Nkowakowa Section D streets from gravel to paving | Upgrading of Nkowakowa Section D streets from gravel to paving
ESD-20 | Construction of low level bridges in villages | Construction of low level bridges in villages
ESD-21 | Upgrading of Tzaneen Ext. 13 internal streets from paving blocks to tar | Upgrading of Tzaneen Ext. 13 internal streets from paving blocks to tar
ESD-22 | Rehabilitation of Dannie Joubert Street (Police Station to CTM) in Tzaneen | Patchwork, Fog Spray and Slurry Seal
ESD-23 | Rehabilitation of Pusela to Van Velden to Billy Maritz street in Tzaneen | Patchwork, Fog Spray and Slurry Seal
ESD-24 | Rehabilitation of 1st Avenue street in Tzaneen | Patchwork, Fog Spray and Slurry Seal
ESD-25 | Rehabilitation of 3rd Avenue to Hospital to 2nd Avenue street in Tzaneen | Patchwork, Fog Spray and Slurry Seal
ESD-26 | Rehabilitation of Haenertsburg Cemetery road | Rehabilitation |  |  | 0 | 0 | 0
ESD-27 | Rehabilitation of Main CBD Street and Parking in Letsitele | Rehabilitation of Main CBD Street and Parking in Letsitele | [5 empty] | OWN
ESD-28 | Rehabilitation of Boundary street in Tzaneen | Rehabilitation of Boundary street in Tzaneen | [5 empty] | OWN
ESD-29 | Rehabilitation of Nkowakowa Internal streets (Bankuna, Tambo to Maxakeni Road) | Rehabilitation of Nkowakowa Internal streets (Bankuna, Tambo to Maxakeni Road) | [5 empty] | OWN
ESD-30 | Rehabilitation of Lenyenye Internal Streets (Main street to Industrial Area, Stadium, Ithuseng to Main street via Police Station) | Rehabilitation of Lenyenye Internal Streets (Main street to Industrial Area, Stadium, Ithuseng to Main street via Police Station) | [5 empty] | OWN
ESD-31 | Rehabilitation Voster street in Letsitele | Rehabilitation Voster street in Letsitele | [5 empty] | OWN
ESD-32 | Rehabilitation of Eerste street in Letsitele | Rehabilitation of Eerste street in Letsitele | [5 empty] | OWN
ESD-33 | Construction of speed humps in all wards | Construction of speed humps in all wards | [5 empty] | OWN
0 | Purchase of Walk-behind Roller X 2 | Purchase of Walk-behind Roller X 2 | [5 empty] | OWN
ESD-34 | Purchase of 1x Bulldozer | Purchase of Bulldozer | [5 empty] | OWN
ESD-35 | Purchase of a Lowbed Truck and Trailer | Purchase of a Lowbed Truck and Trailer | [5 empty] | OWN
ESD-36 | Purchasing of tar cutting machines and small compactors | Purchasing of tar cutting machines and small compactors | [5 empty] | OWN
ESD-37 | Purchase of construction machinery: TLB, Grader | 4x TLB, 2x graders G140. Dumper tractor for sewer plant | [5 empty] | OWN
ESD-39 | Installation of Power Generator for Aqua Park Booster Pump Station | Installation of Power Generator for Aqua Park Booster Pump Station | [5 empty] | OWN
ESD-40 | Purchase of Fleet Management System | Purchase of Fleet Management System | [5 empty] | OWN
ESD-41 | Purchase of the Waste removal truck | Purchase of the Waste removal truck | [5 empty] | OWN | 1800000 | 1800000 | 0 | 44435 | 2021-12-15 | 2022-03-31 | 2022-06-30 | N/A |  | N/A
ESD-42 | Purchase of 1 x Trailer for traffic services | Purchase of 1 x Trailer for traffic services | [5 empty] | OWN | 270000 | 0 | 0 | 44435 | 2021-12-15 | 2022-03-31 | 2022-06-30 | N/A |  | N/A
ESD-43 | Purchase of the Mayor’s vehicle | Purchase of the Mayor’s vehicle | [5 empty] | OWN | 750000 | 0 | 0 | 44435 | 2021-12-15 | 2022-03-31 | 2022-06-30 | N/A | Consulting Engineers appointed | N/A
ESD-44 | Purchase of the Speaker’s vehicle | Purchase of the Speaker’s vehicle | [5 empty] | OWN | 750000 | 0 | 0 | 44435 | 2021-12-15 | 2022-03-31 | 2022-06-30 | N/A |  | N/A
ESD-45 | Construction of New ablution block, offices and storage facility at Tzaneen testing grounds | Construction of New ablution block (4 x male and 4 female), offices and storage facility at Tzaneen testing grounds, | [5 empty] | OWN | 1000000 | 0 | 0 | 44435 | 2021-12-15 | 2022-03-31 | 2022-06-30 | N/A |  | N/A
ESD-46 | Refurbishment of Nkowankowa testing grounds | Painting inside, floor tiles access gate and fence | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
0 | Refurbishment of Tzaneen testing grounds | Painting inside, floor tiles, access gate and fence | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-47 | Additional toilet block and change rooms in parks | New ablution block and change rooms | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-48 | Shiluvane and Mulati library | Carports and Guardroom and painting, tiling and repairs to leaking roof | [5 empty] | OWN | 0 | 0 | 500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-49 | Refurbishment of public toilets in Tzaneen | New floor tiles, painting, security , gates | [5 empty] | OWN | 0 | 0 | 700000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-50 | Refurbishment of public toilets in Nkowa nkowa | New floor tiles, painting, security gates | [5 empty] | OWN | 0 | 0 | 200000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-51 | Refurbishment of public toilets in Letsitele | New floor tiles, painting, security gates | [5 empty] | OWN | 0 | 0 | 200000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-53 | New toilet block in Sanlam centre | New ablution block | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-54 | New sleeping quarters at Tzaneen dam | Sleeping quarters and new kitchen | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-55 | New sleeping quarters for electrical | Sleeping quarters and new kitchen | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-56 | New sleeping quarters at Georges valley treatment plant | Sleeping quarters and new kitchen | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-57 | New sleeping quarters at Nkowa nkowa plumbers workshop | Sleeping quarters and new kitchen | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-58 | New sleeping quarters at Tzaneen plumbers workshop | Sleeping quarters and new kitchen | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-59 | New sleeping quarters at Letsitele water treatment works | Sleeping quarters and new kitchen | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-60 | Airfield fencing | New concrete palisade fencing | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-61 | Refurbishment of mechanical workshop | Painting of the entire workshop, revamping for heavy vehicles and paving road to workshop | [5 empty] | OWN | 0 | 0 | 1000000 | N/A | N/A | N/A | N/A | N/A | Designs completed | N/A
ESD-62 | Purchase of Diagnostic machine for the workshop and replacement of hydrolicjack and toolbox | mechanical tools for the workshop | [5 empty] | OWN | 0 | 0 | 500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-63 | Upgrading of the chlorine dosage rooms for all water treatment plant | New installation extracor fans for chlorine and sensors for chlorine | [5 empty] | OWN | 0 | 0 | 300000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-64 | Upgrading of the chlorine dosage rooms for all water treatment plant | New installation extracor fans for chlorine and sensors for chlorine | [5 empty] | OWN | 0 | 0 | 300000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-65 | Erection of concrete palisade fence at Lenyenye | Erection of concrete palisade fence at Lenyenye | [5 empty] | OWN | 2000000 | 0 | 0 | 44435 | 2021-12-15 | 2022-03-31 | 2022-06-30 | N/A |  | N/A
ESD-66 | Ablution block with change room at Lesedi Regional Cemetery (Lenyenye) | Construction of ablution facility at cemetery between Lesedi Regional cemetery (Lenyenye) | [5 empty] | OWN | 0 | 0 | 150000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-67 | Storeroom with guard house at Lesedi Regional cemetery (Lenyenye) | Construction of Storeroom with ablution at Lesedi Regional cemetery (Lenyenye) | [5 empty] | OWN | 0 | 0 | 800000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-68 | Environmental Impact Study at Lesedi Regional Cemetery (Lenyenye | Conducting Environmental impact study and monitoring construction of the cemetery | [5 empty] | OWN | 0 | 0 | 400000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-69 | Earthworks at Lesedi Regional cemetery (Lenyenye) | Mass excavation to remove unsuitable material & replacing it with suitable material from commercial sources including compaction. conducting full Environmental Impact study | [5 empty] | OWN | 0 | 0 | 1000000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-70 | Construct ablution with change room at Nkowankowa cemetery | Construction of ablution facility with change room | [5 empty] | OWN | 0 | 0 | 1200000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-71 | Earthworks with full Environmental Impact Assessment study and designs at Nkowankowa cemetery | Mass excavation to remove unsuitable material & conducting Environmental Impact study | [5 empty] | OWN | 0 | 0 | 1000000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-72 | Fence Agatha cemetery extension at Tzaneen | Fencing Agatha cemetery extension | [5 empty] | OWN | 0 | 0 | 1000000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-73 | Earthworks with road construction at Tzaneen | Mass excavation to remove unsuitable material | [5 empty] | OWN | 0 | 0 | 1000000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-75 | Guardroom at Nkowa nkowa testing ground | Construction of new guard house | [5 empty] | OWN | 0 | 0 | 500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-76 | Guardroom at Tzaneen testing ground | Construction of new guard house | [5 empty] | OWN | 0 | 0 | 500000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-77 | Erection of concrete palisade fence at Nkowakowa cemetery | Erection of concrete palisade fence at Nkowakowa cemetery | [5 empty] | OWN | 2000000 | 0 | 0 | 44435 | 2021-12-15 | 2022-03-31 | 2022-06-30 | N/A |  | N/A
ESD-78 | Clear view fencing at Tzaneen cemetery | Construction pf new clear view fencing | [5 empty] | OWN | 0 | 0 | 1600000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-79 | Archive storage at Tzaneen testing ground | Construction of new archive storage | [5 empty] | OWN | 0 | 0 | 1200000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-80 | Heanertzburg library sleeping quarters | Contrsuction fo sleeping quarters and kitchen | [5 empty] | OWN | 0 | 0 | 1500000 | N/A | N/A | N/A | N/A | N/A | Tender processes underway | N/A
ESD-81 | Construction of ablution facility at Tzaneen | Construction of ablution facility | [5 empty] | OWN | 0 | 0 | 800000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-82 | Furniture for sport and recreation facilities at Juliesberg, Burgersdorp, Runnymede, Lenyenye, Nkowankowa | Purchasing furniture for sport & recreation facilities | [5 empty] | OWN | 0 | 0 | 300000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-83 | Construction of Clear view Fencing at Civic Centre and Stores | Construction of Clear view Fencing at Civic Centre and Stores | [5 empty] | OWN | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-84 | Construction of civic centre roof | Construction of civic centre roof | [5 empty] | OWN | 4000000 | 0 | 0 | N/A | N/A | 2021-07-01 | 2021-11-30 | N/A |  | N/A
ESD-85 | Upgrading of civic centre building | Upgrading of civic centre building | [5 empty] | OWN | 0 | 0 | 10000000 | N/A | N/A | N/A | N/A | N/A |  | N/A
ESD-86 | Renovation of Nkowakowa offices (Old Home Affairs building) | Renovation of Nkowakowa offices (Old Home Affairs building) | [5 empty] | OWN | 0 | 800000 | 0 | N/A | N/A | N/A | N/A | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A | Tender advertised for installation of clearvu fencing | N/A
[16 empty] | N/A | Tender advertised for construction | N/A
[16 empty] | N/A |  | N/A
[16 empty] | N/A |  | N/A

## CORPORATE SERVICES
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MATLALA BS
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2020/2021 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022' | 2022/2023' | 2023/2024' | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
CORPORATE SERVICES
| MICROSOFT CORPORATION (MICROSOFT PRODUCTS) | MICROSOFT CORPORATION (MICROSOFT PRODUCTS) | OPERATIONAL |  | 1400000 |  | Own funds | OWN |  |  |  | 2020-07-01 | 2020-07-01
| LEASE PHOTOCOPIER MACHINE | LEASE PHOTOCOPIER MACHINE | OPERATIONAL |  | R 2 200 000.00 ANNUALLY |  | Own funds | OWN |  |  |  | 2021-02-01 | 2021-04-01
| MIMECAST (EMAILS & SECURITY) | MIMECAST (EMAILS & SECURITY) | OPERATIONAL |  | R 360.000, |  | Own funds | OWN |  |  |  | 2021-01-01 | 2021-03-01
. | ORGPLUS | ORGPLUS | OPERATIONAL |  | 15000 |  | OWN funds | OWN |  |  |  | 2020-11-01 | 2020-11-01
| SITA | SITA | OPERATIONAL |  | R 80 000 ANNUALLY |  | OWN funds | OWN |  |  |  | 2020-01-01 | 2020-02-01
| PAYDAY (EMPLOYEE MANAGEMENT SYSTEM) | PAYDAY (EMPLOYEE MANAGEMENT SYSTEM) | OPERATIONAL |  | R 200 000 |  | Own funds | OWN |  |  |  | 2020-07-01 | 2020-07-01
| VODACOM (INTERNET LINE) | VODACOM (INTERNET LINE) | OPERATIONAL |  |  |  | Own funds | OWN |  |  |  | 2020-07-01 | 2020-07-01
1
2
3
4
5
6
7
8
9
10

## COMMUNITY SERVICES
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MATLALA BS
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2020/2021 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2020/2021 | 2021/2022 | 2022/2023 | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
COMMUNITY SERVICES
CSD-112 | Purchase of speed measuring instrument | Purchase of speed measuring instrument | [5 empty] | OWN
CSD-113 | Purchase of Computers for traffic administration | Purchase of Computers for traffic administration | [5 empty] | OWN
CSD-114 | Purchase of Printers for traffic administration | Purchase of Printers for traffic administration | [5 empty] | OWN
CSD-115 | Purchase of traffic light controllers for law enforcement administration | Purchase of traffic light controllers for red traffic light offenders | [5 empty] | OWN
CSD-116 | Purchase of Electronic National and Traffic and Information System terminal and equipment | Purchase of ENaTIS terminal and equipment | [5 empty] | OWN
CSD 117 | Cash - In- Transist Banking Services | Collection of Cash and Banking Services | [5 empty] | OWN | 2020/2021 |  |  |  |  | None |  | Readvert | Bid period expired
CSD 118 | Surveilance Cameras | Surveilance Security for Strategic areas | [5 empty] | OWN |  | 2021/2022 |  |  |  | None |  | Tender was advertised 3 times without award
CSD 119 | Physical Security | Provision of physical security at GTM premises | [5 empty] | OWN | 2021/2022 |  |  |  |  | None |  | Not yet completed BEC | Awaiting to complete BEC process
CSD 120 | Security Measures | Provision of Security Measures for GTM Substations | [5 empty] | OWN |  | 2021/2022 |  |  |  | 01/04/2019 | 31/03/2022 | None | Contract in effect

## PED
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MATLALA BS
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2020/2021 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022 | 2022/2023 | 2023/2024 | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
PED
| Erf 2379 Lenyenye: proposed development | Developemnt of erf 2379 Lenyenye for settlement | Capital
| erf 1730 nkowwankowa-A | Request for proposal for the development of ERF 1730 Nkowankowa A | Capital
| Jetty 3 | Request for proposal of managing of Jetty 3 dam | Capital
| Erf 2993Tzaneen, for development | Request for development for commercial purposes | Capital
| Erf 590 Tzaneen | Request for proposal for development of ERF 590 Tzaneen | Capital
PED-7 | Purchase of Geographical Information Systems | Purchase of Geographical Information Systems | Capital |  | 2800000 |  |  |  | 2800000 | 4000000 | 4000000

## GTEDA
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
GTEDA
GTEDA-117 | Purchase of MSCOA printers Equipment | Purchase of MSCOA printers Equipment | 258500 |  | 235000 |  |  | OWN

## Compatibility Report
Compatibility Report for PROCUREMENT PLAN FOR 2021 2022.xls
Run on 2021/03/25 11:16
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 18 | Excel 97-2003