## Cover Page
2nd Quarter Report Performance Report January 2013
Service Delivery and Budget Implementation Plan (SDBIP)
2012/2013
GREATER TZANEEN MUNICIPALITY
Approved: 20 June 2012

## Contents
TABLE OF CONTENTS
Page
Introduction & Approval | 3
Monthly Revenue Projections by source | 4
Monthly Expenditure by vote | 6
Quarterly Summary of Projected Revenue and Expenditure by Vote | 12
Summary of Mid-year Financial Performance | 14
Capital Funding by source & Expenditure by Vote | 15
Service Delivery Targets (KPIs & Projects) - Office of the Municipal Manager | 16
Service Delivery Targets (KPIs & Projects) - Chief Financial Officer | 27
Service Delivery Targets (KPIs & Projects) - Corporate Services | 32
Service Delivery Targets (KPIs & Projects) - Office of the Mayor | 41
Service Delivery Targets (KPIs & Projects) - Electrical Engineering | 45
Service Delivery Targets (KPIs & Projects) - Engineering Services | 49
Service Delivery Targets (KPIs & Projects) - Community Services | 60
Service Delivery Targets (KPIs & Projects) - Planning and Economic Development | 73
Capital Works Plan | 85
Risk Management | 89

## Introduction
INTRODUCTION & APPROVAL
The Service Delivery and Budget Implementation Plan (SDBIP) is developed in terms of the Municipal Finance Management Act (Act no.56 of 2003). In terms of the MFMA Circular 13 of the National Treasury, "the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA." The budget gives effect to the strategic priorities of the municipality and it is therefore important to supplement the budget and the IDP with a management and implementation plan, therefore the SDBIP. The SDBIP serves as the commitment by Council to reaching the service delivery targets as set in the Integrated Development plan (IDP) in an attempt to address the needs expressed by the community. The SDBIP is therefore developed annually to form the basis for monitoring and measuring the performance of the Municipality against quarterly service delivery targets and budget projections. The SDBIP is therefore a vital link between the Mayor, Council and the Administration and a tool to hold Management accountable for its performance in terms of execution of the budget and the performance of Senior Management in the achievement of the strategic objectives as set by Council. The SDBIP therefore also forms the basis of the Performance Agreements of the Municipal Manager and other Senior Managers. Quarterly progress reports will be submitted to Council based on the SDBIP to serve as an early warning mechanism to ensure that non-compliance to service delivery commitments is addressed in time.

## Revenue
Monthly Revenue projections by source for 2012/13
Source | Jul '12 | Aug '12 | Sep '12 | Oct '12 | Nov '12 | Dec '12 | Jan '13 | Feb '13 | Mar '13 | Apr '13 | May '13 | Jun '13 | TOTAL
| Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected | Projected
Property rates | 4167050.1496 | 4257581.7355 | 4133909.3603 | 4260347.2993 | 4151919.5194 | 4224587.4778 | 4227457.721 | 4427395.652 | 4623710.2747 | 5168841.8346 | 4159492.9717 | 4197706.0041 | 52000000
Penalties imposed and collection charges on rates | 236831.5995 | 237029.5149 | 237086.3943 | 220205.3445 | 263956.2871 | 274586.5353 | 277817.6467 | 285451.2458 | 270936.5812 | 323057.5603 | 297744.5805 | 275296.7099 | 3200000
Service charges | 31119326.8399 | 31656706.2333 | 31666759.3111 | 30045889.0874 | 29733808.7044 | 30368996.5597 | 29524403.9203 | 29028340.5088 | 30000040.9566 | 31144108.7213 | 29931995.2106 | 30332323.9466 | 364552700
Rent of facilities and equipment | 18606.2174 | 18714.6169 | 19828.0317 | 24765.0712 | 24245.5132 | 19777.8264 | 21527.0195 | 31668.5725 | 20993.3365 | 18068.4319 | 19982.7039 | 20922.6588 | 259100
Interest earned - external investments | 16190.3774 | 153848.6371 | 154116.5425 | 100738.2775 | 0 | 1000 | 65852.6881 | 0 | 0 | 10321.6429 | 148149.8082 | 350782.0264 | 1001000
Interest earned - outstanding debtors | 1219678.3971 | 1219900.431 | 1281872.8289 | 1191694.024 | 1293966.1097 | 1406620.1121 | 1346840.0563 | 1368986.369 | 1197300.9934 | 1461967.5705 | 1400376.7959 | 1610796.312 | 16000000
Fines | 134548.139 | 170728.3323 | 105974.4604 | 459596.8515 | 353613.3668 | 376175.5061 | 429606.3813 | 256123.211 | 272389.401 | 151170.2874 | 365184.8225 | 135025.2407 | 3210136
Licenses and Permits | 42411.4621 | 36730.4782 | 21741.2698 | 33514.4055 | 15286.5765 | 15012.8886 | 23247.0118 | 13465.1127 | 41584.8822 | 31680.7229 | 27340.2261 | 42984.9635 | 345000
Income from Agency services | 3320122.5493 | 3699834.5033 | 3489456.9953 | 3956737.4345 | 3188256.9312 | 3313875.728 | 4806555.8635 | 3646564.7683 | 4043244.5302 | 3145525.5701 | 3686420.7023 | 4151654.425 | 44448250.001
Operating grants and subsidies | 111608707.2675 | 2324358 | 2321571 | 2321571 | 88528372.913 | 2321571 | 0 | 0 | 64157848.8395 | 0 |  |  | 273584000.02
Other Revenue | 429182.0087 | 460322.6117 | 445826.3989 | 435815.0884 | 389741.8585 | 455647.6983 | 461073.3231 | 453985.4375 | 439294.7642 | 445317.4478 | 390110.9037 | 396885.4594 | 5203203
Gain on disposal of property, plant and equipment | 0 | 0 | 0 | 0 | 0 | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | 2300000
Income foregone | -711801.6846 | -659485.1367 | -643060.946 | -732920.0138 | -719079.5659 | -732518.7879 | -729499.146 | -850419.1826 | -753156.9338 | -871057.7973 | -734845.644 | -753155.1614 | -8891000
Total Revenue | 151600853.3228 | 43576269.9577 | 43235081.6471 | 42317953.8699 | 127224088.2138 | 44345332.5444 | 40454882.4856 | 38661561.695 | 104314187.6259 | 41029001.9925 | 39691953.0813 | 40761222.585 | 757212389.021
Monthly Actual Revenue by source for 2012/13
Source | Jul '12 | Aug '12 | Sep '12 | Oct '12 | Nov '12 | Dec '12 | Jan '13 | Feb '13 | Mar '13 | Apr '13 | May '13 | Jun '13 | TOTAL
| Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
Property rates | 5372677.83 | 6008027.88 | 5469043.77 | 5717404.94 | 5762716.47 | 5772175.65 | [6 empty] | 34102046.54
Penalties imposed and collection charges on rates | 266398.95 | 340976.81 | 355825.52 | 355891.19 | 358074.8 | 361474.68 | [6 empty] | 2038641.95
Service charges | 35409843.74 | 36967836.44 | 36547424.5 | 28932859.48 | 28548406.1 | 28917221.95 | [6 empty] | 195323592.21
Rent of facilities and equipment | 62532.43 | 67301.26 | 40004.37 | 392026.75 | 63514.61 | 157578.03 | [6 empty] | 782957.45
Interest earned - external investments | 91977.74 | 499134.4 | 522267.27 | 286885.5 | 365235.59 | 111487.43 | [6 empty] | 1876987.93
Interest earned - outstanding debtors | 889508.38 | 1269031.28 | 1319546.36 | 1216408.78 | 1506210.69 | 1305791.78 | [6 empty] | 7506497.27
Fines | 40276.43 | 344229.61 | 185547.9 | 357123.26 | 129851.95 | 75942.41 | [6 empty] | 1132971.56
Licenses and Permits | 47991.18 | 44029.97 | 34680.32 | 74893.53 | 37276.1 | 17638.91 | [6 empty] | 256510.01
Income from Agency services | 3523555.25 | 3349441.1 | 2852531.68 | 4036935.6 | 2818268.44 | 297719.01 | [6 empty] | 16878451.08
Operating grants and subsidies | 104239000 | 0 | 1293000 | 7992000 | 6300000 | 72267000 | [6 empty] | 192091000
Other Revenue | 2579.32 | 28452.26 | 181072.73 | 458145.43 | 1274133.09 | 18356.57 | [6 empty] | 1962739.4
Gain on disposal of property, plant and equipment | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
Income foregone | -797642.53 | -1089830.78 | -538383.77 | -845898.01 | -824712.33 | -853349.03 | [6 empty] | -4949816.45
Total Revenue | 149148698.72 | 47828630.23 | 48262560.65 | 48974676.45 | 46338975.51 | 108449037.39 | [6 empty] | 449002578.95

## Exenditure
Monthly Projected Ependiture by Vote 2012/13
| 2012-07-01 |  |  | 2012-08-01 |  |  | 2012-09-01 |  |  | 2012-10-01 |  |  | 2012-11-01 |  |  | 2012-12-01 |  |  | 2013-01-01 |  |  | 2013-02-01 |  |  | 2013-03-01 |  |  | 2013-04-01 |  |  | 2013-05-01 |  |  | 2013-06-01 |  |  | Total
| Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev
Vote | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000
Municipal Manager | 878383.5613 |  |  | 713384.5633 |  |  | 475667.9587 |  |  | 667039.554 |  |  | 1855871.5582 |  |  | 570152.7188 | 500000 |  | 461260.032 |  |  | 377928.5743 |  |  | 552088.8736 |  |  | 450521.4893 |  |  | 430856.8504 |  |  | 537223.1367 | 0 |  | 7970378.8707 | 500000 | 0
Executive and Council | 1795542.0463 |  | 0 | 2608764.2145 |  | 0 | 1863408.8097 |  | 0 | 1849325.2583 |  | 0 | 1903146.383 |  | 0 | 2653968.0086 |  | 0 | 2164077.0299 |  | 0 | 1813192.1974 |  | 1000 | 1853104.8151 |  | 100 | 1816143.5914 |  | 0 | 1571741.2871 |  | 0 | 2099890.7187 |  | 0 | 23992304.36 | 0 | 1100
Financial Services | 3574422.5248 |  | 86094157.8017 | 2819763.5441 |  | 5647364.6626 | 3537498.4886 |  | 6259562.8612 | 7195956.0674 |  | 5506751.5141 | 5112944.1182 |  | 68342055.2432 | 9642316.0427 | 500000 | 7976629.621 | 3068145.655 |  | 5679034.9127 | 1711968.0455 |  | 5717232.4563 | 3437968.2542 |  | 52856202.2553 | 3927417.5732 |  | 6562543.9763 | 3577214.3857 |  | 5692562.3428 | 3163356.2513 | 1000000 | 6263888.3529 | 50768970.9507 | 1500000 | 262597986
Corporate Services | 2825603.2333 |  | 0 | 3183930.053 |  | 167.1786 | 2314534.0847 |  | 133.9286 | 2698892.7243 |  | 8.9286 | 3249105.9644 |  | 0 | 3000417.7908 | 500000 | 0 | 2446487.8429 |  | 0 | 3341127.6693 |  | 71.4286 | 3225667.4252 |  | 48.75 | 2687569.9829 |  | 17.8571 | 3193253.0212 |  |  | 2987466.8805 |  |  | 35154056.6724 | 500000 | 448.0714
Planning and Economic Development | 1945137.0197 |  | 2552158.2052 | 1345794.9694 |  | 45146.7297 | 1614216.9457 | 518954.1732 | 40879.1766 | 976604.5841 | 471886.532 | 48800.9984 | 1171821.0721 | 1027543.3034 | 1467459.5109 | 2198533.176 | 1779481.2233 | 36063.9593 | 942753.4172 | 221877.4535 | 42021.4753 | 1084944.4143 | 175687.1235 | 34875.7115 | 1721275.4387 |  | 1116990.3739 | 836393.0805 | 201464.8434 | 37138.2654 | 1093356.6016 | 159661.3397 | 39962.3885 | 3393700.9795 | 943444.0079 | 52158.2052 | 18324531.6988 | 5500000 | 5513655
Community Services | 4850704.1884 |  | 4944358.1885 | 7495800.6764 |  | 1906992.6826 | 6805531.0621 |  | 1857751.1508 | 7155072.4361 |  | 1904638.4984 | 5926194.0268 |  | 4109633.8149 | 9796831.5998 | 500000 | 1811132.5973 | 5810225.8174 |  | 1694362.3026 | 6825406.5186 |  | 1669658.8965 | 7514670.4909 |  | 3590937.2144 | 6499294.1581 |  | 1702507.6642 | 5821968.1702 |  | 1707432.4126 | 6388699.806 |  | 1699074.5972 | 80890398.9508 | 500000 | 28598480.02
Engineering Services | 4431700.8071 | 2079517.0971 | 23002675.0197 | 10421435.516 | 2394582.9184 | 53891.3786 | 13191029.4101 | 5396001.3105 | 46757.6736 | 10551899.5126 | 794560.3171 | 54015.1458 | 11078653.6835 | 6094570.9238 | 19596584.331 | 15499158.226 | 7017873.7224 | 42470.4396 | 6685808.9508 | 3838696.3182 | 46324.9995 | 5157718.6399 | 8648717.9016 | 52989.4809 | 11775098.8992 | 13308756.966 | 14222317.9472 | 8316461.9358 | 12788986.3953 | 54316.5858 | 10790071.6238 | 13297206.1987 | 49927.8528 | 11413286.8531 | 8995357.9309 | 55054.1455 | 119312324.0579 | 84654828 | 57277325
Transport, Safety, Security and Liaison | 2889636.2596 |  | 3441464.5294 | 4859434.7311 |  | 3845965.3038 | 4508397.3367 |  | 3580224.5559 | 4910704.091 |  | 4392802.7132 | 5075330.3665 |  | 3529407.5559 | 5453125.0583 |  | 3672992.607 | 4464526.706 |  | 5221562.3914 | 5562997.0901 |  | 3888009.2656 | 6108892.1136 |  | 4305798.759 | 5277194.4622 |  | 3286104.6285 | 4959111.3786 |  | 4035886.2629 | 5449777.2361 |  | 4274031.4286 | 59519126.83 | 0 | 47474250.001
Electrical Engineering | 27254330.9385 |  | 31566039.5783 | 32169848.7869 | 593087 | 32076742.0219 | 27798336.1861 | 871731 | 31449772.3004 | 29562131.4761 | 2804612.9676 | 30410936.0716 | 30428127.4897 | 819576.5149 | 30178947.7579 | 37340726.4419 | 5000000 | 30806043.3203 | 23805480.4069 | 4000000 | 27771576.4041 | 28220898.1239 | 5330989.778 | 27297724.4556 | 26407465.8814 | 2500000 | 28221792.3261 | 27819160.6072 | 1000000 | 29386373.0151 | 24679112.3508 | 1500000 | 28166181.8217 | 30535419.2795 | 1080002.7395 | 28417006.9269 | 346021037.9688 | 25500000 | 355749136
Total By Vote | 50445460.579 | 2079517.0971 | 151600853.3228 | 65618157.0546 | 2987669.9184 | 43576269.9577 | 62108620.2824 | 6786686.4838 | 43235081.6471 | 65567625.704 | 4071059.8167 | 42317953.8699 | 65801194.6623 | 7941690.7422 | 127224088.2138 | 86155229.0629 | 15797354.9456 | 44345332.5444 | 49848765.8581 | 8060573.7717 | 40454882.4856 | 54096181.2733 | 14155394.8031 | 38661561.695 | 62596232.1919 | 15808756.966 | 104314187.6259 | 57630156.8807 | 13990451.2387 | 41029001.9925 | 56116685.6695 | 14956867.5384 | 39691953.0813 | 65968821.1414 | 12018804.6782 | 40761213.6564 | 741953130.36 | 118654828 | 757212380.0924
Monthly Actual Ependiture by Vote 2012/13
| 2012-07-01 |  |  | 2012-08-01 |  |  | 2012-09-01 |  |  | 2012-10-01 |  |  | 2012-11-01 |  |  | 2012-12-01 |  |  | 2013-01-01 |  |  | 2013-02-01 |  |  | 2013-03-01 |  |  | 2013-04-01 |  |  | 2013-05-01 |  |  | 2013-06-01 |  |  | Total
| Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev
Vote | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000
Municipal Manager | 685391.03 |  |  | 520569.82 |  |  | 437779.31 |  |  | 431529.25 |  |  | 619656.13 |  |  | 714086.33 | [20 empty] | 3409011.87 | 0 | 0
Executive and Council | 1735460.17 |  |  | 3249838.15 |  |  | 1689142.57 |  |  | 1720370.6 |  |  | 1875016.51 |  |  | 2120547.03 | [20 empty] | 12390375.03 | 0 | 0
Financial Services | 3552342.31 |  | 89263289.74 | 537880.17 |  | 7213168.06 | 3296787.62 |  | 8265785.92 | 4233245.97 | 0 | 7350137.24 | 5284292.48 | 10510.87 | 9130626.66 | 3962492.59 | 0 | 58494445.9 | [18 empty] | 20867041.14 | 10510.87 | 179717453.52
Corporate Services | 2212921.89 |  |  | 4048571 |  | 9 | 3406729.05 | 6000 | 9 | 4327310.3 | 7890 |  | 4021936.28 | 0 |  | 2994452.53 | 2638 | [19 empty] | 21011921.05 | 16528 | 18
Planning and Economic Development | 863099.9 |  | 15510 | 1258363.81 | 238000 |  | 1320600.91 |  | 17170 | 1404095.18 | 1288018.53 | 15480 | 2962180.14 | 634588.75 | 5007770 | 1680211.2 | 553498.96 | 0 | [18 empty] | 9488551.14 | 2714106.24 | 5055930
Community Services | 4827475.14 |  | 1499254 | 7111438.02 |  | 1897327.29 | 5689163.59 |  | 2299533.03 | 4894053.35 |  | 2543175.18 | 7645788.23 |  | 1978174.93 | 9161947.27 |  | 1874148.56 | [18 empty] | 39329865.6 | 0 | 12091612.99
Engineering Services | 6203032.28 | 2215442 | 21292822.61 | 10305190.87 | 2994272.49 | 107361.23 | 9126357 | 2818745.27 | 170661.69 | 7938950.91 | 4586926.94 | 1511431.28 | 7987517.58 | 1772.62 | -1092270.29 | 9255456.63 | 2225727.99 | 19736366.94 | [18 empty] | 50816505.27 | 14842887.31 | 41726373.46
Transport, Safety, Security and Liaison | 2466911.22 |  | 3553516 | 5303773.76 |  | 3675225.74 | 5077452.82 |  | 3021001.68 | 4458405.68 |  | 4372413.59 | 7402503.58 |  | 2926859.53 | 4869777.35 |  | 344298.09 | [18 empty] | 29578824.41 | 0 | 17893314.63
Electrical Engineering | 6201115.63 |  | 33524305.85 | 36901275.33 |  | 34935538.91 | 44579305.68 | 17231.62 | 34488399.33 | 21494959.25 | 29877.12 | 33182039.16 | 29104877.18 | 327310.15 | 28387814.68 | 22291996.16 | 291912.74 | 27999777.9 | [18 empty] | 160573529.23 | 666331.63 | 192517875.83
Total By Vote | 28747749.57 | 2215442 | 149148698.2 | 69236900.93 | 3232272.49 | 47828630.23 | 74623318.55 | 2841976.89 | 48262560.65 | 50902920.49 | 5912712.59 | 48974676.45 | 66903768.11 | 974182.39 | 46338975.51 | 57050967.09 | 3073777.69 | 108449037.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347465624.74 | 18250364.05 | 449002578.43

## Qtr Rev & Exp
Quarterly Summary of Projected Revenue and Expenditure by Vote (2012/13)
Vote | Quarter ending 30 September 2012 |  |  | Quarter ending 31 December 2012 |  |  | Quarter ending 31 March 2013 |  |  | Quarter ending 30 June 2013 |  |  | Total
| Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev
| R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000
Municipal Manager | 2067436.0834 | 0 | 0 | 3093063.831 | 500000 | 0 | 1391277.4799 | 0 | 0 | 1418601.4765 | 0 | 0 | 7970378.8707 | 500000 | 0
Executive and Council | 6267715.0705 | 0 | 0 | 6406439.6499 | 0 | 0 | 5830374.0424 | 0 | 1100 | 5487775.5973 | 0 | 0 | 23992304.36 | 0 | 1100
Financial Services | 9931684.5576 | 0 | 98001085.3254 | 21951216.2283 | 500000 | 81825436.3783 | 8218081.9546 | 0 | 64252469.6243 | 10667988.2102 | 1000000 | 18518994.672 | 50768970.9507 | 1500000 | 262597986
Corporate Services | 8324067.3709 | 0 | 301.1071 | 8948416.4794 | 500000 | 8.9286 | 9013282.9374 | 0 | 120.1786 | 8868289.8847 | 0 | 17.8571 | 35154056.6724 | 500000 | 448.0714
Planning and Economic Development | 4905148.9348 | 518954.1732 | 2638184.1115 | 4346958.8322 | 3278911.0587 | 1552324.4686 | 3748973.2702 | 397564.577 | 1193887.5608 | 5323450.6615 | 1304570.1911 | 129258.8592 | 18324531.6988 | 5500000 | 5513655
Community Services | 19152035.9269 | 0 | 8709102.0219 | 22878098.0627 | 500000 | 7825404.9106 | 20150302.8269 | 0 | 6954958.4135 | 18709962.1343 | 0 | 5109014.674 | 80890398.9508 | 500000 | 28598480.02
Engineering Services | 28044165.7331 | 9870101.326 | 23103324.0719 | 37129711.4221 | 13907004.9633 | 19693069.9163 | 23618626.4899 | 25796171.1859 | 14321632.4276 | 30519820.4127 | 35081550.5248 | 159298.5842 | 119312324.0579 | 84654828 | 57277325
Transport | 12257468.3274 | 0 | 10867654.3891 | 15439159.5158 | 0 | 11595202.8761 | 16136415.9098 | 0 | 13415370.4159 | 15686083.077 | 0 | 11596022.32 | 59519126.83 | 0 | 47474250.001
Electrical Engineering | 87222515.9115 | 1464818 | 95092553.9006 | 97330985.4077 | 8624189.4825 | 91395927.1498 | 78433844.4122 | 11830989.778 | 83291093.1858 | 83033692.2374 | 3580002.7395 | 85969561.7638 | 346021037.9688 | 25500000 | 355749136
Total By Vote | 178172237.916 | 11853873.4992 | 238412204.9276 | 217524049.4291 | 27810105.5045 | 213887374.6282 | 166541179.3233 | 38024725.5409 | 183430631.8065 | 179715663.6916 | 40966123.4553 | 121482168.7302 | 741953130.36 | 118654828 | 757212380.0924
Quarterly Summary of Actual Revenue and Expenditure by Vote (2012/13)
Vote | Quarter ending 30 September 2012 |  |  | Quarter ending 31 December 2012 |  |  | Quarter ending 31 March 2013 |  |  | Quarter ending 30 June 2013 |  |  | Total
| Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev | Opex | Capex | Rev
| R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000 | R '000
Municipal Manager | 1643740.16 |  |  | 1765271.71 | 0 | 0 | [6 empty] | 3409011.87 | 0 | 0
Executive and Council | 6674440.89 |  |  | 5715934.14 | 0 | 0 | [6 empty] | 12390375.03 | 0 | 0
Financial Services | 7387010.1 |  | 104742243.72 | 13480031.04 | 10510.87 | 74975209.8 | [6 empty] | 20867041.14 | 10510.87 | 179717453.52
Corporate Services | 9668221.94 | 6000 | 18 | 11343699.11 | 10528 | 0 | [6 empty] | 21011921.05 | 16528 | 18
Planning and Economic Development | 3442064.62 | 238000 | 32680 | 6046486.52 | 2476106.24 | 5023250 | [6 empty] | 9488551.14 | 2714106.24 | 5055930
Community Services | 17628076.75 |  | 5696114.32 | 21701788.85 | 0 | 6395498.67 | [6 empty] | 39329865.6 | 0 | 12091612.99
Engineering Services | 25634580.15 | 8028459.76 | 21570845.53 | 25181925.12 | 6814427.55 | 20155527.93 | [6 empty] | 50816505.27 | 14842887.31 | 41726373.46
Transport | 12848137.8 |  | 10249743.42 | 16730686.61 | 0 | 7643571.21 | [6 empty] | 29578824.41 | 0 | 17893314.63
Electrical Engineering | 87681696.64 | 17232 | 102948244.09 | 72891832.59 | 649100.01 | 89569631.74 | [6 empty] | 160573529.23 | 666332.01 | 192517875.83
Total By Vote | 172607969.05 | 8289691.76 | 245239889.08 | 174857655.69 | 9960672.67 | 203762689.35 | 0 | 0 | 0 | 0 | 0 | 0 | 347465624.74 | 18250364.43 | 449002578.43

## Financial Summary
Summary of Mid-year Financial Performance 2012/13
Item: Revenue Budget | Budget | Year to date receipt (30 Dec '12) | % Receipt
Grants & Subsidies | 318584000 | 192091000 | 60.3%
Rates & Taxes (billing) | 435695329 | 231236917 | 53.08%
Rates & Taxes (collection rate) | 231236917 | 222302071 | 96.13%
Debtors age analysis |  | 251292325
Bank Balance |  | 33872950.85
Initiative (Expenditure Budget) | Budget | Year do date expenditure (30 Dec '12) | % Spent
Salaries & Allowances | 192938336 | 103855952 | 53.83%
Remuneration of Councillors | 18036148 | 8792274 | 48.75%
Repairs & Maintenance | 139074684 | 57268710 | 41.18%
Bulk Purchases | 233753047 | 112986559 | 48.34%
Contracted Services | 69269801 | 27778906 | 40.1%
Operating Expenditure | 812803661 | 372326621 | 45.81%
General Expenses | 159731645 | 61644220 | 38.59%
Capital Expenditure | 118654828 | 18250364 | 15.38%
Initiative : Conditional Grants | Budget | Year do date expenditure | % Spent
FMG | 1500000 | 1393016 | 92.87%
INEP | 13000000 | 3295101 | 33.18
NDPG | 5000000 | 4163761 | 83.28
MSIG | 800000 | 354034 | 44.25
Free Basic Services | 15000000 | 9695503
MIG | 56665000 | 11921708 | 29.24
EPWP | 935000 | 643816 | 69.86

## Capex Sum
2012/13 Capital Funding by source |  |  | 2012/13 Capital Allocation by vote
Funding Source | R '000 | % | Vote | R '000 | %
MIG | 54526 | 45.95% | Community Services | 500 | 0.4214%
Own Source | 29129 | 24.55% | Corporate Services | 500 | 0.4214%
Grant | 5000 | 4.214% | Chief Financial Officer | 1500 | 1.264%
Loan | 30000 | 25.28% | Engineering Services | 84655 | 71.35%
Total | 118655 | 100% | Electrical Engineering | 25500 | 21.49%
|  |  | Municipal Manager | 500 | 0.4214%
|  |  | Planning and Economic Development | 5500 | 4.635%
|  |  | Total | 118655 | 100%
INSERT PIE CHART HERE |  |  | INSERT PIE CHART HERE

## MM KPIs
Key Performance Indicators (KPIs) - Office of the Municipal Manager
KPA/ Theme | Strategic Objective | Programme | Strategic KPI | Departmental KPI | Baseline (end June 2012) | Target Sept '12 | Actual Sept '12 | Target Dec '12 | Actual Dec '12 | Target Mar '13 | Target Jun '13 | Reason for deviation | Means of verification
BSD | Develop and build skilled and knowledgeable workforce | Capacity building and Training | % compliance to Workplace Skills plan |  | 15% | 25% | 13.8% | 50% | 25% | 75% | 100% | bulk of vote transferred to legal vote (R 400 000.00) | Workplace Skills Plan Training plan
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | % increase in households with access to electricity |  | new indicator | Reporting only - no target | Not available | Reporting only - no target | 87% | Reporting only - no target | Reporting only - no target | new projects are being implemented. | Electrification reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | R-value sourced to implement electricity recovery plan |  | 55350000 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 25000000 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Free Basic Services | % increase in households with access to free basic services |  | new indicator | Reporting only - no target | Not available | Reporting only - no target | Not available | Reporting only - no target | Reporting only - no target | All registered indigents households have access to basic services | Revenue reports
BSD | Improve access to sustainable and affordable services | Free Basic Services | %Increase in households with access to free electricity |  | 25000 | Reporting only - no target | Not available | Reporting only - no target | Not available | Reporting only - no target | Reporting only - no target | all registered indigents households have access to basic electricity via eskom | Revenue reports
BSD | Improve access to sustainable and affordable services | Free Basic Services | % of households with access to basic level of electricity |  | 75% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 83% |  | Records of correspondence
BSD | Improve access to sustainable and affordable services | Free Basic Services | % Households with access to basic level of waste management services |  | 10% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 11% |  | Solid waste Service schedules
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | % reduction in road backlog |  | new indicator | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 12% |  | Road completion reports
BSD | Improve access to sustainable and affordable services | Water and sanitation services | Number of water systems with Blue Drop Certification |  | 2 | 2 | 2 | 2 | 2 | 2 | 3 |  | Blue Drop Certificates
BSD | Optimise infrastructure investment and services | Maintenance of municipal assets | % capital budget spent on upgrading municipal assets |  | 72% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 100% |  | Monthly reports
BSD | Optimise infrastructure investment and services | Maintenance of municipal assets | % operational budget spent on repairs and maintenance |  | 13% | Reporting only - no target | 1.36 | Reporting only - no target | 7.05 | Reporting only - no target | 18.9% |  | Maintenance Expenditure Statement
BSD | Promote environmentally sound practices and social development | Disaster management |  | Annual Disaster Management report submitted to Council and MDM within legislated timeframes | January'12 | 31 July '12 | Not yet approved | Not applicable this quarter | Not yet approved | Not applicable this quarter | Not applicable this quarter | report was submitted to Council but Council referred it back to the Social and economic cluster. | Disaster Annual Report proof of submission to Council & MDM
BSD | Promote environmentally sound practices and social development | Disaster management |  | % disaster incidences responded to (relieved) within 72-hours | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Relief reports
BSD | Promote environmentally sound practices and social development | Environmental Health management | % compliance to the environmental legislation checklist |  | 76% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 80% |  | Environmental Checklist
BSD | Promote environmentally sound practices and social development | Library Services | # of new libraries developed |  | 0 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 1 | 1 |  | Shilovane & Molati building site reports Correspondence with DSAC
GG | Develop effective and sustainable stakeholder relations | Customer Care | % Community satisfaction rating |  | 50% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 50% |  | External Client Satisfaction Survey report
GG | Develop effective and sustainable stakeholder relations | Inter-governmental relations | % of MM forum and technical working group meeting resolutions implemented |  | 100% | 100% | 75% | 100% | 80% | 100% | 100% |  | Resolutions register
GG | Develop effective and sustainable stakeholder relations | Inter-governmental relations | # of quarterly reports from MDM council representatives |  | 0 | 1 | 0 | 2 | 0 | 3 | 4 |  | MDM Council reps reports
GG | Develop effective and sustainable stakeholder relations | Inter-governmental relations | % of premier IGR resolutions implemented |  | 100% | 100% | 75% | 100% | 80% | 100% | 100% |  | IGR resolution register and Quarterly Council reports Minutes of MM s forum
GG | Develop effective and sustainable stakeholder relations | Inter-governmental relations | % of district IGR forum and technical working group meeting resolutions implemented |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Minutes of meetings - Resolutions Register
GG | Develop effective and sustainable stakeholder relations | Inter-governmental relations | # of meetings with individual sector Departmens and State owned Enterprises |  | new indicator | 1 | 0 | 2 | 0 | 3 | 4 | IGR Held on a district level | Minutes and attendance registers
GG | Develop effective and sustainable stakeholder relations | Inter-governmental relations | # of District MM Forum attended |  | 1 | Reporting only - no target | 1 | Reporting only - no target | 1 | Reporting only - no target | Reporting only - no target |  | Minutes of meetings, attendance register & resolution register
GG | Effective and Efficient administration | Council Support | % of GTM Council resolutions implemented |  | 95% | 100% | 95% | 100% | 95% | 100% | 100% |  | Council annual program Resolution register
GG | Effective and Efficient administration | Fraud and Anti- corruption | # of cases of fraud and corruption reported |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fraud and Corruption reports
GG | Effective and Efficient administration | Fraud and Anti- corruption | % cases of fraud and corruption successfully dealt with |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Fraud and Corruption reports
GG | Effective and Efficient administration | Management and Administration |  | # Management meetings | 22 | 13 | 2 | 26 | 1 | 39 | 52 |  | Minutes of management meetings & Attendance Registers
GG | Effective and Efficient administration | Performance monitoring and reporting |  | # of audited Quarterly performance reports submitted to Council on time | 4 | 1 | 1 | 2 | 0 | 3 | 4 | Delays in the finalisation of reports does not allow sufficient time for auditing | Exco Agendas containing Quarterly Performance Reports
GG | Effective and Efficient administration | Performance monitoring and reporting |  | # of MM Departmental monthly reports submitted on time | 12 | 3 | 3 | 6 | 6 | 9 | 12 |  | Monthly, quarterly, half yearly and annual reports
GG | Effective and Efficient administration | Performance monitoring and reporting |  | % capital projects within budget | 100% | 100% | 50% | 100% | 60% | 100% | 100% | Project delays due to court interdict | Monthly reports
GG | Effective and Efficient administration | Performance monitoring and reporting |  | % of capital projects within time | 50% | 100% | 50% | 100% | 60% | 100% | 100% | Project delays due to court interdict | Monthly reports
GG | Effective and Efficient administration | Performance monitoring and reporting |  | % of capital projects within specifications | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Monthly reports
GG | Effective and Efficient administration | Regulatory Framework | # of By-laws gazetted |  | new indicator | 3 | 0 | 6 | 0 | 9 | 12 | No bylaws gazetted | By-Law Register Report on contravention legal action
GG | Effective and Efficient administration | Regulatory Framework | # of policies approved |  | new indicator | Reporting only - no target | 0 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target | No policies were referred to by depts to Legal. | Policy register
GG | Effective and Efficient administration | Risk management | % of identified risks addressed |  | new indicator | 90% | 0% | 90% | 0% | 90% | 90% | Risk officer not yet appointed | Risk register
GG | Effective and Efficient administration | Risk management | # of risks identified |  | new indicator | Not applicable this quarter | Not applicable this quarter | 15 | 68 | Not applicable this quarter | 10 |  | Risk register
GG | Effective and Efficient administration | Sound Governance | % of NDPG reports submitted in time |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | NDPG reports submissions
GG | Effective and Efficient administration | Sound Governance | % of reported cases of corruption prosecuted |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% |  | Anti-corruption and theft policy approved
GG | Effective and Efficient administration | Sound Governance |  | # of quarterly internal audit reports submitted to audit committee | 4 | 1 | 0 | 2 | 1 | 3 | 4 | Audit Committee rejected 1st Quarter Report | Audit Risk Report Quarterly Audit reports
GG | Effective and Efficient administration | Sound Governance |  | # of Audit committee packs subimtted 7 days before meeting | Actual Awaited | 1 | 0 | 2 | 0 | 3 | 4 | Coordination of submissions needs to be improved | Acknowledgement of receipt & schedule of meetings
GG | Effective and Efficient administration | Sound Governance | % reduction in audit queries from AG |  | New indicator | Not applicable this quarter | Not applicable this quarter | 100% | 0% | Not applicable this quarter | Not applicable this quarter | Non compliance | Audit Report
GG | Effective and Efficient administration | Sound Governance |  | % of Internal Audit queries responded to within 10 days | 100% | 100% | 50% | 100% | 0% | 100% | 100% |  | Register of Internal Audit queries & corresponding reports
GG | Effective and Efficient administration | Sound Governance |  | # of Outcome 9 reports submitted on time | 4 | 4 | 4 | 1 | 1 | 2 | 3 |  | Quarterly MTAS reports, Acknowledgement of receipt
GG | Effective and Efficient administration | Sound Governance | Audit opinion |  | Qualified | Not applicable this quarter | Not applicable this quarter | Unqualified audit opinion | Disclaimer Audit Opinion | Not applicable this quarter | Not applicable this quarter | Non compliance | Audit Report
GG / MFVM | Increase financial viability | Budget management | % of capital spent on projects as prioritised in IDP for specific year |  | 100% | 100% | 6.99% | 100% | 15% | 100% | 100% |  | Expenditure report
GG / MFVM | Increase financial viability | Budget management | % of municipal budget spent |  | 92% | Reporting only - no target | 19.33 | Reporting only - no target | 45.8% | Reporting only - no target | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Budget management |  | % of departmental budget spent | 90% | 25% | 20.37% | 50% | 42.77% | 75% | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Budget management | % increase in cost coverage |  | 2.32 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 0.11 |  | Financial reports Financial viability calculations
GG / MFVM | Increase financial viability | Expenditure Management | % capital spent on upgrading municipal assets |  | 72% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 100% |  | Budget report
GG / MFVM | Increase financial viability | Financial reporting | % of AG queries responded to within 2 working days |  | 100% | Not applicable this quarter | Not applicable this quarter | 100% | 80% | Not applicable this quarter | Not applicable this quarter | Two journal books were missing and asset managment queries were responded to by the service provider which resulted in a late response. | Register of AG queries and response dates
GG / MFVM | Increase financial viability | Municipal Assets |  | # of departmental asset verifications done | 1 | 0 | 0 | 1 | 1 | 1 | 2 |  | Asset verification checklist
GG / MFVM | Increase financial viability | Revenue Management | % decrease in outstanding rates and service debtors |  | 2% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 3% |  | Financial reports
GG / MFVM | Increase financial viability | Revenue Management | % increase in R-value revenue collection |  | 4% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 5% |  | Report on revenue generated
GG / MFVM | Increase financial viability | Supply chain management | % compliance to supply chain management processes |  | new indicator | 100% | 100% | 100% | 80% | 100% | 100% | Most of the contracts have expired, SCM process are not centralised in the SCM unit and training have not been provided to SCM unit | SCM process checklist
GG / MFVM | Increase financial viability | Supply chain management | # of Tenders awarded that deviated from the adjudication committee recommendations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Monthly SCM report
GG / MFVM | Increase financial viability | Supply chain management | % of Bids awarded within 2 weeks after adjudication committee resolution |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Submission register Monthly reports
GG / MTOD | Effective and Efficient administration | Performance monitoring and reporting | # performance reports submitted within legislated timeframes |  | 8 | 2 | 2 | 4 | 4 | 6 | 8 |  | Performance Reports submission register (Otutcome 9 & SDBIP)
GG / MTOD | Effective and Efficient administration | Performance monitoring and reporting | Timeous submission of annual report |  | 2012-01-30 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 31 Jan '12 | n/a |  | Acknowledgement of Receipt, DLGH, AG & PT
GG / MTOD | Effective and Efficient administration | Sound Governance | # of Section 71 (MFMA) reports submitted within legislated timeframes |  | 12 | 3 | 3 | 6 | 6 | 9 | 12 |  | MFMA Report submission register
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | % Staff turnover |  | 7.1% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 6.5% |  | HR reports
LED | Create a stable economic environment by attracting suitable investors | Economic Growth and Investment | # of committed investors attracted through GTEDA |  | new indicator | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 3 |  | Investment reports (LADC, MDDA, Premiers Office & SEDA)
LED | Create Community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | # of jobs created through municipal LED initiatives |  | 503 | Reporting only - no target | 1827 | 200 | 1388 | Reporting only - no target | 600 |  | LED monthly job creation report Capital projects job creation reports
LED | Create Community beneficiation and empowerment opportunities | Poverty Reduction and empowerment | % reduction in unemployment |  | Not available | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 5% |  | Unemployment Results from Stats SA or other accepted source
LED | Integrated developmental planning | 2030 Vision Strategy | 2030 Vision Strategy Developed and approved within required timeframe |  | new indicator | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 2012-06-30 |  | Council Minutes
LED | Integrated developmental planning | Integrated development planning | IDP credibility rating |  | High | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | High |  | DLGH report
LED | Integrated developmental planning | Integrated development planning | Timeous submission of draft IDP to COGHSTA |  | 2012-03-31 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Disclaimer Audit Opinion | 31 March '12 | Not applicable this quarter |  | Acknowledgement of receipt
LED | Integrated developmental planning | Integrated development planning |  | Timeous adoption of IDP | 2012-05-30 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 2012-05-31 |  | Council Minutes
LED | Integrated developmental planning | Integrated development planning |  | Timeous adoption of SDBIP | 2012-06-20 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 2012-06-30 |  | SDBIP signed by Mayor
LED | Integrated developmental planning | Integrated Development Planning |  | # of IDP Technical Committee meetings | 4 | 2 | 1 | 4 | 2 | 5 | 6 | Key stakeholders were not available on the scheduled dates | Minutes & attendance registers of Steering Committee meetings
LED | Integrated developmental planning | Integrated Development Planning |  | # of IDP steering Committee meetings | 4 | 2 | 1 | 4 | 1 | 5 | 6 | Key stakeholders were not available on the scheduled dates | Minutes & attendance registers of Steering Committee meetings
LED | Integrated developmental planning | Integrated Development Planning |  | # of IDP Rep forum meetings | 3 | 2 | 1 | 4 | 1 | 5 | 6 | IDP rep Forum is convened after the technical and steering comm have met and prepared documents as such, non convening of the mentioned committee. | Minutes & Attendance registers of Rep forum meetings
LED | Integrated developmental planning | Integrated Spatial Development | # Capital projects implemented in SDF nodes |  | new indicator (IDP) | Reporting only - no target |  | Reporting only - no target | 36 | Reporting only - no target | Reporting only - no target |  | Revised SDF vs Capital Expenditure
LED | Integrated developmental planning | Integrated Spatial Development | % of capital spent on projects as prioritised in IDP for specific year |  | 100% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 100% |  | IDP list of capital projects & Budget report
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management |  | # of formal performance reviews | 2 | 1 | 0 | 1 | 0 | 2 | 2 | Delayed until the appointment of all Section 56/57 positions | Mid-year and Annual Assessment reports
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | % of critical posts with signed performance agreements |  | 100% | 100% | 0% | 100% | 33% | 100% | 100% | Only ESD & Town Planner has signed (MM, CFO, HR & Communications awaited) | Signed Performance Agreements
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | % Section 57 Managers with signed Performance Agreements/ Plans by 30 Jun |  | 100% | 100% | 14% | Not applicable this quarter | 42.85% | Not applicable this quarter | Not applicable this quarter | Onlyl ESD, PED & EED has signed | Performance Agreements for Sect 57 Managers
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management |  | % of MM Manager's with signed performance plans by 31 July | 100% | 100% | 0% | Not applicable this quarter | 0% | Not applicable this quarter | Not applicable this quarter | Was delayed along with appointment of MM | Signed Performance Plans Managers

## MM Projects
Quarterly targets per Project - Office of the Municipal Manager
KPA/ Theme | Strategic Objective | Programme | Project | Planned end date | Opex 2012/2013 | Capex 2012/2013 | Qtr Ending Sept '12 | Actual Sept '2012 | Qtr Ending - Dec '12 | Actual Dec '2012 | Qtr Ending - Mar '13 | Qtr Ending - Jun '13 | Reason for deviation | Means of verification
BSD | Optimise infrastructure investment and services | Infrastructure Planning | Infrastructure Development Plans | 30/06/2013 |  |  | Monitor the drafting of the Infrastructure Development plans (Water, Sewer, Roads, Parks & Cemetery master plans) | No funds available. Still busy accessing funds | Monitor the drafting of the Infrastructure Development plans (Water, Sewer, Roads, Parks & Cemetery master plans) | Only Electrical Master Plan in place | Monitor the drafting of the Infrastructure Development plans (Water, Sewer, Roads, Parks & Cemetery master plans) | Monitor the drafting of the Infrastructure Development plans (Water, Sewer, Roads, Parks & Cemetery master plans) | MDM as WSA will draft master plans for water. No funds to draft Roads Master Plan | Correspondence with Directors Progress Reports
BSD | Optimise infrastructure investment and services | Municipal assets | Furniture - MM | 30/06/2013 |  | 500000 | Procure furniture for the Office of the Municipal Manager | not yet procured | Not applicable this quarter | Not yet procured. | Not applicable this quarter | Not applicable this quarter | No funds available due to the increase in salaries. | Invoice & Proof of payment
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | Water Service Authority | 30/06/2013 |  |  | Follow-up with COGSTA on progress with GTM Service Authority Status recommendation and report progress | No progress. | Follow-up with COGSTA on progress with GTM Service Authority Status recommendation and report progress | New SLA had been signed with MDM in June 2012. | Follow-up with COGSTA on progress with GTM Service Authority Status recommendation and report progress | Follow-up with COGSTA on progress with GTM Service Authority Status recommendation and report progress |  | Correspondence
BSD | Promote environmentally sound practices and social development | Disaster management | Disaster response and recovery | 30/06/2013 |  |  | Develop a response and recovey plan for GTM based on the district plan | Response plan developed. | Submit GTM response and recovery plan to Council for approval | Response plan developed and sent to Council. | Train departments on the implemention of the Response and recovery plan | Train departments on the implemention of the Response and recovery plan |  | GTM Response & Recovery plan Council minutes Training attendance register
BSD | Promote environmentally sound practices and social development | Disaster management | Disaster Risk Reduction | 30/06/2013 |  |  | Update the Disaster & Emergency Plan and submit to Management for approval. Arrange Disaster risk awareness campaign to cover all wards | updated, will be sent to Management for approval. | Arrange Disaster risk awareness campaign to cover all wards | Updated and awareness campaign held. | Arrange Disaster risk awareness campaign to cover all wards | Arrange Disaster risk awareness campaign to cover all wards |  | Managenent Minutes Disaster & Emergency Plan approval -Awareness campaign report
BSD | Promote environmentally sound practices and social development | Disaster management | Institutional Capacity for Disaster management | 30/06/2013 |  |  | Build capacity of Disaster Management unit and ensure attendance of Advisory Forum &Technical Committees. | No progress with expanding capacity. Forums at district level only | Build capacity of Disaster Management unit and ensure attendance of Advisory Forum &Technical Committees. | No progress with expanding capacity. Forums at district level only | Build capacity of Disaster Management unit and ensure attendance of Advisory Forum &Technical Committees. | Build capacity of Disaster Management unit and ensure attendance of Advisory Forum &Technical Committees. |  | Council Minutes for 2011/12 Disaster management report
GG | Effective and Efficient administration | Fraud & Anti-corruption | Anti-corruption strategy implemented | 30/06/2013 |  |  | Not applicable this quarter | Not applicable this quarter | Submit draft strategy to Council for adoption | Not yet implemented | Develop terms of reference for establishment of Council Anti-corruption committee | Anti-Corruption Strategy Approved Anti-Corruption committee established | The Mayoral hotline is being developed. | Anti-corruption strategy Minutes of Anti-corruption committee meetings
GG | Effective and Efficient administration | Fraud & Anti-corruption | Corruption and Maladministration | 30/06/2013 |  |  | Ensure that an Anti-corruption committee is established | No committee was established | Monitor administration to curb corruption and maladministration. | No committee was established | Monitor administration to curb corruption and maladministration. | Monitor administration to curb corruption and maladministration. | Currently in the process of forming an anti corruption committee. | Correspondence Response to Internal Audit Reports Council Resolution
GG | Effective and Efficient administration | Information management | Integrated Management Information System (IMIS/GIS) | 30/06/2013 |  |  | Consult all Departments to determine the requirements for an Integrated Management Information System (ISMIS) | Still in progress | Draft a Terms of Reference for the appointment of a service provider | Still in progress | Appoint service Provider for the development of a IMIS | Monitor the development of a IMIS |  | Correspondence with Departments TOR SLA for IMIS
GG/MTOD | Effective and Efficient administration | Performance Monitoring and Reporting | Performance Auditing | 30/06/2013 |  |  | Conduct audit on 2011/12 Annual Performance report within 2 weeks of receipt and submit report to the MM and the Audit Committee | Annual Performance report approved by Council on 28 August. | Conduct audit on the Annual Report and submit report to the MM and Audit Committee. Audit 1st Quarter SDBIP report and submit report to MM within 7 days of receipt. | Performance Reports not audited | Audit the 2nd Qtr SDBIP report and submit report to the MM and Audit Committee within 7 days of receipt. | Audit the 3rd Qtr SDBIP report and submit report to the MM and Audit Committee within 7 days of receipt. | Reporting timelines doesn't allow sufficient time for internal audit to conduct audit prior to submission to Council | SDBIP Audit Reports -Annual Performance Report audit report -Annual Report Audit report
GG/MTOD | Effective and Efficient administration | Performance Monitoring and Reporting | Performance Management Software | 30/06/2013 |  |  | Finalise TOR and submit specifications to SCM for advertisement of electronic PM System. | TOR submitted to Acting Muncipal Manager, awaiting approval | Appointment of service provider. Develop implementation programme. | No progress | Ensure roll-out of electronic PM and capacity building of PM officials in HR and MM office to manage system | Ensure roll-out of electronic PM and capacity building of PM officials in HR and MM office to manage system | TOR submitted to Acting Muncipal Manager, awaiting approval | Proof of Purchase
GG/MTOD | Effective and Efficient administration | Performance Monitoring and Reporting | Performance Reporting | 30/06/2013 |  |  | Finalise Annual Performance Report by 30 August. Submit 4th Qtr MTAS report to DLGH within 5 weeks of close of quarter | Annual Performance Report approved by Council on 28 August. MTAS and Outcome 9 Reports submitted within timeframes | Submit 1st Quarter MTAS & SDBIP reports to DLGH within 5 weeks of close of quarter | 1st Quarter MTAS & Outcome 9 along with SDBIP was completed and submitted as required | Submit 2nd Quarter MTAS & SDBIP reports to DLGH within 5 weeks of close of quarter | Submit 3rd Quarter MTAS & SDBIP reports to DLGH within 5 weeks of close of quarter |  | Proof of submission of MTAS (4) and SDBIP (4)
GG | Effective and Efficient administration | Risk management | Risk assessment and monitoring | 30/06/2013 |  |  | Update risk assessment and prevention mechanisms on a quarterly basis. Monitor risks in all Departments and report to Risk Management Committeee | No risk officer was appointed. | Update risk assessment and prevention mechanisms on a quarterly basis. Monitor risks in all Departments and report to Risk Management Committeee | No progress | Update risk assessment and prevention mechanisms on a quarterly basis. Monitor risks in all Departments and report to Risk Management Committeee | Update risk assessment and prevention mechanisms on a quarterly basis. Finalise Combined assurance plan and submit to Council on an annual basis. Monitor risks in all Departments and report to Risk Management Committeee | Risk officer not yet appointed | Quarterly Risk Assessment Report Combined Assurance Plan Reports
GG | Effective and Efficient administration | Risk management | Risk management awareness | 30/06/2013 |  |  | Sensitise management timeously of the need to perform risk assessments | No risk officer was appointed. | Conduct training sessions with senior and middle management to familiarise them with risk management principles and practices | No progress | Conduct training sessions with senior and middle management to familiarise them with risk management principles and practices | Conduct training sessions with senior and middle management to familiarise them with risk management principles and practices | Risk officer not yet appointed | Training session attendance registers
GG | Effective and Efficient administration | Risk management | Risk management implementation plan | 30/06/2013 |  |  | Draft Risk Management implementation plan in line with the national framework and submit to council for approval by 30 July. | No risk officer was appointed. | Ensure that Risk Management processes and reporting lines are established | No progress | Establish Risk Management Committee | Coordinate Risk Management committee meetings | Risk officer not yet appointed | Council minutes Communiques Risk Management Committee Establishment notice & Minutes
GG | Effective and Efficient administration | Risk management | Risk regulatory framework | 30/06/2013 |  |  | Customise national Risk Management policy and strategy to GTM circumstances | No risk officer was appointed. | Customise national Risk Management policy and strategy to GTM circumstances | No progress | Submit customised Risk Management Policy to Council for approval | Submit customised Risk Management Strategy to Council for approval | Risk officer not yet appointed | Council minutes for Risk Policy & Risk Management Strategy
GG/MFVM | Effective and Efficient administration | Sound Governance | Audit Committee Support | 30/06/2013 |  |  | Provide administrative support to the Audit Committee by ensuring that the Agenda is Prepared, required documentation is submitted in time and minutes are prepared. Submit quarterly Internal Audit reports | Administrativ support is done effectively. | Provide administrative support to the Audit Committee by ensuring that the Agenda is Prepared, required documentation is submitted in time and minutes are prepared. Submit quarterly Internal Audit reports | Administrative support is done effectively. | Provide administrative support to the Audit Committee by ensuring that the Agenda is Prepared, required documentation is submitted in time and minutes are prepared. Submit quarterly Internal Audit reports | Provide administrative support to the Audit Committee by ensuring that the Agenda is Prepared, required documentation is submitted in time and minutes are prepared. Submit quarterly Internal Audit reports |  | AC Agendas Minutes of meetings Quarterly reports
GG | Effective and Efficient administration | Sound Governance | Council Resolution Implementation | 30/06/2013 |  |  | Monitor the implementation of Council resolutions. Keep register of progress | Council Resolution registers are sent to Management Meetings for updating. | Monitor the implementation of Council resolutions. Keep register of progress | Council Resolution registers are sent to Management Meetings for updating and circulated via email to all Directors and Secretaries. | Monitor the implementation of Council resolutions. Keep register of progress | Monitor the implementation of Council resolutions. Keep register of progress |  | Resolution Register Implementation
LED | Integrated Developmental Planning | Integrated development planning | IDP stakeholder register | 30/06/2013 |  |  | Advertise for local stakeholders to register with GTM on the IDP stakeholder register. Updated register ready by 30 August '11 | The advert was done. We have compiled a list of stakeholders who have applied for registration. | Monitor the attendance of IDP Representative Forum meetings by registered stakeholders and devise initiatives to encourage attendance | The advert was done. Stakeholders registered. We now have a database of stakeholders. | as per the approved programme | as per the approved programme |  | Advertisement Stakeholder Register Attendance Log
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Cascade Performance Management System | 30/06/2013 |  |  | Identify "best practice" municpalities to visit and study process of cascading individual PMS. Draft implementation guidelines. Appoint capable personnel in HR to manage process and appoint service provider | Draft TOR awaiting approval by MM. Implementation guidelines not revised yet. | Commence with cascading process by putting procedures and templates in place and by arranging workshops with union representatives and employees on targeted levels to train them on PMS. | No progress | Commence with cascading process by putting procedures and templates in place and by arranging workshops with union representatives and employees on targeted levels to train them on PMS. | Development of performance plans for targeted levels of employees | HR to be capacitated to take over the cascading of Employee Performance Management (HR function) | Correspondence Workshop attendance registers Procedure Mannual
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Employee Performance Evaluation | 30/06/2013 |  |  | Conduct audit on 2011/12 Annual Individual Performance Report and submit report to MM & audit committee within 2 weeks | Not done | Not applicable this quarter | Not done | Conduct audit on 2012/13 Mid-year individual performance report and submit report to MM & audit committee within 2 weeks | Not applicable this quarter | Employee Performance Assessment was postponed to allow for the appointment of Section 56/57 Managers | Audit report on Annual Individual Performance Report -Audit report on Mid-year individual performance report
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Instilling Values and Culture of Discipline (10 Point plan) | 30/06/2013 |  |  | Revise the existing 10 point plan to ensure that measurable targets are set. Monitor implementation | Still in the process of revising | Revise the existing 10 point plan to ensure that measurable targets are set. Monitor implementation | Still in the process of revising | Revise the existing 10 point plan to ensure that measurable targets are set. Monitor implementation | Revise the existing 10 point plan to ensure that measurable targets are set. Monitor implementation |  | Revised 10 Point plan Progress reports
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance Management implementation guidelines (institutional) | 30/06/2013 |  |  | Draft implementation guidelines for institutional performance management in line with reporting requirements | Drafting in progress | Submit Implementation Guidelines to Council for approval. | Drafting in progress | Arrange a workshop with Management to familiarise all with implementation guidelines | Implement guidelines. | Limited Human Resources in PM office | PMS Implementation guidelines Workshop attendance register
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance monitoring & evaluation | 30/06/2013 |  |  | Ensure that annual assessment of all relevant employees in the Office of the MM is conducted. Ensure that the Annual Performance Evaluations for 2011/12 is concluded by 30 July. | Annual Performance Assessment for 2011/12 was not conducted | Conduct an informal evaluation of 1st Quarter Performance of relevant employees in the Office of the MM and draft a report by 21 October | Not done | Ensure that a mid-year assessment of employee performance is conducted and a report drafted by 30 January '13 | Ensure that an informal evaluation of 3rd Quarter Performance of relevant employees in the Office of the MM is conducted and a report drafted by 20 April | Performance Agreements not yet signed due to the delays in the filling of MM position | 1st & 3rd Qtr Informal Departmental Individual Performance Report 2011/12 Individual Performance report 2012/13 Mid-year individual performance report
SR/LED | Integrated Developmental Planning | 2030 Vision Strategy | 2030 Growth and development strategy | 30/06/2013 | 500000 |  | Draft Specifications and project requirements | Specifications and project requirements not yet completed | Advertise and appoint a service provider | List of IDP Representative Forum finalized and available | Monitor data collection by service provider | 1st Draft Strategy ready for discussion |  | 2030 Growth and development strategy framework and guidelines
SR/LED | Integrated Developmental Planning | Integrated Development Planning | IDP implementation monitoring | 30/06/2013 |  |  | Monitor the implementation of the IDP by ensuring that Thrust meetings are held and that reports are discussed at Management. Attend meetings on request | IDP Technical, Steering Committees and Rep Forums (instead of Thrust) are regularly held | Monitor the implementation of the IDP by ensuring that Thrust meetings are held and that reports are discussed at Management. Attend meetings on request | IDP Technical, Steering Committees and Rep Forums (instead of Thrust) are regularly held | Monitor the implementation of the IDP by ensuring that Thrust meetings are held and that reports are discussed at Management. Attend meetings on request | Monitor the implementation of the IDP by ensuring that Thrust meetings are held and that reports are discussed at Management. Attend meetings on request |  | Thrust meeting reports
SR/LED | Integrated Developmental Planning | Integrated Development Planning | IDP review | 30/06/2013 |  |  | Draft Process plan and submit to Council by 30 July. Circulate community needs to departments and facilitate analysis phase review through the Representative Forum. | Busy with the review of the IDP Analysis Phase for the 2013/2014 cycle | Conduct Strategic planning session and prioritise projects for next financial year. Submit project requests to Sector Departments. | Done with IDP Strategic Planning Session. To start with the project phase during January 2013 | Draft IDP to Council by 30 March. Submit draft IDP to COGHSTA within legislated timeframes | Advertise IDP for public input, consolidate inputs and present to Council by 30 May. Submit final IDP to COGHSTA within legislated timeframes |  | Council Minutes on Process Plan Progress report per phase Correspondence with Departments Council Minutes for IDP adoption
SR/LED | Integrated Developmental Planning | Integrated Development Planning | IDP, Budget & PMS alignment | 30/06/2013 |  |  | Manage the drafting of the IDP and Budget. Ensure that the SDBIP is aligned to the IDP & Budget | Efforts in place to ensure compliance in terms of alignment of the IDP and SDBIP | Manage the drafting of the IDP and Budget. Ensure that the SDBIP is aligned to the IDP & Budget | Efforts in place to ensure compliance in terms of alignment of the IDP and SDBIP | Manage the drafting of the IDP and Budget. Ensure that the SDBIP is aligned to the IDP & Budget | Manage the drafting of the IDP and Budget. Ensure that the SDBIP is aligned to the IDP & Budget |  | Correspondence Audit report

## CFO KPIs
Key Performance Indicators (KPIs) - Office of the Chief Financial Officer
KPA/ Theme | Strategic Objective | Programme | Departmental KPI | Baseline (end June 2012) | Target Sept '12 | Actual end Sept '12 | Target Dec '12 | Actual end Dec '12 | Target Mar '13 | Target Jun '13 | Reason for deviation | Means of verification
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | % households earning less than R1100 with access to basic electricity (registered as indigents) | 33.396 | Reporting only - no target | Information not available | Reporting only - no target | Information not available | Reporting only - no target | Reporting only - no target | Statistics still to be updated with Census 2011 information | Indigent register
BSD | Improve access to sustainable and affordable services | Free Basic Services | % of households earning less that R1100 (indigent) served with free basic electricity | 25.411 | Reporting only - no target | Information not available | Reporting only - no target | 66% | Reporting only - no target | Reporting only - no target |  | Reports & correspondence
BSD | Improve access to sustainable and affordable services | Free Basic Services | Nr of households with access to free basic electricity | 6714 | not applicable this quarter | Not applicable this quarter | 10000 | 7350 | not applicable this quarter | 10000 |  | Revenue reports
BSD | Improve access to sustainable and affordable services | Waste Management | % households earning less than R1100 with access to basic waste removal (registerd as indigents) | 11% | Reporting only - no target | Information not available | Reporting only - no target | 12% | Reporting only - no target | Reporting only - no target |  | Indigent register
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | Total R-value of contracts awarded to women, youth & disabled | 56456018 | Reporting only - no target | 198000 | Reporting only - no target | 95774089 | Reporting only - no target | Reporting only - no target |  | Monthly SC reports
GG | Effective and Efficient administration | Council Support | % of Departmental Council resolutions implemented | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Departmental Resolution register
GG | Effective and Efficient administration | Management and Administration | # of departmental meetings | 4 | 1 | 4 | 2 | 2 | 3 | 4 |  | Minutes and Attendance registers of Departmental meetings
GG | Effective and Efficient administration | Performance monitoring and reporting | # of Finance Departmental monthly reports submitted on time | 12 | 3 | 3 | 6 | 6 | 9 | 12 |  | Monthly, quarterly, half yearly and annual reports
GG | Effective and Efficient administration | Sound Governance | % of Internal Audit queries responded to within 10 days | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Register of Internal Audit queries & corresponding reports
GG / MFVM | Develop and build skilled and knowledgeable workforce | Capacity building and Training | % of budget allocated for training and development (SDP) | 1.39% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 1.32% |  | Approved Departmental budget 31 May 2010
GG / MFVM | Increase financial viability | Budget management | R-value Salaries budget (including benefits) | 169188952 | 45807063 | 45124456 | 93926481 | 103855952 | 143061682 | 192938336 |  | System printout
GG / MFVM | Increase financial viability | Budget management | R-value Total operating budget | 800620250 | 183866879 | 157087315.71 | 385171865 | 372326621 | 572012855 | 811700287 |  | Approved Budget
GG / MFVM | Increase financial viability | Budget management | % Operating budget for Councillor allowances (Councillor allowances budgeted / total operating budget) | 2.25% | Reporting only - no target | 0.517% | Reporting only - no target | 1.08% | Reporting only - no target | 2.25% |  | Approved Departmental budget 31 May 2010
GG / MFVM | Increase financial viability | Budget management | % General expenses budget / Operating expenses budget | 10% | Reporting only - no target | 2.08% | Reporting only - no target | 4.43% | Reporting only - no target | 10% |  | Budget Reports
GG / MFVM | Increase financial viability | Budget management | Final budget tabled before Council by within legislated timeframes | 2012-05-29 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 2012-05-31 |  | Council resolution
GG / MFVM | Increase financial viability | Budget management | Annual Adjustment budget approved by Council within legislated timeframes | 2012-02-28 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | end February '13 | Not applicable this quarter |  | Council resolution
GG / MFVM | Increase financial viability | Budget management | Cost coverage ratio | 3.37 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 0.8 |  | Financial reports Financial viability calculations
GG / MFVM | Increase financial viability | Budget management | Debt coverage ratio | 12.88 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 30 |  | Financial reports Financial viability calculations
GG / MFVM | Increase financial viability | Expenditure Management | % of Loan amount utilised for capital projects | 100% | Reporting only - no target | 0% | 100% | 100% | Reporting only - no target | 100% |  | Correspondence, Capital project payment records
GG / MFVM | Increase financial viability | Expenditure Management | % decrease in municipal budget variance | new indicator | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 98% |  | Expenditure report
GG / MFVM | Increase financial viability | Expenditure Management | Monthly operational expenditure as a percentage of planned expenditure | 110% | Not applicable this quarter | Not applicable this quarter | 90% | 46% | Not applicable this quarter | 90% | Deviation is due to the provision for bad debt not yet affected as well as underspending on: Grans and Subsidies Repairs & Maintenance and Interest paid on ext. Borrowing which is not paid in equal installments | MTAS reports
GG / MFVM | Increase financial viability | Expenditure Management | Monthly capital expenditure as a % of planned capital expenditure | 94% | Reporting only - no target | 6.99% | Reporting only - no target | 17.2% | Reporting only - no target | Reporting only - no target |  | MTAS reports
GG / MFVM | Increase financial viability | Expenditure Management | % of operational budget spent on repairs and maintenance | 16% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 17% |  | MTAS reports
GG / MFVM | Increase financial viability | Financial reporting | Timeous submission of annual financial statements | 2011-08-31 | 2012-08-31 | 2012-08-31 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter |  | Acknowledgement of receipt by AG & PT
GG / MFVM | Increase financial viability | Financial reporting | % variance from annual Legislated Budget timetables | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | Timetable & progress reports
GG / MFVM | Increase financial viability | Financial reporting | % of AG queries responded to within 2 working days | 100% | Not applicable this quarter | Not applicable this quarter | 100% | 70% | Not applicable this quarter | Not applicable this quarter | poor submission of information due to to missing of information | Records of Audit queries
GG / MFVM | Increase financial viability | Municipal Assets | # of departmental asset verifications done | 1 | 0 | 0 | 1 | 0 | 1 | 2 | Asset register not finalised | Asset verification checklist
GG / MFVM | Increase financial viability | Municipal Assets | % GRAP compliance (asset register) | 100% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 100% |  | Audit report
GG / MFVM | Increase financial viability | Revenue Management | Increase in number of households billed |  | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 800 |  | Billing reports
GG / MFVM | Increase financial viability | Revenue Management | R-value outstanding service debtors | 222203000 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 230000000 |  | Financial Statements
GG / MFVM | Increase financial viability | Revenue Management | Average % Payment rate for municipal area | 92% | 90% | 84% | 90% | 84% | 90% | 90% | Tzaneen, Haenertsburg and Letsitele = 104% Nko/Len = 33% | Budget report
GG / MFVM | Increase financial viability | Revenue Management | R-value total debts written off annually | 20286673 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 9500000 |  | Council Resolution
GG / MFVM | Increase financial viability | Revenue Management | R debtors outstanding as a % of own revenue | 41 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 55% |  | MTAS reports
GG / MFVM | Increase financial viability | Revenue Management | % of debt over 90 days | 71 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 45% |  | MTAS reports
GG / MFVM | Increase financial viability | Revenue Management | R-value annual revenue actually received for services | 430420649 | Reporting only - no target | 77710940.44 | Reporting only - no target | 236191191 | Reporting only - no target | Reporting only |  | Revenue reports
GG / MFVM | Increase financial viability | Revenue Management | % Payment rate - Tzaneen (urban) | 99% | 95% | 96.79% | 95% | 100% | 95% | 95% |  | Budget reports
GG / MFVM | Increase financial viability | Revenue Management | % Payment rate -Tzaneen (rural) | 92% | 90% | 82.11% | 90% | 95% | 90% | 90% |  | Budget reports
GG / MFVM | Increase financial viability | Revenue Management | % Payment rate -Nkowankowa | 29% | 35% | 23.97% | 35% | 27% | 35% | 35% |  | Budget reports
GG / MFVM | Increase financial viability | Revenue Management | % Payment rate -Lenyenye | 39% | 40% | 41.1% | 40% | 40% | 40% | 40% |  | Budget reports
GG / MFVM | Increase financial viability | Revenue Management | % Payment rate -Letsitele | 111% | 96% | 103.1% | 96% | 112% | 96% | 96% |  | Budget reports
GG / MFVM | Increase financial viability | Revenue Management | % Payment rate -Haenertsburg | 92% | 90% | 88.39% | 90% | 114% | 90% | 90% |  | Budget reports
GG / MFVM | Increase financial viability | Revenue Management | Outstanding service debtors to revenue ratio | 68% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 50% |  | Financial reports Financial viability calculations
GG / MFVM | Increase financial viability | Revenue Management | % reduction in rates and services billed, not recovered | 0% | 0.25% | 0% | 0.5% | 0% | 0.75% | 1% | Collection rate in Tzaneen more than 100% | Quarterly Revenue reports
GG / MFVM | Increase financial viability | Revenue Management | % Revenue from grants | 30% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 38% |  | Budget reports
GG / MFVM | Increase financial viability | Revenue Management | R-value MIG funding / R-Value Capital budget as % | 19% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 50% |  | Budget reports
GG / MFVM | Increase financial viability | Revenue Management | % equitable share received | 95% | 41.6% | 42% | 60% | 70% | 100% | 100% |  | Bank Statement
GG / MFVM | Increase financial viability | Supply chain management | Total R-value of contracts awarded during the financial year | 138055183.51 | Reporting only - no target | 839820 | Reporting only - no target | 95972089 | Reporting only - no target | Reporting only - no target |  | SCM Report
GG / MFVM | Increase financial viability | Supply chain management | Average time taken from tender advertisement to submission of recommendation to the MM (# of weeks) | 9 | 8 | 8 | 8 | 8 | 8 | 8 | CFO/BAC recommends for re-evaluation | Contract register
GG/ MFVM | Increase Financial Viability | Revenue Management | Number of indigents registered | 10440 | 10440 | 644 | 10440 | 3023 | 10440 | 14000 | Rural still to be done | Indigent register
LED | Integrated developmental planning | Integrated development planning | Timeous adoption of budget | 28 May '12 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 31 May '12 |  | Council Minutes
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | % of CFO Manager's with signed performance plans by 31 July | 100% | 100% | 0% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter |  | Signed Performance Plans
Note on D44: frieda: Outstanding service debtors/ revenue from services =

## CFO Projects
Quarterly targets per Project - Office of the Chief Financial Officer
KPA/ Theme | Strategic Objective | Programme | Project | Planned end date | Opex 2012/2013 | Capex 2012/2013 | Qtr Ending Sept '12 | Actual end Sept '12 | Qtr Ending - Dec '12 | Actual End Dec '12 | Qtr Ending - Mar '13 | Qtr Ending - Jun '13 | Reason for deviation | Means of verification
BSD | Integrated Developmental Planning | Integrated Development planning | 5 Year Capital Investment framework | 30/06/2013 |  |  | Draft the 5-Year Capital Invest framework | No progress | Draft the 5-Year Capital Invest framework | In the process of drafting | Ensure the 5-Year Capital Investment framework is included in the draft IDP | Not applicable this quarter |  | 5 Yr Capital Investment framework
BSD | Optimise infrastructure investment and services | Municipal assets | Furniture -CFO | 30/06/2013 |  | 500000 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Procure furniture for the Office of the CFO |  | Invoice & Proof of payment
GG/ MFVM | Increase Financial Viability | Financial reporting | Operation Clean Audit | 30/06/2013 | 200000 |  | Manage annual audit and timeous response on audit queries (AFS 2011/12) | 2 Audit steering committee meetings held | Finalisation of Annual Audit | Annual Audit was finalised | Drafting and approval of Clean Audit Action Plan | Implementation of the Clean Audit Action plan |  | Council Minutes approving Audit Action Plan Audit Report & Management report
GG/ MFVM | Increase Financial Viability | Financial viability | 5 Year Financial Plan | 30/06/2013 |  |  | Not applicable this quarter | Not applicable this quarter | Assess financial performance during 2010/11 and draft 5-Year Financial Plan accordingly | Draft five year financial plan to be reviewed and approved | Submit 5 Year Financial plan to the MM for inclusion in the draft IDP. | Not applicable this quarter |  | 5 Year Financial Plan Correspondence
GG/ MFVM | Increase Financial Viability | Financial Viability | Cost recovery | 30/06/2013 |  |  | Monitor Stand data verification, credit control, debt collection and report progress. Ensure that public is informed of all processes | Contractor busy with stand data verification, credit control and debt collection | Monitor Stand data verification, credit control, debt collection and report progress. Ensure that public is informed of all processes | Contractor busy with stand data verification, credit control and debt collection | Monitor Stand data verification, credit control, debt collection and report progress. Ensure that public is informed of all processes | Monitor Stand data verification, credit control, debt collection and report progress. Ensure that public is informed of all processes |  | Cost recovery progress reports
GG/ MFVM | Increase Financial Viability | Financial Viability | Financial Resource Mobilisation | 30/06/2013 |  |  | Monitor budget to actual expenditure, cashflow and the aquisition of loans and short term investments. Report monthly | Reports submitted on time | Monitor budget to actual expenditure, cashflow and the aquisition of loans and short term investments. Report monthly | Reports submitted on time | Monitor budget to actual expenditure, cashflow and the aquisition of loans and short term investments. Report monthly | Monitor budget to actual expenditure, cashflow and the aquisition of loans and short term investments. Report monthly |  | Budget report
GG/ MFVM | Increase Financial Viability | Financial Viability | GRAP Training and Financial System improvement | 30/06/2013 | 200000 |  | Comprehensive system analysis and official training | GRAP & MFMP training conducted | Comprehensive system analysis and official training | GRAP & MFMP training conducted | Comprehensive system analysis and official training | Comprehensive system analysis and official training |  | Attendance registers of training sessions
GG/ MFVM | Increase Financial Viability | Municipal Assets | Asset management | 30/06/2013 |  |  | Manage Departmental Assets ensure that Asset register are kept up to date | Departmental assets were checked and no movements of assets were recorded | Manage Departmental Assets ensure that Asset register are kept up to date and conduct mid-year asset verification | Assets verification will be done in the 4th quarter and we are in the process of finalising asset register | Manage Departmental Assets ensure that Asset register are kept up to date | Manage Departmental Assets ensure that Asset register are kept up to date. Ensure that annual asset verification are completed within the required timeframe |  | *Institutional Asset Verification Report *Bi-Annual Departmental Asset verification reports
GG/ MFVM | Increase Financial Viability | Revenue Management | Credit control - Data cleansing (DBSATA) | 30/06/2013 | 2400000 |  | Manage and co-ordinate implementation of credit and debt control systems and procedures | Ongoing process | Manage and co-ordinate implementation of credit and debt control systems and procedures | Ongoing process | Manage and co-ordinate implementation of credit and debt control systems and procedures | Review credit and debt collection policy and submit to Council for approval |  | Reviewed Credit and debt control policy
GG/ MFVM | Increase Financial Viability | Revenue Management | Indigent register policy | 30/06/2013 | 200000 |  | Monitor the registration and evaluation of indigents applications. Review of indigent policy and workshop with stakeholders. Finalisation of indigent policy and submit to Council for approval | Registration of indigents in progress. Policy approved | Monitor the registration and evaluation of indigents applications. | Registration of indigents in progress. Policy approved | Monitor the registration and evaluation of indigents applications. | Monitor the registration and evaluation of indigents applications. Consolidate and submit indigent write offs report for approval by Council. |  | Reviewed indigent policy Updated indigent register Council resolutions
GG/ MFVM | Increase Financial Viability | Revenue Management | Investment management | 30/06/2013 |  |  | Keep monthly investment register and ensure that all cash available are invested in efficiently | Monthly investment register kept with 100% of cash avalable invested daily at ABSA. Short term investments are made to split the risk Council is exsposed to. | Keep monthly investment register and ensure that all cash available are invested in efficiently | Keep monthly investment register and ensure that all cash available are invested in efficiently | Keep monthly investment register and ensure that all cash available are invested in efficiently | Keep monthly investment register and ensure that all cash available are invested in efficiently |  | Investment register
GG/ MFVM | Increase Financial Viability | Revenue Management | Revenue enhancement | 30/06/2013 |  | 1000000 | Debt book cleaning, Credit control enhancement and data cleansing. Installation of prepaid meters at indigent households | Debt book cleaning and credit control on ongoing basis. Installation of prepaid meters scheduled for October '12 | Debt book cleaning, Credit control enhancement and data cleansing. Installation of prepaid meters at indigent households | Debt book cleaning and credit control on ongoing basis. Installation of prepaid meters commenced | Credit control enhancement and data cleansing. Installation of prepaid meters at indigent households | Credit control enhancement and data cleansing. Installation of prepaid meters at indigent households |  | Debt assessment report
GG/ MFVM | Increase Financial Viability | Revenue Management | Revenue enhancement Strategy | 30/06/2013 |  |  | Monitor implementation of the revenue enhancement strategy | Progress resport submitted to the Finance Cluster | Monitor implementation of the revenue enhancement strategy | Monthly reports received from UMS | Revise revenue enhancement strategy and submit to Council | Monitor implementation of the revenue enhancement strategy |  | Council Minutes Revised Revenue Enhancement strategy
GG/ MFVM | Increase Financial Viability | Revenue Management | Valuation Roll | 30/06/2013 | 4500000 |  | Balancing of valuation roll to system | Valuars appointed to compile a new valuation roll | Balancing of valuation roll to system | Draft valuation roll submitted by service provider | Finalise Draft Valuation Roll | Advertise valuation roll, finalise objection process and submit to Council for approval |  | Supplementary valuation roll TOR for Valuation roll review
GG/ MFVM | Increase Financial Viability | Supply chain management | Supply chain functionality improvement (MTAS) | 30/06/2013 |  |  | Draft a list of criteria to measure SCM functionality. Report quarterly on progress made on improving functionality. Review SCM Policy and submit to Council | Functionality list has been developed. | Draft a list of criteria to measure SCM functionality. Report quarterly on progress made on improving functionality | Policy ready for Council approval | Draft a list of criteria to measure SCM functionality. Report quarterly on progress made on improving functionality | Draft a list of criteria to measure SCM functionality. Report quarterly on progress made on improving functionality |  | Supply Chain Functionality Checklist SCM Policy Resolution
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance monitoring & evaluation | 30/06/2013 |  |  | Participate in the Annual Performance Assessment for 2011/12. Ensure that scoresheets are completed in time & POEs are complete | Assessments postponed | Conduct an informal assessment of 1st Quarter Performance of relevant employees in the Department and send report to the MM by 21 October '12 | Assessments postponed | Participate in the mid-year employee performance evaluations for 2012/13. Ensure that scoresheets are completed in time & POEs are complete | Conduct an informal assessment of the 3rd Quarter Performance of relevant employees in the Department and submit report to the MM by 20 April '13 | Awaited appointment MM. Will conducted in 3rd Qtr | 1st & 3rd Qtr Informal Departmental Individual Performance Reports Correspondence

## CORP KPIs
Key Performance Indicators (KPIs) - Corporate Services Department
KPA/ Theme | Strategic Objective | Programme | Departmental KPI | Baseline (end June 2012) | Target Sept '12 | Actual Sept '12 | Target Dec '12 | Actual End Dec '12 | Target Mar '13 | Target Jun '13 | Reason for deviation | Means of verification
BSD | Develop and build skilled and knowledgeable workforce | Capacity building and Training | R-value spent on training | 1084725 | 250000 | 138466 | 500000 | 272451 | 750000 | 100000 | R400 000 transfered to Legal Fees vote | Budget reports
BSD | Develop and build skilled and knowledgeable workforce | Capacity building and Training | Work place skills plan submitted to LGSETA within required timeframe | 2012-06-30 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 2012-06-30 |  | Aknowledgement of receipt
BSD | Develop and build skilled and knowledgeable workforce | Capacity building and Training | # of Senior managers successfully completed CPMD, MFMP/ ELMDP Training | 21 Senior Managers & 6 Cllrs | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 12 |  | CPMD Training schedule
BSD | Develop and build skilled and knowledgeable workforce | Labour Relations | Level of functionality of Local Labour Forum (LLF) | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | MTAS reports
BSD | Develop and build skilled and knowledgeable workforce | Labour Relations | # Industrial actions | 2 | 0 | 0 | 0 | 1 | 0 | 0 | Strike on Benchmarking | Referral letter of Industrial Action
BSD | Develop and build skilled and knowledgeable workforce | Labour Relations | # of Trained presiding officers | 5 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 35 |  | Training attendance register
BSD | Develop and build skilled and knowledgeable workforce | Labour Relations | # of Trained prosecutors(initiators) | 5 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 35 |  | Training attendance register
BSD | Develop and build skilled and knowledgeable workforce | Labour Relations | # of grievances successfully dealth with | 0 | Reporting only - no target | 0 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target |  | Grievance forms
BSD | Develop and build skilled and knowledgeable workforce | Labour Relations | # of disciplinary cases successfully dealt with | 0 | Reporting only - no target | 1 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target |  | Payday printout
BSD | Develop and build skilled and knowledgeable workforce | Labour Relations | #of labour disputes resolved | 1 | Reporting only - no target | 0 | Reporting only - no target | 1 | Reporting only - no target | Reporting only - no target | Settlement in CCMA | Settlement agreements
GG | Attract and retain the best human capital to become employer of choice | Employee Assistance | # of cases reported | 397 | Reporting only - no target | 4 | Reporting only - no target | 3 | Reporting only - no target | Reporting only - no target |  | Monthly reports
GG | Attract and retain the best human capital to become employer of choice | Employee Assistance | # of EAP cases successfully attended to annually | 395 | Reporting only - no target | 6 | Reporting only - no target | 3 | Reporting only - no target | Reporting only - no target |  | Monthly reports
GG | Attract and retain the best human capital to become employer of choice | Organisational Design | Total Number of staff employed in the municipality | 627 | Reporting only - no target | 653 | Reporting only - no target | 651 | Reporting only - no target | Reporting only - no target | Staff turnover | Staff establishment
GG | Attract and retain the best human capital to become employer of choice | Organisational Design | Number of budgeted posts vacant for more than three months during the financial year | 45 | Reporting only - no target | 0 | Reporting only - no target | 4 | Reporting only - no target | Reporting only - no target |  | HR Monthly reports
GG | Attract and retain the best human capital to become employer of choice | Organisational Design | Total Number of Section 57 staff employed | 5 | 8 | 4 | 8 | 6 | 8 | 8 | Director Corp Vacant & Director Mayor not yet budgted for | Staff establishment
GG | Attract and retain the best human capital to become employer of choice | Organisational Design | Number of Section 57 posts vacant for more than three months | 2 | 1 | 4 | 1 | 2 | 1 | 1 | No appointment made for Director (Corporate Services) No budget for Director (Office of the Mayor) | Staff establishment
GG | Develop effective and sustainable stakeholder relations | Communication | # of media briefings arranged | new indicator | 2 | 0 | 3 | 1 | 4 | 6 | Next one will be held in March 2013 | Register of publications
GG | Develop effective and sustainable stakeholder relations | Communication | # of external newsletters produced | 1 | 1 | 1 | 2 | 0 | 3 | 4 | Insufficient budget to implement | Publications
GG | Develop effective and sustainable stakeholder relations | Communication | # of media reports and articles released | 2 | 6 | 7 | 12 | 14 | 18 | 24 |  | Register of publications
GG | Develop effective and sustainable stakeholder relations | Communication | # of website updates | 101 | 16 | 16 | 32 | 43 | 48 | 52 |  | Website update register
GG | Develop effective and sustainable stakeholder relations | Information management | Number of weekly website updates | 21 | 12 | 5 | 24 | 13 | 36 | 48 |  | Website update register
GG | Develop effective and sustainable stakeholder relations | Public Participation | # of local imbizos held (community meetings per ward) | 136 | 34 | 4 | 68 | 4 | 102 | 136 | We have been advised that the ground was not condusive | Minutes and Attendance register
GG | Develop effective and sustainable stakeholder relations | Public Participation | # of people attending imbizo's | 4 | No target - Reporting only | 2000 | No target - Reporting only | 0 | No target - Reporting only | No target - Reporting only | No Imbizos conducted in the 2nd Qtr | Attendance Registers
GG | Develop effective and sustainable stakeholder relations | Public Participation | % of issues raised during Imbizos resolved | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Imbizo Resolution register
GG | Develop effective and sustainable stakeholder relations | Public Participation | # of issues Presidential Imbizos held | none | No target - Reporting only | 0 | No target - Reporting only | 0 | No target - Reporting only | No target - Reporting only |  | Izimbizo Report. Correspondence
GG | Develop effective and sustainable stakeholder relations | Public Participation | % of issues raised at Presidential Imbizo's resolved | 0 | 100% | 0% | 100% | 0% | 100% | 100% | No Imbizos conducted | Izimbizo Report. Correspondence
GG | Develop effective and sustainable stakeholder relations | Public Participation | Number Provincial Imbizos resolved | 0 | Reporting only - no target | 0 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target | No Imbizos conducted | Imbizo Resolution register
GG | Develop effective and sustainable stakeholder relations | Public Participation | % of issues raised during the Provincial Imbizos resolved | 0 | 100% | 0% | 100% | 0% | 100% | 100% | No Imbizos conducted | Imbizo Resolution implementation report
GG | Effective and Efficient administration | Council Support | % of Cluster committees quorated | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cluster and other committee agendas & minutes
GG | Effective and Efficient administration | Council Support | % of Departmental Council resolutions implemented | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Departmental Resolution register
GG | Effective and Efficient administration | Council Support | # of Council meetings held | 13 | 1 | 1 | 2 | 2 | 3 | 4 |  | Mintues and attendance registers
GG | Effective and Efficient administration | Council Support | # of Exco meetings held | 22 | 6 | 4 | 12 | 3 | 18 | 24 |  | Mintues and attendance registers
GG | Effective and Efficient administration | Information management | % Daily Data and mail backup available | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Mail backup logs Data back-up logs
GG | Effective and Efficient administration | Information management | % of legislated website content updated | New indicator | 100% | 100% | 100% | 100% | 100% | 100% |  | Website content checklist
GG | Effective and Efficient administration | Information management | % of Attendance to IT faults within 24Hours. | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Monthly IT reports on Jobs completed (Jobcard based)
GG | Effective and Efficient administration | Information management | % of workstations with access to IT network | 95% | 95% | 95% | 95% | 98% | 95% | 95% |  | Monthly reports
GG | Effective and Efficient administration | Information management | hrs downtime for outside work stations | New indicator | 0 | 95% offline | 0 | 50 | 0 | 0 |  | Down time register
GG | Effective and Efficient administration | Information management | # of employees on laptop scheme | 35 | Reporting only - no target | 35 | Reporting only - no target | 35 | Reporting only - no target | Reporting only - no target |  | Laptop Contract register
GG | Effective and Efficient administration | Legal support | R-value spent on external legal fees | 100000 | Reporting only - no target | 1579022.1 | Reporting only - no target | 4032612.24 | Reporting only - no target | Reporting only - no target |  | Legal Expenditure
GG | Effective and Efficient administration | Legal support | # of legal cases reported | 2 | Reporting only - no target | 0 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target |  | Register of legal cases
GG | Effective and Efficient administration | Management and Administration | # of departmental Manager meetings | 4 | 1 | 1 | 2 | 1 | 3 | 4 |  | Minutes and Attendance registers of Management meetings
GG | Effective and Efficient administration | Performance monitoring and reporting | # of Corporate Services Departmental monthly reports submitted on time | 12 | 3 | 3 | 6 | 6 | 9 | 12 |  | Monthly, quarterly, half yearly and annual reports
GG | Effective and Efficient administration | Performance monitoring and reporting | # of Governance Thrust meetings held | 0 | 1 | 0 | 2 | 1 | 3 | 4 |  | Minutes and Attendance Registers
GG | Effective and Efficient administration | Sound Governance | % of Internal Audit queries responded to within 10 days | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Register of Internal Audit queries & corresponding reports
GG / MFVM | Effective and Efficient administration | Risk management | # Successful claims against the municipality | 0 | 0 | 2 | 0 | 2 | 0 | 0 |  | Register of claims
GG / MFVM | Effective and Efficient administration | Risk management | R-value successful claims against the municipality | 100000 | 0 | 1500000 | 0 | 1500000 | 0 | 0 |  | Reportign only
GG / MFVM | Increase Financial Viability | Expenditure Management | % Personnel costs / Operating expenses (excl Salaries of councillors) | 21.58% | 35% | 29.52% | 35% | 29% | 35% | 35% |  | Budget reports
GG / MFVM | Increase financial viability | Budget management | % of departmental budget spent | 122.9% | 25% | 25.75% | 50% | 56% | 75% | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Financial reporting | % of AG queries responded to within 2 working days | 100% | Not applicable this quarter |  | 100% | 100% | Not applicable this quarter | Not applicable this quarter |  | Register of Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Municipal Assets | # of departmental asset verifications done | 1 | 0 | 1 | 1 | 1 | 1 | 2 |  | Asset verification checklist
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | # of staff appointed (new engagements) | 42 | Reporting only - no target | 10 | Reporting only - no target | 5 | Reporting only - no target | Reporting only - no target | New appointments | Staff establishment
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | # of people from employment equity target groups employed in the three highest levels of management | 19 | 19 | 19 | 19 | 19 | 19 | 22 |  | Employment Equity report
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | % Compliance to Employment Equity plan | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Employment Equity plan & compliance report
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | % of employees that are female | 24% | 24.1% | 34.4% | 27.5% | 34.7% | 31.0% | 35% | New appointments | Employment Equity plan & compliance report
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | % of employees that have a disability | 1.7% | 1.9% | 2.3% | 2.0% | 2.1% | 2.1% | 2.2% | Staff turnover | Employment Equity plan & compliance report
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | % of employees in the three highest levels of management that are female | 32% | 32.5% | 32.5% | 33% | 23% | 33.5% | 35% | Staff turnover | Employment Equity plan & compliance report
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | % of employees that are youth | 31% | 31.5% | 26.5% | 31.5% | 23% | 32% | 35.5% | Rectification | Employment Equity plan & compliance report
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | % of critical posts filled | 100% | 100% | 98% | 100% | 98% | 100% | 100% | Manager (Risk) re-advertised | Staff establishment
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | # of resignations | 7 | Reporting only - no target | 0% | Reporting only - no target | 2% | Reporting only - no target | Reporting only - no target | Retirements | Staff establishment
GG/ MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | # of promotions | 7 | Reporting only - no target | 0% | Reporting only - no target | 2% | Reporting only - no target | Reporting only - no target |  | Staff establishment
GG/ PP | Develop effective and sustainable stakeholder relations | Ward Committees | Number of wards implementing the Funding Model for Ward Committees | 34 | 34 | 34 | 34 | 34 | 34 | 34 |  | Ward committee functionality reports
GG/ PP | Develop effective and sustainable stakeholder relations | Ward Committees | Percentage attendance by Ward Committee members (O9) | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Register of attendance
GG/PP | Develop effective and sustainable stakeholder relations | Ward Committees | # of Ward committee meetings | 102 | 102 | 102 | 204 | 204 | 306 | 408 |  | *Register of Minutes of ward committee meetings *Ward committee & Community feedback meeting programme
GG/PP | Develop effective and sustainable stakeholder relations | Ward Committees | # of quarterly feedback mass meetings | 34 | 34 | 102 | 68 | 68 | 102 | 136 |  | Minutes & Attendance Register of Mass meetings
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Level to which employee performance management has cascaded | new indicator | 3 | 3 | 4 | 3 | 4 | 4 | Performance plans only designed for Level 3's at this stage | Performance Plans for level 4
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | % of CORP Manager's with signed performance plans by 31 July | 100% | 100% | 0% | Not applicable this quarter | 0% | Not applicable this quarter | Not applicable this quarter | Awaiting appointment of Director | Signed Performance Plans
Note on D60: frieda: Outcome9 critical posts are: MM, CFO, Town Planner, Engineer (Technical services), Corporate Services & Communications

## CORP Projects
Quarterly targets per Project - Corporate Services Department
KPA/ Theme | Strategic Objective | Programme | Project | Planned end date | Opex 2012/2013 | Capex 2012/2013 | Qtr Ending Sept '12 | Actual Achieved Sept '12 | Qtr Ending - Dec '12 | Actual End Dec '12 | Qtr Ending - Mar '13 | Qtr Ending - Jun '13 | Reason for deviation | Means of verification
BSD | Optimise infrastructure investment and services | Municipal assets | Mayoral Furniture (Banquet and Entertainment Hall) | 30/06/2013 |  | 105000 | Not applicable this quarter | Not applicable this quarter | Acquisition of furniture and audio system for the Entertainment Hall | Not yet purchased | Not applicable this quarter | Not applicable this quarter | Tenders was advertised but the process was put on hold due to buget constraints | Invoice & Proof of payment
BSD/ MTOD | Develop and build skilled and knowledgeable workforce | Capacity building and Training | Workplace Skills Plan | 30/06/2013 | 1000000 |  | Implement approved Work Place Skills plan. 25% expenditure | R138466 spent on training | Implement approved Work Place Skills plan. 50% Expenditure | 25% spent on training. (R272 451) | Conduct an annual training needs assessment (audit) by February. Consolidate training needs into the Work Place Skills Plan. Implement approved Work Place Skills plan. 75% Expenditure | Finalise the Workplace Skills Plan and implement. Submit to LG Seta by 30 June 2013. Develop a training implementation plan by 30 June 2013. Implement approved Work Place Skills plan. 100% Expenditure Submission of ATR by 30 June '13 | R400 000 from training vote transferred to cover legal costs. | LGSETA Claim form WSP ATR - proof of submission
GG/MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | Career Management and retention | 30/06/2013 |  |  | Imlement Career Management and Retention policy upon approval | Retention Strategy approved by Council | Imlement Career Management and Retention policy upon approval | Retention Strategy implemented | Imlement Career Management and Retention policy upon approval | Imlement Career Management and Retention policy upon approval |  | Council Resolution Career Management and Retention Policy
GG/MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | Personel Provisioning | 30/06/2013 |  |  | Revise Personnel Provisioning policy . | Policy reviewed for submission | Submit Revised policy to Council for approval | Not yet submitted | Monitor implementation of revise policy and report monthly | Monitor implementation of revise policy and report monthly | Further engagmenet needed with stakeholders | Council Resolution Personnel provisioning policy Monthly reports
GG/MTOD | Attract and retain the best human capital to become employer of choice | Human Resource Management | Task software | 30/06/2013 |  | 70000 | Submit Item on Task implementation to Council | Project placed on ice as Council resolved to revert to vd Merwe System | Source quotations for Task software and license | Project placed on ice. | Procure and install Task software. Implement and maintain system | Implement and maintain system | Reverted back to vd Merwe System | Council Resolution Proof of Purchase
GG/MTOD | Attract and retain the best human capital to become employer of choice | Labour Relations | Local Labour Forum | 30/06/2013 |  |  | Coordinate Local Labour Forum meetings. | Co-ordinated Local Labour Forum meetings | Coordinate Local Labour Forum meetings. | Co-ordiantes Local Labour Forum Meetings (3 meetings held up to end Dec 2012) | Coordinate Local Labour Forum meetings. | Coordinate Local Labour Forum meetings. |  | Minutes of Meetings
GG | Attract and retain the best human capital to become employer of choice | Organisational Design | TASK Job evaluation outcome implementation | 30/06/2013 |  |  | Maintain Task Job Evaluation system | Reverted back to vd Merwe System | Maintain Task Job Evaluation system | Reverted back to vd Merwe System | Maintain Task Job Evaluation system | Maintain Task Job Evaluation system | Reverted back to vd Merwe System | Service Register Payroll Organogram
GG | Develop effective and sustainable stakeholder relations | Communication | Communication strategy | 30/06/2013 |  |  | Revise the Communication Strategy in consultation with all Departments | Finalized 19/9/2012 | Submit revised Communication strategy to Council for approval by 30 November '12 | Revised Policy was reverted back by the Governance Committee for consideration. | Ensure that all Official communication activities are in line with the approved strategy | Ensure that all Official communication activities are in line with the approved strategy | It will be resubmitted in the next quarter | Revised Communication Strategy -Council Minutes
GG | Develop effective and sustainable stakeholder relations | Communication | Digital Cameras | 30/06/2013 |  | 15000 | Source quotations and purchase digital cameras | Buy 1 Digital Camera September2012 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter |  | Proof Purchase
GG | Develop effective and sustainable stakeholder relations | Communication | Internal and External Communication | 30/06/2013 | 150000 |  | Collect news from various departments. Develop Quarterly Newsletters. Compile monthly internal newsletter | 1 Newsletter in August | Collect news from various departments. Develop Quarterly Newsletters. Compile monthly internal newsletter | Not done | Collect news from various departments. Develop Quarterly Newsletters. Compile monthly internal newsletter | Collect news from various departments. Develop Quarterly Newsletters. Compile monthly internal newsletter | Due to budget constraints | Copies of newsletters
GG | Develop effective and sustainable stakeholder relations | Communication | Media Relations | 30/06/2013 | 20000 |  | Plan and ensure successful networking session. | Was held on 6 July 2012 | Not applicable this quarter | Not applicable this quarter | Plan and ensure successful networking session. | Not applicable this quarter |  | Activity report
GG | Develop effective and sustainable stakeholder relations | Communication | Municipal Audio System | 30/06/2013 |  | 60000 | Not applicable this quarter | Not applicable this quarter | Acquisition of an Audio system | Not purchased | Not applicable this quarter | Not applicable this quarter | Audio System no longer needed | Proof of purchuse
GG | Develop effective and sustainable stakeholder relations | Communication | Municipal Branding Eqiupment | 30/06/2013 |  | 100000 | Procure branding equipment. Utilise branding equipment and municipal flag to market GTM at all events | Bought 4 X banners during July 2012 | Utilise branding equipment and municipal flag to market GTM at all events | All branding materials are being used at all events and still need more branded equipments of wich will be purchased in the next quarter. | Utilise branding equipment and municipal flag to market GTM at all events | Utilise branding equipment and municipal flag to market GTM at all events |  | Branding equipment proof of purchase Register of events and branding done
GG | Develop effective and sustainable stakeholder relations | Communication | Public Loud Hailing system | 30/06/2013 |  | 70000 | Not applicable this quarter | Not applicable this quarter | Acquisition of a Loud Hailing system | Will be purchased in the 4th Quarter | Not applicable this quarter | Not applicable this quarter |  | Proof of purchuse
GG | Develop effective and sustainable stakeholder relations | Communication | Video cameras | 30/06/2013 |  | 20000 | Source quotations and purchase video cameras | Still at quotation stage | Not applicable this quarter | Will be purchased in the 4th Quarter | Not applicable this quarter | Not applicable this quarter |  | Proof of purchuse
GG | Develop effective and sustainable stakeholder relations | Intergovernmental relations | Municipal IGR | 30/06/2013 | 50000 |  | Ensure regular attendance of IGR meetings and implementation of resolutions | Attended 1 IGR meeting. | Ensure regular attendance of IGR meetings and implementation of resolutions | No meeting was convened. | Ensure regular attendance of IGR meetings and implementation of resolutions | Ensure regular attendance of IGR meetings and implementation of resolutions |  | Minutes and resolutions
GG | Develop effective and sustainable stakeholder relations | Public Participation | Public Participation management | 30/06/2013 | 50000 |  | Coordinate public participation in line with the Strategy and Implementation plan. Finalise integrated public participation programme in consultation with IDP and other Departments by 15 July. | Not done | Review PP implementation plan in line with the strategy and implement | Has been postponed to February | Coordinate and facilitate public participation sessions as per the implementation plan | Coordinate and facilitate public participation sessions as per the implementation plan. Draft public participation programme for 2013/14. | Awaiting the training of ward committees to be finalised by end January | Integrated Public Participation programme, -Reports of programmes implemented
GG | Effective and Efficient administration | Information management | Delegation of Authority | 30/06/2013 | 250000 |  | Review Delegations and and submit to Council for approval. Arrange a Workshop on delegations | To be concluded by 30 November 2012 after Strategic Session. | Not applicable this quarter | The Draft Delegations of Powers was prepared and waiting for Council approval. | Not applicable this quarter | Not applicable this quarter |  | Council Resolution Revised Delegations Report
GG | Effective and Efficient administration | Information management | Maintenance Contract Tally-Genicom line printers | 30/06/2013 | 50000 |  | Source quotations for the maintenance of the Tally-Genicom line printers and appoint | Service provider not appointed, a second request for quotations sent out (not enough provided). | Monitor implementation of SLA for maintenance of Tally-Genicom line printers | SLA monitored for maintenance of Tally-Genicom line printers | Monitor implementation of SLA for maintenance of Tally-Genicom line printers | Monitor implementation of SLA for maintenance of Tally-Genicom line printers | No Deviation | IT reports
GG | Effective and Efficient administration | Information management | Records Binding Machine | 30/06/2013 |  | 60000 | Source Quotations from service providers and purchase binding machine | Request for quotations submitted to SCMU. | Not applicable this quarter | Request to purchase from sole supplier submitted to the CFO for approval | Not applicable this quarter | Not applicable this quarter |  | Proof of Purchase
GG | Effective and Efficient administration | Information management | Rural Broadband connectivity (PP4) | 30/06/2013 |  |  | Provide technical inputs into the provision of connectivity for satalite and Thusong Centres. Attend NDPG task team meetings | Construction of towers has started and revised project workplan indicates end of November 2012 as completion date. | Provide technical inputs into the provision of connectivity for satalite and Thusong Centres. Attend NDPG task team meetings | Seven satellite offices currently connected and online. Currently busy with processes to connect remaining satellite offices to complete Phase 1 | Provide technical inputs into the provision of connectivity for satalite and Thusong Centres. Attend NDPG task team meetings | Provide technical inputs into the provision of connectivity for satalite and Thusong Centres. Attend NDPG task team meetings | No Deviation | Minutes and attendance registers of NDPG meetings
GG | Effective and Efficient administration | Legal support | Arbitration and litigation | 30/06/2013 |  |  | Represent Council in Arbitration and Conciliation report outcome | 2 Arbitrations | Represent Council in Arbitration and Conciliation report outcome | 2 Arbitrations | Represent Council in Arbitration and Conciliation report outcome | Represent Council in Arbitration and Conciliation report outcome |  | Register of cases Progress Reports
GG | Effective and Efficient administration | Regulatory Framework | Promulgation of By-laws | 30/06/2013 |  |  | Appoint service provider for promulgation. Ensure that by-laws are promulgated. Monitor the public participation process and finalise by-laws for promulgation. | Still in Public Participation processes | Ensure that by-laws are promulgated. Monitor the public participation process and finalise by-laws for promulgation | Still in Public Participation Proces | Ensure that by-laws are promulgated. Monitor the public participation process and finalise by-laws for promulgation | Ensure that by-laws are promulgated. Monitor the public participation process and finalise by-laws for promulgation |  | Government Gazette
GG/MTOD | Effective and Efficient administration | Sound Governance | Institutional Plan | 30/06/2013 |  |  | Initiate and monitor organisational re-engineering | Service Provider appointed to conduct benchmarking exercise | Complete Job evaluations | Not yet compeled | Draft Institutional Plan and submit to Council with draft IDP | Finalise institional plan en ensure approval by Council | Task Job evaluation process was enterupted by Council Resolution to revert back to van der Merwe | Council Resolution on Institutional Plan
GG / PP | Develop effective and sustainable stakeholder relations | Ward Committees | Ward Committees Functionality | 30/06/2013 |  |  | Facilitate, co-ordinate and provide administrative support to enable the Ward committees to function effectively. Monitor functionality by compiling Monthly consolidated WC report & report on attendance of meetings | All Wards are supported by the CDF | Facilitate, co-ordinate and provide administrative support to enable the Ward committees to function effectively. Monitor functionality by compiling Monthly consolidated WC report & report on attendance of meetings | 34 wards are all functional | Facilitate, co-ordinate and provide administrative support to enable the Ward committees to function effectively. Monitor functionality by compiling Monthly consolidated WC report & report on attendance of meetings | Facilitate, co-ordinate and provide administrative support to enable the Ward committees to function effectively. Monitor functionality by compiling Monthly consolidated WC report & report on attendance of meetings |  | Monthly Consolidated WC report Register of Attendance
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance monitoring & evaluation | 30/06/2013 |  |  | Participate in the Annual Performance Assessment for 2011/12. Ensure that scoresheets are completed in time & POEs are complete | 2011/12 Performance Assessment posponed | Conduct an informal assessment of 1st Quarter Performance of relevant employees in the Department and send report to the MM by 21 October '12 | No Informal assessment was conducted because of non signing of Performance Agreement by Managers | Participate in the mid-year employee performance evaluations for 2012/13. Ensure that scoresheets are completed in time & POEs are complete | Conduct an informal assessment of the 3rd Quarter Performance of relevant employees in the Department and submit report to the MM by 20 April '13 |  | 1st & 3rd Qtr Informal Departmental Individual Performance Reports Correspondence
SR/LED | Integrated Developmental Planning | Integrated Development Planning | IDP implementation monitoring | 30/06/2013 |  |  | Arrange quarterly Good Governance Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | No Thrust meeting held. | Arrange quarterly Good Governance Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | Thrust Committee not been established only Councillor Committees are to process | Arrange quarterly Good Governance Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | Arrange quarterly Good Governance Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM |  | Stakeholder list Minutes proof of submission to MM
Note on K2: Frieda Human: Actual activity undertaken in period
Note on N2: Frieda Human: Why was target not achieved??

## DMO KPIs
Key Performance Indicators (KPIs) - Mayors Office
KPA/ Theme | Strategic Objective | Programme | Departmental KPI | Baseline (end June 2012) | Target Sept '12 | Actual Sept '12 | Target Dec '12 | Actual End Dec '12 | Target Mar '13 | Target Jun '13 | Reason for deviation | Means of verification
BSD | Promote environmentally sound practices and social development | Health well- being | # of HIV/AIDS council meetings | 0 | 1 | 0 | 2 | 0 | 3 | 4 | HIV officer not appointed | Minutes & Attendance registers
BSD | Promote environmentally sound practices and social development | Health well- being | # Of HIV/AIDS campaigns or initiatives implemented and supported | 0 | 1 | 0 | 2 | 0 | 3 | 4 | HIV officer not appointed | Invitations, Programmes & Minutes of preparatory meetings
BSD | Promote environmentally sound practices and social development | Health well- being | # of Community members attending external HIV/AIDS awareness sessions | 0 | Reporting only - no target | 0 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target | HIV officer not appointed | Attendance Records
BSD | Promote environmentally sound practices and social development | Health well- being | # of employees attending internal HIV/AIDS awareness sessions | 0 | Reporting only - no target | 0 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target | HIV officer not appointed | Attendance Registers
BSD | Promote environmentally sound practices and social development | Health well- being | # of internal peer educators trained | 0 | 22 | 0 | Not applicable this quarter | 0 | Not applicable this quarter | 22 | HIV officer not appointed | Attendance registers
BSD | Promote environmentally sound practices and social development | Health well- being | # of by-monthly meetings held with peer educators | 0 | 1 | 0 | 3 | 0 | 4 | 6 | HIV officer not appointed | Minutes & Attendance registers
BSD | Promote environmentally sound practices and social development | Health well- being | # of condoms distributed | 0 | Reporting only - no target | 0 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target | HIV officer not appointed | Monthly report
BSD | Promote environmentally sound practices and social development | Health well- being | # HIV/AIDS Councillors trained | 0 | Reporting only - no target | 0 | Reporting only - no target | 0 | Reporting only - no target | Reporting only - no target | HIV officer not appointed | Training attendance register
BSD | Promote environmentally sound practices and social development | Health well- being | # of newsletter updates relating to HIV/AIDS | 0 | 1 | 0 | 2 | 0 | 3 | 4 | HIV officer not appointed | News Letters
BSD | Promote environmentally sound practices and social development | Health well- being | # of Website updates relating to HIV/AIDS | 0 | 1 | 0 | 2 | 0 | 3 | 4 | HIV officer not appointed | Website updates
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | # of Jobs created by Municipal Capital projects for youth | 269 | Reporting only - no target | 1196 | Reporting only - no target | 1201 | Reporting only - no target | Reporting only - no target |  | Consolidated Job creation reports
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | # of Jobs created by Municipal Capital projects for women | 114 | Reporting only - no target | 330 | Reporting only - no target | 330 | Reporting only - no target | Reporting only - no target |  | Consolidated Job creation reports
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | # of Jobs created by Municipal Capital projects for disabled persons | 15 | Reporting only - no target | 2 | Reporting only - no target | 2 | Reporting only - no target | Reporting only - no target |  | Consolidated Job creation reports
GG | Effective and Efficient administration | Council Support | % of Departmental Council resolutions implemented | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Departmental Resolution register
GG | Effective and Efficient administration | Management and Administration | # of departmental meetings | 0 | 1 | 0 | 2 | 0 | 3 | 4 | Position of Director vacant Attending CORP meetings | Minutes and Attendance registers of Departmental meetings
GG | Effective and Efficient administration | Performance monitoring and reporting | # of Office of the Mayor Departmental monthly reports submitted on time | N/A | 3 | 0 | 6 | 0 | 9 | 12 | Incorporated into CORP | Monthly, quarterly, half yearly and annual reports
GG | Effective and Efficient administration | Sound Governance | % of Internal Audit queries responded to within 10 days | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Register of Internal Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Budget management | % of departmental budget spent | 93% | 25% | 27% | 50% | 51.67% | 75% | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Financial reporting | % of AG queries responded to within 2 working days | 100% | Not applicable this quarter | Not applicable this quarter | 100% | 100% | Not applicable this quarter | Not applicable this quarter |  | Register of Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Municipal Assets | # of departmental asset verifications done | 1 | 0 | 0 | 1 | 0 | 1 | 2 |  | Asset verification checklist

## DMO Projects
Quarterly targets per Project - Mayors Office
KPA/ Theme | Strategic Objective | Programme | Project | Planned end date | Opex 2012/2013 | Capex 2012/2013 | Qtr Ending Sept '12 | Actual Achieved Sept '12 | Qtr Ending - Dec '12 | Actual end Dec '12 | Qtr Ending - Mar '13 | Qtr Ending - Jun '13 | Reason for deviation | Means of verification
BSD | Promote environmentally sound practices and social development | Health well-being | HIV/AIDS Council | 30/06/2013 |  |  | Arrange Quarterly HIV/AIDS Council sittings submit report to Council. | No progress | Arrange Quarterly HIV/AIDS Council sittings submit report to Council. | No progress | Arrange Quarterly HIV/AIDS Council sittings submit report to Council. | Arrange Quarterly HIV/AIDS Council sittings submit report to Council. | HIV officer not appointed | Agenda & Minutes - Council Items
BSD | Promote environmentally sound practices and social development | Health well-being | HIV/AIDS mainstreaming | 30/06/2013 |  |  | Monitor HIV/AIDS mainstreaming ensure that HIV/AIDS awareness is included in all SLAs and municipal programmes | No progress | Monitor HIV/AIDS mainstreaming ensure that HIV/AIDS awareness is included in all SLAs and municipal programmes | No progress | Monitor HIV/AIDS mainstreaming ensure that HIV/AIDS awareness is included in all SLAs and municipal programmes | Monitor HIV/AIDS mainstreaming ensure that HIV/AIDS awareness is included in all SLAs and municipal programmes | HIV officer not appointed | Correspondence
BSD | Promote environmentally sound practices and social development | Health well-being | HIV/Aids management | 30/06/2013 | 30000 |  | Conduct 1 workshop for peer educators | No progress | Conduct workshop on HIV/Aids awareness for all ward committee members responsible for health | No progress | Refresher course for peer educators | Not applicable this quarter | HIV officer not appointed | Attendance registers
BSD | Promote environmentally sound practices and social development | Health well-being | HIV/Aids seminars for target groups | 30/06/2013 | 27000 |  | Conduct seminar targeting female church representatives | No progress | Conduct seminar targeting youth leaders | No progress | Not applicable this quarter | Not applicable this quarter | HIV officer not appointed | Attendance register
BSD | Promote environmentally sound practices and social development | Health well-being | HIV/Aids theme day celebrations | 30/06/2013 | 40000 |  | Not applicable this quarter | Not applicable this quarter | Red Ribbon Month (Nov) World Aids Day (Dec) | No progress | Not applicable this quarter | World TB day (Apr) | HIV officer not appointed | Action plans, Correspondence
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | Annual Youth Assembly | 30/06/2013 | 35000 |  | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Arrange and co-ordinate Annual youth assembly during June 2013 |  | Youth Assembly agenda & attendance register
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | Disability Council Official Launch | 30/06/2013 | 30000 |  | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Arrange and co-ordinate launch of Disability Council during June 2013 |  | Disability Council minutes & attendance register
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | National Disability Month Celebrations | 30/06/2013 | 30000 |  | Not applicable this quarter | Not applicable this quarter | Arrange and co-ordinate national disability month celebrations during December | * Local Celebrations held on 28/11/2012 in Nkowankowa Community Hall (100 disabled) * 22 disabled sent to District celebrations in Lulekani community hall on 07/12/2012 * 60 disabled sent to Provincial event at mankweng on 04/12/2012 | Not applicable this quarter | Not applicable this quarter |  | Disability month activity plan & report
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | National Women's Month Celebrations | 30/06/2013 | 35000 |  | Arrange and co-ordinate national women's month celebrations during August | Transport was provided to Provincial Womans day celebration (R9,000.00) | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter |  | Women's month activity plan & report
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | National Youth Month celebrations | 30/06/2013 | 70000 |  | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Arrange and co-ordinate national youth month celebrations during June |  | Youth month activity plan and report
| Promote environmentally sound practices and social development | Youth, Gender & Disability support | Annual Men's indaba | 30/06/2013 | 70000 |  | Arrange and coordinate Annual Mens Indaba and report to Council | No progress will be hosted February 2013 | Not applicable this quarter | No progress will be hosted February 2013 | Not applicable this quarter | Preperations for Annual Men's Indaba |  | Agenda & Attendance Register
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | Relaunch Of SAWID | 30/06/2013 | 40000 |  | Not applicable this quarter | Not applicable this quarter | Arrange and co-ordinate relaunch of SAWID during November. | Will be hosted in february 2013 in colaboration with Men's Indaba | Not applicable this quarter | Arrange launching of young SAWID during June . | It clashed with other events | SAWID agenda & attendance register Young SAWID agenda & attendance Register
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | 16 Days of activism against Women and child abuse | 30/06/2013 | 10000 |  | Not applicable this quarter | Not applicable this quarter | Arrange and coordinate 16 days of activism campaign in November | Incoporated into GTM AIDS day event | Not applicable this quarter | Not applicable this quarter | Budgetary constraints | Agenda & Attendance Register
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | Youth Strategic Session | 30/06/2013 | 25000 |  | Arrange and co-ordinate Youth strategic session during September | YSS scheduled for 25/10/2012 at Tzaneen Country lodge | Not applicable this quarter | 60 Youth from wards youth organisations and SAYC met on a strategic session on 23/10/2012 at Tzaneen Country Lodge | Arrange and co-ordinate Youth strategic session during March | Not applicable this quarter |  | Agenda & Attendance register for the Youth Strategic Session
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | Young Entrepreneur summit | 30/06/2013 | 25000 |  | Not applicable this quarter | Not applicable this quarter | Arrangements for Young Entrepreneur summit | Youth Entrepreneurs summit was held on 23/11/2012 at Nedtex Lodge (50 entrepreneurs) | Arrange and coordinate young entrepreneur summit and submit report to Council | Not applicable this quarter |  | Agenda & Attendance Register
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | Youth Plenaries | 30/06/2013 | 15000 |  | Arrange and Coordinate Youth Plenary quarterly | Youth plenary scheduled for 19/10/2012 at Runymede TSC | Arrange and Coordinate Youth Plenary quarterly | Youth Plenary was held on 19/10/2012 at Runnymede TSC attended by 30 youth organisations & SAYC | Arrange and Coordinate Youth Plenary quarterly | Arrange and Coordinate Youth Plenary quarterly |  | Agenda & Attendance Registers
GG | Effective and Efficient administration | Council Support | Office of the Chief Whip Support | 30/06/2013 |  |  | Ensure effective administration in the Office of the Chief Whip. | Administrative support provided to the Chief Wip | Ensure effective administration in the Office of the Chief Wip. Facilitate the appointment of a secretary for the Chief Whip | Administrative support provided to the Chief Wip | Ensure effective administration in the Office of the Chief Whip by providing secretarial support | Ensure effective administration in the Office of the Chief Whip by providing secretarial support |  | Appointment letter of Secretary Monthly activity reports
GG | Effective and Efficient administration | Council Support | Office of the Mayor support | 30/06/2013 |  |  | Ensure effective administration in the Office of the Mayor by providing administrative and logistical support | Administrative support provided to the Mayor | Ensure effective administration in the Office of the Mayor by providing administrative and logistical support | Administrative support provided to the Mayor | Ensure effective administration in the Office of the Mayor by providing administrative and logistical support | Ensure effective administration in the Office of the Mayor by providing administrative and logistical support |  | Monthly Activity Reports
GG | Effective and Efficient administration | Council Support | Office of the Speaker Support | 30/06/2013 |  |  | Ensure effective administration in the Office of the Speaker. Coordinate Administrative support in terms of Public Participation | Administrative support provided to the Speaker | Ensure effective administration in the Office of the Speaker. Coordinate Administrative support in terms of Public Participation | Administrative support provided to the Speaker | Ensure effective administration in the Office of the Speaker. Coordinate Administrative support in terms of Public Participation | Ensure effective administration in the Office of the Speaker. Coordinate Administrative support in terms of Public Participation |  | Correspondence -Public Participation report -Consolidated Ward Committee report
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance monitoring & evaluation | 30/06/2013 |  |  | Participate in the Annual Performance Assessment for 2011/12. Ensure that scoresheets are completed in time & POEs are complete | No progress. Position of Director Vacant. No budget for position | Conduct an informal assessment of 1st Quarter Performance of relevant employees in the Department and send report to the MM by 21 October '12 | No progress. Position of Director Vacant. No budget for position | Participate in the mid-year employee performance evaluations for 2012/13. Ensure that scoresheets are completed in time & POEs are complete | Conduct an informal assessment of the 3rd Quarter Performance of relevant employees in the Department and submit report to the MM by 20 April '13 |  | 1st & 3rd Qtr Informal Departmental Individual Performance Reports Correspondence

## EED KPIs
Key Performance Indicators (KPIs) - Electrical Engineering Department
KPA/ Theme | Strategic Objective | Programme | Departmental KPI | Baseline (end June 2012) | Target Sept '12 | Actual Sept '12 | Target Dec '12 | Actual End Dec '12 | Target Mar '13 | Target Jun '13 | Reason for deviation | Means of verification
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | Nr of households with access to basic (or higher) electricity | 77116 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 79933 |  | Eskom reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | % electricity backlog ( # Households that needs electrical connections / Total # households as %) (Electrification) | 14.15 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 11.8% |  | Eskom reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | # of new electricity connections in licensed distribution area | 36 | Reporting only - no target | 12 | Reporting only - no target | 25 | Reporting only - no target | Reporting only - no target |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | MVA Electricity available (town) (firm capacity) | 35 | Reporting only - no target | 55 | Reporting only - no target | 55 | Reporting only - no target | 45 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | MVA Electricity available (outlying) (firm capacity) | 40 | Reporting only - no target | 40 | Reporting only - no target | 40 | Reporting only - no target | 50 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | Total electricity purchased (in kWh) | 374727628 | Reporting only - no target |  | Reporting only - no target | 193605366 | Reporting only - no target | Reporting only - no target |  | Revenue reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure | The total electricity supplied & metered (in kWh) | 326987328 | Reporting only - no target |  | Reporting only - no target | 159629824 | Reporting only - no target | Reporting only - no target |  | Revenue reports
BSD | Optimise infrastructure investment and services | Cost Recovery | % of Electricity losses | 12.74% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Reported Annually | Not applicable this quarter | 12% |  | Revenue reports
BSD | Optimise infrastructure investment and services | Cost Recovery | R-value of electricity loss | 31690462 | Reporting only - no target | Reported Annually | Reporting only - no target | Reported Annually | Reporting only - no target | Reporting only - no target |  | Revenue reports
BSD | Optimise infrastructure investment and services | Cost Recovery | Total kwh electricity loss | 47740299 | Reporting only - no target | Reported Annually | Reporting only - no target | Reported Annually | Reporting only - no target | Reporting only - no target |  | Revenue reports
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | R-value electricity maintenance | 19646538 | 4911634.5 | 2391352 | 9823269 | 16808973 | 14734903.5 | 19606539 |  | Budget expenditure
GG | Effective and Efficient administration | Council Support | % of Departmental Council resolutions implemented | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Departmental Resolution register
GG | Effective and Efficient administration | Management and Administration | # of departmental meetings | 2 | 0 | 0 | 1 | 1 | 1 | 2 |  | Minutes and Attendance registers of Departmental meetings
GG | Effective and Efficient administration | Performance monitoring and reporting | # of Electrical Engineering Departmental monthly reports submitted on time | 12 | 3 | 3 | 6 | 6 | 9 | 12 |  | Monthly, quarterly, half yearly and annual reports
GG | Effective and Efficient administration | Sound Governance | % of Internal Audit queries responded to within 10 days | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Register of Internal Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Budget management | % of departmental budget spent | 98% | 25% | 22.6% | 50% | 46% | 75% | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Expenditure Management | % of capital budget for electricity spent | 97% | 10% | 0..31% | 20% | 8% | 50% | 100% | Waiting for Capital from loan | Approved Departmental budget 31 May 2010
GG / MFVM | Increase financial viability | Financial reporting | % of AG queries responded to within 2 working days |  | Not applicable this quarter | Not applicable this quarter | 100% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter |  | Register of Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Municipal Assets | # of departmental asset verifications done | 1 | 0 | 0 | 1 | 0 | 1 | 2 |  | Bi-annual Asset verification checklist
LED | Integrated developmental planning | Integrated Spatial Development | % of departmental capital spent in the priority areas identified in Spatial Development Framework | 100% | 100% | Not applicable this quarter | 100% | 8.26% | 100% | 100% |  | Revised SDF vs Capital Expenditure
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | % of EED Manager's with signed performance plans by 31 July | 100% | 100% | 100% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter |  | Signed Performance Plans
| Improve access to sustainable and affordable services | Electricity Infrastructure | # of new household connections in villages (DOE grant) | 1015 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 1349 |  | Project progress reports

## EED Projects
Quarterly targets per Project - Electrical Engineering Department
KPA/ Theme | Strategic Objective | Programme | Project | Planned end date | Opex 2012/2013 | Capex 2012/2013 | Qtr Ending Sept '12 | Actual Achieved Sept '12 | Qtr Ending - Dec '12 | Actual End Dec '12 | Qtr Ending - Mar '13 | Qtr Ending - Jun '13 | Reason for deviation | Means of verification
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Capacity to Rainbow Chickens (phase 1) | 30/06/2013 |  | 1000000 | Monitor and approve the Design and procurement of contractor by Rainbow Chickens | No progress | Monitor construction and ensure compliance to set standards | No progress | Monitor construction and ensure compliance to set standards | Final inspection and commissioning of line and substation | Awaiting Capital from loan | Project progress reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electricity Capacity Building in phases | 30/06/2013 |  | 14000000 | Design and procurement of contractor for cabling from Prison to Extention 53 | No progress | Ground work initiated | No progress due to no capital | Cable 50% installed | Cable installation completed | Awaiting Capital from loan | Project progress reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electrification of Lekgwareng (215 units) | 30/06/2013 | 2200000 |  | Designs approved | Busy with Appointment of Service Provider | Contracter appointed | Project at design stage | Project 50% completed | Project completed 215 units energised |  | Consultant Reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electrification of Mandlakazi (90 units) | 30/06/2013 | ESKOM |  | Monitor progress and report to Council and Local Energy Forum | Busy with Appointment of Service Provider | Monitor progress and report to Council and Local Energy Forum | Project at construction phase | Monitor progress and report to Council and Local Energy Forum | Monitor progress and report to Council and Local Energy Forum |  | Progress reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electrification of Mathipa (Senopelwa)(624 units) | 30/06/2013 | ESKOM |  | Monitor progress and report to Council and Local Energy Forum | Project at Construction Phase | Monitor progress and report to Council and Local Energy Forum | Project at construction phase | Monitor progress and report to Council and Local Energy Forum | Monitor progress and report to Council and Local Energy Forum |  | Progress reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electrification of Mbekwana and Lwandlamuni (570 units) | 30/06/2013 | 5450000 |  | Designs approved | Busy with Appointment of Service Provider | Contracter appointed | Project at design stage | Project 50% completed | Project completed 570 units energised |  | Consultant Reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electrification of Mohlaba Cross and Malekeke (564 units) | 30/06/2013 | 5350000 |  | Designs approved | Busy with Appointment of Service Provider | Contracter appointed | Project at design stage | Project 50% completed | Project completed 564 units energised |  | Consultant Reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electrification of Moime Extension(125 units) | 30/06/2013 | ESKOM |  | Monitor progress and report to Council and Local Energy Forum | Busy with Appointment of Service Provider | Monitor progress and report to Council and Local Energy Forum | Busy with Appointment of Service Provider | Monitor progress and report to Council and Local Energy Forum | Monitor progress and report to Council and Local Energy Forum |  | Progress reports
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electrification of Mokgolobotho and Dan Ext 1&2 (Phase 2) | 30/06/2013 | 9000000 |  | Source funding to complete Dan Extention | Busy with Appointment of Service Provider | Source funding to complete Dan Extention | Design approved by Eskom awaiting handover | Electrification of 544 households | Not applicable this quarter |  | Monthly report
BSD | Improve access to sustainable and affordable services | Electricity Infrastructure Development | Electrification of Mokomotjie (85 units) | 30/06/2013 | ESKOM |  | Monitor progress and report to Council and Local Energy Forum | Busy with Appointment of Service Provider | Monitor progress and report to Council and Local Energy Forum | Busy with Appointment of Service Provider | Monitor progress and report to Council and Local Energy Forum | Monitor progress and report to Council and Local Energy Forum |  | Progress reports
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Auto Reclosers | 30/06/2013 |  | 2000000 | Identification of areas and planning of installations | No progress | Place orders for auto reclosers | No progress | Auto reclosers delivered | Installation of auto reclosers (estimated 2 X 33kv & 6 X 11kv) | Awaiting Capital from loan | Monthly Report
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Capital Tools (Outlying) | 30/06/2013 |  | 250000 | Procurement of tools as & when required | R17 231.62 spent on purrchase of capital tools | Procurement of tools as & when required | R36 165.59 on Purchase of Capital Tools | Procurement of tools as & when required | Procurement of tools as & when required | No Deviation | Monthly Report
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Capital Tools (Town) | 30/06/2013 |  | 250000 | Not applicable this quarter | R7,877.0 spent on capital tools | Procurement of tools as & when required | R21 979 Spent on Purchase of Capital Tools | Procurement of tools as & when required | Procurement of tools as & when required | No Deviation | Monthly Report
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Electricity network upgrading | 30/06/2013 |  | 5000000 | Allocate funding acquired trough service contribution payments to projects for increased capacity. | Planning started on expanding infrastructure with new capasity project | Allocate funding acquired trough service contribution payments to projects for increased capacity | Awaiting approval for prison sub. Material bought for prison sub and Letsitele main sub on rollover funds. | Allocate funding acquired trough service contribution payments to projects for increased capacity | Allocate funding acquired trough service contribution payments to projects for increased capacity | Awaiting Capital from loan | Allocate funding acquired trough service contribution payments to projects for increased capacity
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Reactive and preventive maintenance on overhead lines and equipment (Outlying) | 30/06/2013 | 3364358 |  | Ongoing maintenance on overhead lines within Outlying distribution network | Ongoing maintenance on overhead lines within Outlying distribution network | Ongoing maintenance on overhead lines within Outlying distribution network | Ongoing maintenance on overhead lines within outlying distribution network | Ongoing maintenance on overhead lines within Outlying distribution network | Ongoing maintenance on overhead lines within Outlying distribution network | No Deviation | Weekly report
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Reactive and preventive maintenance on Town distribution, machinery and equipment (Town) | 30/06/2013 | 2006737 |  | Reactive and preventive maintenance on Town distribution, machinery and equipment (Town) | Reactive and preventive maintenance on Town distribution, machinery and equipment (Town) | Reactive and preventive maintenance on Town distribution, machinery and equipment (Town) | Reactive and preventive maintenance on Town distribution, machinery and equipment (town) | Reactive and preventive maintenance on Town distribution, machinery and equipment (Town) | Reactive and preventive maintenance on Town distribution, machinery and equipment (Town) | No Deviation | Capital Spend on Budget
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Rebuilding of Lines | 30/06/2013 |  | 3000000 | Identification of lines to be rebuild | No progress | 5km of lines rebuilt | No progress | 10km of lines rebuilt | 15 km lilnes rebuilt | Awaiting Capital from loan | Project progress reports/ spreadsheet
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Refurbish of distribution network (Outlying) | 30/06/2013 | 770000 |  | Ongoing maintenance on Outlying distribution network | Ongoing maintenance on Outlying distribution network | Ongoing maintenance on Outlying distribution network | Ongoing maintenance | Ongoing maintenance on Outlying distribution network | Ongoing maintenance on Outlying distribution network | No Deviation | Weekly report
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Streetlight Maintenance (Town) | 30/06/2013 | 257123 |  | Maintain all street lights in municipal area | Streetlight Maintenance Ongoing R186,523.00 spent | Maintain all street lights in municipal area | Streetlight Maintenance ongoing R237 095 spent | Maintain all street lights in municipal area | Maintain all street lights in municipal area | Overspending due to backlog from vehicles | Capital Spend on Budget
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Substation Maintenance (Outlying) | 30/06/2013 | 600000 |  | Ongoing maintenance on substations within Outlying distribution network | Ongoing maintenance on substations within Outlying distribution network | Ongoing maintenance on substations within Outlying distribution network | Ongoing maintenance outlying distribution | Ongoing maintenance on substations within Outlying distribution network | Ongoing maintenance on substations within Outlying distribution network | No Deviation | Weekly report
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Traffic Lights LED | 30/06/2013 | 20215 |  | Maintain all Robots | All Traffic Lights LED maintained. R2,065.00 spent | Maintain all Robots | All traffic lights LED maintained. R2 881,00 spent | Maintain all Robots | Maintain all Robots | No Deviation | Capital Spend on Budget
BSD | Optimise infrastructure investment and services | Electricity network upgrade and maintenance | Upgrading Tzaneen Town network including cables | 30/06/2013 |  | 2,000,000 (carried over) | Acquire permission from DPW to construct Switching station | R20,781.56 spent. Surveys done and awaiting final permission to construct switching station | Construction of Switching Substation and cabling complete | 631 637,21 spent on construction of switching and cabling | Not applicable this quarter | Not applicable this quarter | Waiting approval of Prison substation. | Project Certificates & Progress reports
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance monitoring & evaluation | 30/06/2013 |  |  | Participate in the Annual Performance Assessment for 2011/12. Ensure that scoresheets are completed in time & POEs are complete | Annual Performance Assessment not yet conducted | Conduct an informal assessment of 1st Quarter Performance of relevant employees in the Department and send report to the MM by 21 October '12 | Verbal informal assessment done, no report generated | Participate in the mid-year employee performance evaluations for 2012/13. Ensure that scoresheets are completed in time & POEs are complete | Conduct an informal assessment of the 3rd Quarter Performance of relevant employees in the Department and submit report to the MM by 20 April '13 |  | 1st & 3rd Qtr Informal Departmental Individual Performance Reports Correspondence
Note on D8: Frieda Human: Sam to provide expenditure projections for DOE projects

## ESD KPIs
Key Performance Indicators (KPIs) - Engineering Services Department
KPA/ Theme | Strategic Objective | Programme | Departmental KPI | Baseline (end June 2012) | Target Sept '12 | Actual Sept '12 | Target Dec '12 | Actual End Dec '12 | Target Mar '13 | Target Jun '13 | Reason for deviation | Means of verification
BSD | Improve access to sustainable and affordable services | Building Control | % decrease in non-compliance to building regulations | 40% | not applicable this quarter | not applicable this quarter | not applicable this quarter | Not applicable this quarter | not applicable this quarter | 30% |  | Register of contraventions
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Km of new municipal roads constructed (gravel) | 0 | not applicable this quarter | not applicable this quarter | 11 | Not applicable | not applicable this quarter | 21 | Regravelling capital projects are no longer taking place because we are doing tar road. | Monthly reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Km of roads tarred | 0 | Not applicable this quarter | not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 21 |  | Road Progress Reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | # of MIG roads projects on schedule | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 project was on hold due to court interdict | Project progress reports
BSD | Improve access to sustainable and affordable services | Water and sanitation services | Number of households with access to basic (or higher) sanitation | 13192 | 13138 | 13138 | 13158 | 13158 | 13178 | 13198 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Water and sanitation services | Number of households with access to basic (or higher) levels of water | 70110 | 70050 | 70050 | 70070 | 70050 | 70090 | 70110 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Water and sanitation services | m³ increase of water quota | 0 | 2.4 million m³ | 0 | 2.4 million m³ | 0 | 2.4 million m³ | 3.8million m3 | Application has been rejected by DWA | Correspondence from DWAF
BSD | Improve access to sustainable and affordable services | Water and sanitation services | # of new basic water connections | 89 | 50 | 24 | 70 | 43 | 90 | 110 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Water and sanitation services | # metered water connections / total figure of households as % | 0.1% | 0.5% | 0% | 0.5% | 0.0043% | 0.5% | 0.5% |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Water and sanitation services | Total operating cost of water distribution function | 2750000 | No target - Reporting only | 285676 | No target - Reporting only | No target - Reporting only | No target - Reporting only | No target - Reporting only |  | Expenditure report
BSD | Improve access to sustainable and affordable services | Water and sanitation services | # of new water borne sanitation connections | 50 | No target - Reporting only | 6 | No target - Reporting only | 0 | No target - Reporting only | No target - Reporting only |  | Register of new connections
BSD | Improve access to sustainable and affordable services | Water and sanitation services | Total operating cost of sewerage function | 500000 | No target - Reporting only | 46620 | No target - Reporting only | No target - Reporting only | No target - Reporting only | No target - Reporting only |  | Expenditure report
BSD | Integrated developmental planning | Formalisation of informal settlements | Nr of households in informal settlements provided with water | not applicable | No target - Reporting only | not applicable | No target - Reporting only | not applicable | No target - Reporting only | No target - Reporting only | MDM function | Monthly reports
BSD | Integrated developmental planning | Formalisation of informal settlements | Nr of households in informal settlements provided with sanitation | not applicable | No target - Reporting only | not applicable | No target - Reporting only | not applicable | No target - Reporting only | No target - Reporting only | MDM function | Monthly reports
BSD | Optimise infrastructure investment and services | Cost Recovery | % Water unaccounted for (water losses) | 6% | 6% | 5% | 6% | 5.8% | 6% | 6% |  | Water distribution reports
BSD | Optimise infrastructure investment and services | Cost Recovery | R-value of unaccounted water | R 200 000 | Reporting only - no target | 3368.38 | Reporting only - no target | Reporting only - no target | Reporting only - no target | Reporting only - no target |  | Water distribution reports
BSD | Optimise infrastructure investment and services | Fleet Management | R-value spent on fleet maintenance as % of asset value | 30% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 20% |  | Expenditure reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Office space backlog | 200 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 200 |  | Expenditure reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | R-value spent on maintenance of municipal buildings as % of asset value | 44% | Not applicable this quarter | not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 15%
BSD | Optimise infrastructure investment and services | Roads & Storm water upgrading and maintenance | R-value spent on road and storm water maintenance | 27622503 | 8455779.25 | 4050233 | 16911558.5 | 7846970 | 25367337.75 | 33823117 |  | ESD Expenditure reports
BSD | Optimise infrastructure investment and services | Roads and Storm water maintenance and upgrade | R-value spent on maintenance of roads infrastructure as % of asset value | 5% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 5% |  | Expenditure reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | % reduction in distribution losses (water) | 10% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 5% |  | Water distribution reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | R-value spent on water and sanitation infrastructure maintenance | 1533949 | 492500 | R 491 274.00 | 492500 | 953874 | 492500 | 492500 | No breakdowns reporte | Expenditure reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | # of service delivery interruptions (water services) | 120 | 30 | 0 | 60 | 0 | 90 | 120 | No breakdowns reporte | Monthly reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | # of households affected through interruptions (water) | 6000 | 6000 | 0 | 6000 | 0 | 6000 | 6000 | No breakdowns reporte | Monthly reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | # of service delivery interruptions (sanitation) | 120 | 30 | 0 | 60 | 0 | 90 | 120 | No breakdowns reporte | Monthly reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | # of households affected through interruptions (sanitation) | 6000 | 6000 | 0 | 6000 | 0 | 6000 | 6000 | No breakdowns reporte | Monthly reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | R-value spent on maintenance of water infrastructure as % of asset value (5towns) | 23% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 43.8% |  | Expenditure reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | R-value spent on maintenance of sanitation infrastructure as % of asset value (5towns) | 41% | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 41.3% |  | Expenditure reports
BSD | Promote environmentally sound practices and social development | Environmental Health management | % of daily samples taken complying to SANS 241 | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Records of samples and reports
GG | Effective and Efficient administration | Council Support | % of Departmental Council resolutions implemented | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Departmental Resolution register
GG | Effective and Efficient administration | Legal support | # of Departmental policies developed | 0 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 1 |  | Approved Fleet policy
GG | Effective and Efficient administration | Management and Administration | # of departmental meetings | 4 | 1 | 3 | 2 | 4 | 3 | 4 |  | Minutes and Attendance registers of Departmental meetings
GG | Effective and Efficient administration | Performance monitoring and reporting | # of Engineering Services Departmental monthly reports submitted on time | 12 | 3 | 3 | 6 | 6 | 9 | 12 |  | Monthly, quarterly, half yearly and annual reports
GG | Effective and Efficient administration | Performance monitoring and reporting | # of Service Delivery Thrust meetings held | 0 | 1 | 0 | 2 | 0 | 3 | 4 | no thrust meeting | Minutes and Attendance Registers
GG | Effective and Efficient administration | Sound Governance | % of Internal Audit queries responded to within 10 days | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Register of Internal Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Budget management | % of departmental budget spent | 81% | 25% | 11% | 50% | 40% | 75% | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Expenditure Management | % of ESD capital budget spent | 61% | 10% | 11% | 20% | 18% | 50% | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Financial reporting | % of AG queries responded to within 2 working days | 100% | Not applicable this quarter | Not applicable this quarter | 100% | 100% | Not applicable this quarter | Not applicable this quarter |  | Register of Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Municipal Assets | # of departmental asset verifications done | 1 | 0 | 1 | 1 | 1 | 1 | 2 |  | Asset verification checklist
GG/MFMA | Financial Viability | Budget management | % MIG funding spent | 61% | 10% | 11% | 50% | 25% | 75% | 100% | could not spend on the other project due to court interdict | Budget printout
LED | Create Community beneficiation and empowerment opportunities | Extended Public Works | # of jobs created through EPWP projects | 272 | Reporting only - no target | 79 | Reporting only - no target | 79 | Reporting only - no target | Reporting only - no target |  | EPWP reports
LED | Integrated developmental planning | Integrated Spatial Development | % of departmental capital spent in the priority areas identified in Spatial Development Framework | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Revised SDF vs Capital Expenditure
LED | Integrated developmental planning | Integrated Spatial Development | # new serviced sites available for alienation per annum | 360 | Reporting only - no target | 1560 | Reporting only - no target | 1560 | Reporting only - no target | Reporting only - no target |  | Records of correspondence
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | % of ESD Manager's with signed performance plans by 31 July | 100% | 100% | 100% | 100% | 100% | Not applicable this quarter | Not applicable this quarter |  | Signed Performance Plans

## ESD Projects
Quarterly targets per Project - Engineering Services Department
KPA/ Theme | Strategic Objective | Programme | Project | Planned end date | Opex 2012/2013 | Capex 2012/2013 | Qtr Ending Sept '12 | Actual Achieved Sept '12 | Qtr Ending - Dec '12 | Actual End Dec '12 | Qtr Ending - Mar '13 | Qtr Ending - Jun '13 | Reason for deviation | Means of verification
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Lenyenye new cemetery tar road | 30/06/2013 |  | 2000000 | Not applicable this quarter | Not applicable this quarter | Monitor supply chain processes of advertising for a consultant | Waiting for the availability of the new cemetery site. | Monitor appointment of consultant and submission of designs | Appointment of contractor and monitor implementation. Report progress |  | Progress reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Mafarana to Sedan Tar (6km) | 30/06/2013 |  | 10500000 | Design and submit tender documentation to Supply Chain and monitor tender process. Report progress before 6th of every month | Scope of works report was submitted on 31/08/12. Environmental Consultant has been appointed. Engineer busy with designs | Design and submit tender documentation to Supply Chain and monitor tender process. Report progress before 6th of every month | Designs are complete and draft tender document have been submitted for approval. | Monitor implementation and report progress before 6th of every month | Monitor implementation and report progress before 6th of every month |  | Monthly reports to Council & COGHSTA.
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Khwekhwe Low level bridge | 30/06/2013 |  | 500000 | Monitor Supply Chain process | Tender for appointment of the consultant was advertised on the 20 September 2012 | Appointment of consultant to develop designs | The tender for the appointment of the consultant closed on the 12 October 2012 | Appointment of contractor, monitor implementation and report progress | Monitor implementation and report progress |  | Monthly reports SDBIP report
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Mawa Block 12 Low level bridge | 30/06/2013 |  | 500000 | Monitor Supply Chain process | Tender for appointment of the consultant was advertised on the 20 September 2012 | Appointment of consultant to develop designs | The tender for the appointment of the consultant closed on the 12 October 2012 | Appointment of contractor, monitor implementation and report progress | Monitor implementation and report progress |  | Project Certificates & progress reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Mokonyane low level bridge | 30/06/2013 |  | 500000 | Monitor Supply Chain process | Tender for appointment of the consultant was advertised on the 20 September 2012 | Appointment of consultant to develop designs | The tender for the appointment of the consultant closed on the 12 October 2012 | Appointment of contractor, monitor implementation and report progress | Monitor implementation and report progress |  | Project Certificates & progress reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Rikhotso low level bridge | 30/06/2013 |  | 500000 | Monitor Supply Chain process | Tender for appointment of the consultant was advertised on the 20 September 2012 | Appointment of consultant to develop designs | The tender for the appointment of the consultant closed on the 12 October 2012 | Appointment of contractor, monitor implementation and report progress | Monitor implementation and report progress |  | Project Certificates & progress reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Ramotshinyadi to Mokhwati Tar road (Phase 2)(3.5km) | 30/06/2013 |  | 12751569 | Monitor implementation and report progress before 6th of every month | Construction on schedule, physical progress is at 55% | Monitor implementation and report progress before 6th of every month | Construciton is in progress and the physical progress is at 65% | Monitor implementation and report progress before 6th of every month | Monitor implementation and report progress before 6th of every month |  | Project progress reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Rehabilitation of streets in Tzaneen - Claude Wheatly | 30/06/2013 |  | R8,000,000 (Roll over) | Monitor implementation and report progress | Construction on hold | Monitor implementation and report progress | New contractor appointed, sitehandover was on 14/01/13 | Monitor implementation and report progress | Monitor implementation and report progress |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Sasekani to Nkowankowa Tar road (Phase 2) | 30/06/2013 |  | 8473559 | Monitor implementation and report progress before 6th of every month | Construction on hold | Not applicable this quarter | New contractor appointed, sitehandover was on 15/01/13 | Not applicable this quarter | Not applicable this quarter |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Senakwe to Maropalala Tar (Phase 2) | 30/06/2013 |  | 31285000 | Appointment of contractor, monitor implementation and report progress before 6th of every month | Project is on adjudication stage waiting appointment of the contractor by SCM | Monitor implementation and report progress before 6th of every month | Contractor appointed, sitehandover was on 14/01/13. | Monitor implementation and report progress before 6th of every month | Monitor implementation and report progress before 6th of every month |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Speed humps | 30/06/2013 |  | 2200000 | Identification of positions | The identification of the speed hump positions was completed | Implementation of 33 speed humps and report progress | The identification of the speed humps was completed and the project will be implemented after the appointment of contractors for the construction of low level bridges ( Politsi, Motupa, Mopye and Thako to Sefolwe) | Implementation of 33 speed humps and report progress | Implementation of 33 speed humps and report progress |  | Project Certificates & progress reports
BSD | Improve access to sustainable and affordable services | Roads and Storm water Infrastructure Development | Thapane to Moruji Tar | 30/06/2013 |  | 11144700 | Appointment of contractor, monitor implementation and report progress before 6th of every month | Environmental Consultant appointed and the Engineer busy with designs. | Monitor implementation and report progress before 6th of every month | Consulting Engineer busy with the designs | Monitor implementation and report progress before 6th of every month | Monitor implementation and report progress before 6th of every month |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Water and Sewer Infrastructure | Interdepartmental and District Water & Sanitation projects | 30/06/2013 |  |  | Monitor Water and Sanitation projects implemented by COGHSTA and GTM and report progress to Council | Inspect Water and Sanitation projects implemented by COGHSTA and GTM and report progress to Council | Monitor Water and Sanitation projects implemented by COGHSTA and GTM and report progress to Council | Two projects funded by COHGSTA in Dan village and Tzaneen are being monitored by GTM | Monitor Water and Sanitation projects implemented by COGHSTA and GTM and report progress to Council | Monitor Water and Sanitation projects implemented by COGHSTA and GTM and report progress to Council |  | Monthly report Correspondence with COGHSTA
BSD | Integrated Developmental Planning | Infrastructure Planning | Roads masterplan | 30/06/2013 | 3000000 |  | Identify source of funding | The identificationof the source was not done | Advertise for the appointment of a service provider. Appoint service provider | Waiting for availability of budget | Monitor progress with the drafting of the Roads master plan | Monitor progress with the drafting of the Roads master plan | Waiting for the availability of the budget | Monthly reports from service provider
BSD | Optimise infrastructure investment and services | Fleet management | Fleet management | 30/06/2013 | 5502892 |  | Implement fleet mangement system and report progress | Busy with specification for advert for installation of tracing system | Review Fleet Management policy and monitor progress with implementation | Waiting for SCMU to advertise for appointment of service provider for installtion of tracking devices | Monitor the implementation of the fleet management system | Monitor the implementation of the fleet management system |  | Monthly reports
BSD | Optimise infrastructure investment and services | Infrastructure Planning | Water & Sewer master plan | 30/06/2013 | 4000000 |  | Identify source of funding | Mopani District Municipality to fund the water infrastructure Plan | Advertise for the appointment of a service provider. Appoint service provider | Mopani District Municipality to fund the Master Plan for Water and Sanitation. | Monitor progress with the drafting of the Water & Sewer Master Plans | Monitor progress with the drafting of the Water & Sewer Master Plans |  | Monthly reports from service provider
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Additional Office space | 30/06/2013 |  | 3000000 | Implement outcome of the feasabiility study | Evaluation stage of the bidder | Monitor implementatoin and report progress with the providin additional office space | Delayed by SCMU for appointment of service provider to do feasibillty studies | Monitor implementatoin and report progress with the providin additional office space | Monitor implementatoin and report progress with the providin additional office space |  | Office space reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Aerodrome Maintenance | 30/06/2013 | 50000 |  | Maintain the Aerodrome buildings on request | No request received yet | Maintain the Aerodrome buildings on request | No request received yet | Maintain the Aerodrome buildings on request | Maintain the Aerodrome buildings on request |  | Monthly Reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Civic Centre and Community Services painting | 30/06/2013 | 400000 |  | Compile specifications and schedule of quantities for painting the internal walls Civic Centre and obtain quotations by 30 September | Specifications completed to be adverts during this month | Finalise quotations and appoint contractor for painting the civic centre. Implement painting programme as per the implementation plan to be completed by 15 December | Waiting for SCMU to advertise for appointment of service provider | Not applicable this quarter | Not applicable this quarter |  | Project progress reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Emergency Maintenance | 30/06/2013 | 600000 |  | Conduct emergency maintenance as and when the need requires on all municipal buildings and assets (Including Pioneers Old aged homes & the Aerodrome) | Ongoing maintenance services and request are attended to as and when requested | Conduct emergency maintenance as and when the need requires on all municipal buildings and assets (Including Pioneers Old aged homes & the Aerodrome) | Ongoing maintenance services and request are attended to as and when requested | Conduct emergency maintenance as and when the need requires on all municipal buildings and assets (Including Pioneers Old aged homes & the Aerodrome) | Conduct emergency maintenance as and when the need requires on all municipal buildings and assets (Including Pioneers Old aged homes & the Aerodrome) |  | Monthly reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Municipal house (Letsitele) renovations | 30/06/2013 | 150000 |  | Not applicable this quarter | Not applicable this quarter | Compile specifications and schedule of quantities for repairs and maintenance of Municipal house (Letsitele) and advertise for quotations. | Delayed by SCMU for appointment of service provider | Not applicable this quarter | Not applicable this quarter | Delayed by SCMU for appointment of service provider | Project progress reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Paving Nkowankowa testing ground | 30/06/2013 | 200000 |  | Not applicable this quarter | Not applicable this quarter | Compile specifications and schedule of quantities for paving Nkowankowa testing ground and advertise for quotations. | Supply chain to advertise for appointment of sevice provider | Not applicable this quarter | Not applicable this quarter |  | Project progress reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Tiling of Tzaneen Library | 30/06/2013 | 200000 |  | Not applicable this quarter | Not applicable this quarter | Compile specifications and schedule of quantities for tiling of Tzaneen Library and advertise for quotations. Ensure that service provider is appointed and project completed by end of November | Service provider has been appointed and busy with the Tiling work of the Library | Not applicable this quarter | Not applicable this quarter | The service provider was apointed in december last year and due to SCMU process that delaysed the appointing service provider | Project progress reports
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Replaceing Aircon and furniture in Engineering Department | 30/06/2013 |  | 500000 | Draft speficifications and advertise for the provision of aircons and furniture | The specification s and advertisement was done | Appoint service provider and monitor implementation | Service provider has been appointed and busy with the installation of Aircons | Appoint service provider and monitor implementation | Appoint service provider and monitor implementation |  | Invoice & Proof of payment
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Securing of Rates Hall and Morphy Access Control system | 30/06/2013 |  | R1500000 (roll over) | Planning and design of Rates hall changes | Installation of safety doors already started> Only waiting for advert for installation of lift in the civic centre | Ensure that Rates Hall is secured and Morphy Access Control System is installed. Liaise with Safety & Security | Installation of safety doors in rates hall completed only waiting for advertisement of installation of Lift in the civic centre | Hand over the Morphy Access system to the CSD (Safety & Security) for managing the system | Not applicable this quarter |  | Project progress reports
BSD | Optimise infrastructure investment and services | Maintenance of municipal assets | Aerodrome Maintenance | 30/06/2013 | 150000 |  | Cut grass at the airport | There was no need for grass cutting | Cut grass at the airport | Cutting of grass and replacing of fence was done at the airfield | Cut grass at the airport | Cut grass at the airport |  | Aerodrome maintenance programme & reports
BSD | Optimise infrastructure investment and services | Municipal assets | Capital Equipment | 30/06/2014 |  | 150000 | Source Quotations for the purchasing of Fuel tankers, brush cutters and pruners | Waiting for availiability of budget | Purchasing of Fuel tankers, brush cutters and pruners | Not yet implemented | Not applicable this quarter | Not applicable this quarter | Waiting for availiability of budget (Capital loan) | Invoice & Proof of payment
BSD | Optimise infrastructure investment and services | Municipal assets | Tzaneen Airfield Fencing | 30/06/2013 |  | 650000 | Monitor Supply Chain process to appoint contractor | This was not done | Appointment of contractor. Monitor implementation and report progress | Not yet implemented | Monitor implementation and report progress | Monitor implementation and report progress | Waiting for availiability of budget (Capital loan) | Progress Reports
BSD | Optimise infrastructure investment and services | Roads & Storm water maintenance and upgrade | Funeral roads in all clusters | 30/06/2013 | 4257000 |  | 100% compliance to requisitions submitted | 472km graded | 100% compliance to requisitions submitted | 584 km graded | 100% compliance to requisitions submitted | 100% compliance to requisitions submitted |  | Funeral road register
BSD | Optimise infrastructure investment and services | Roads & Storm water maintenance and upgrade | Regravelling of internal streets all clusters | 30/06/2013 | 11892312 |  | Maintain internal streets in all clusters as and when required, report activities on a monthly basis | 5.4km regravelled at Mafarana and Runnymade | Maintain internal streets in all clusters as and when required, report activities on a monthly basis | No regravelling was done. | Maintain internal streets in all clusters as and when required, report activities on a monthly basis | Maintain internal streets in all clusters as and when required, report activities on a monthly basis |  | Regravelling Project progress reports
BSD | Optimise infrastructure investment and services | Roads & Storm water maintenance and upgrade | Side walk and pavements | 30/06/2013 | 525000 |  | Maintain sidewalks and pavements as and when required, report activities on a monthly basis | 861m2 sidewalk paving in Tzaneen town | Maintain sidewalks and pavements as and when required, report activities on a monthly basis | 270 m2 side walk paved at Lenyenye | Maintain sidewalks and pavements as and when required, report activities on a monthly basis | Maintain sidewalks and pavements as and when required, report activities on a monthly basis |  | Sidewalk & pavement Project progress reports
BSD | Optimise infrastructure investment and services | Roads & Storm water maintenance and upgrade | Storm water management | 30/06/2013 | 4930432 |  | Maintain stormwater drainage systems as and when required, report activities on a montly basis | 742 m2 stone pitching constructed at Bokutha, Morapalala and Mafarana. Cleaning of catch pits and sub-soil drainage installation at Hermanus street. . | Maintain stormwater drainage systems as and when required, report activities on a montly basis | 100m stone pitching constructed at Moruji. | Maintain stormwater drainage systems as and when required, report activities on a montly basis | Maintain stormwater drainage systems as and when required, report activities on a montly basis |  | Stormwater maintenance Project progress reports
BSD | Optimise infrastructure investment and services | Roads & Storm water maintenance and upgrade | Tar patching | 30/06/2013 | 10973000 |  | Maintain tar roads and streets as and when required and report activities on a monthly basis | 4987m2 tar patching in Tzaneen town, Lenyenye and Nkowankowa | Maintain tar roads and streets as and when required and report activities on a monthly basis | 2452m2 tar patching was done in Tzaneen town, Lenyenye and Nkowankowa | Maintain tar roads and streets as and when required and report activities on a monthly basis | Maintain tar roads and streets as and when required and report activities on a monthly basis |  | Monthly reports
BSD | Optimise infrastructure investment and services | Roads & Storm water maintenance and upgrade | Tar patching of sand seal roads | 30/06/2013 | 795697 |  | 100% compliance to general maintenance schedule and eradication of backlogs | 300m2 tar patching at Mokgapeng. | 100% compliance to general maintenance schedule and eradication of backlogs | 500m2 tar patching was done at Mokgapeng | 100% compliance to general maintenance schedule and eradication of backlogs | 100% compliance to general maintenance schedule and eradication of backlogs |  | Schedule -Project progress reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | BlueDrop Water Certification (BDC) | 30/06/2013 |  |  | Maintain blue drop status by monitoring compliance to SANS 241:2011 at Tzaneen & Letsitele water system. Develop water safety plans and policies for Nkowankowa and Lenyenye to secure BDC | Maintain BDC and assist Mopani with Lenyenye and Nkowankowa | Maintain blue drop status by monitoring compliance to SANS 241:2011 at Tzaneen & Letsitele water system. Develop water safety plans and policies for Nkowankowa and Lenyenye to secure BDC | Update of Water and Wastewater Quality data for Water Safety Plan and Risk Abatement Plan are in progress | Maintain blue drop status by monitoring compliance to SANS 241:2011 at Tzaneen & Letsitele water system. Develop water safety plans and policies for Nkowankowa and Lenyenye to secure BDC | Maintain blue drop status by monitoring compliance to SANS 241:2011 at Tzaneen & Letsitele water system. Develop water safety plans and policies for Nkowankowa and Lenyenye to secure BDC |  | Water Quality reports Policies
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | GreenDrop Certification (GDC) | 30/06/2013 |  |  | Develop plans for waste water management to secure GDC for Tzaneen & Nkowankowa and Lenyenye. Monitor activies to ensure adherenece to SANS 241:2011 | Maintain GDC and assist MDM with Lenyenye and Nkowankowa | Develop plans for waste water management to secure GDC for Tzaneen & Nkowankowa and Lenyenye. Monitor activies to ensure adherenece to SANS 241:2011 | Risk Abatement Plan for 2012 which covers all pump stations and their improvement plan are being evaluated. | Develop plans for waste water management to secure GDC for Tzaneen & Nkowankowa and Lenyenye. Monitor activies to ensure adherenece to SANS 241:2011 | Develop plans for waste water management to secure GDC for Tzaneen & Nkowankowa and Lenyenye. Monitor activies to ensure adherenece to SANS 241:2011 |  | *Waste Water Management Plan *Waste Water Quality reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | Preperation of Laboratory for ISO 17025:2005 accreditation | 30/06/2013 | 400000 |  | Development of laboratory policies | Waiting for BEC: the bid closed on the 28 september 2012 | Training of laboratory personnel | The BID had been readverised due to poor response from the bidders. | Monitor Implementation of policy and laboratory operations | Monitor Implementation of policy and laboratory operations |  | Laboratory Policy Progress reports Laboratory activity reports
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | Operations and maintenance sewer (distribution networks) | 30/06/2013 | 200000 |  | 100% compliance to maintenance schedules. 25% expenditure | Complyying to Maintenance schedule : 25% with R 46,620. spent with budget of R 500,000. | 100% compliance to maintenance schedules. 25% expenditure | Pump stations and disribution network are being done accordingly. At 50% level. | 100% compliance to maintenance schedules. 25% expenditure | 100% compliance to maintenance schedules. 25% expenditure |  | Maintenance Schedule Monthly report
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | Operations and maintenance water distribution network | 30/06/2013 | 1735000 |  | 100% compliance to maintenance schedules. 25% expenditure | Complying to maintence schedule 25% with R 285,675. spent and the budget being R 2, 750,000. | 100% compliance to maintenance schedules. 50% expenditure | Progress is at 50% while the expenditure is at R 953,874.00 with R 2,750,000.00 budget. | 100% compliance to maintenance schedules. 75% expenditure | 100% compliance to maintenance schedules. 100% expenditure |  | Maintenance Schedule Monthly report
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | Operations and maintenance water purification | 30/06/2013 | 675000 |  | 100% compliance to maintenance schedules. 25% expenditure | Compliance to Water Purification : schedule at 25% with R 205,598. spent at the budget of R 1,000,000. | 100% compliance to maintenance schedules. 50% expenditure | The work progress is at 50% while the water quality is complying at 100%.expenditure is R 346,865.00 | 100% compliance to maintenance schedules. 75% expenditure | 100% compliance to maintenance schedules. 100% expenditure |  | Maintenance Schedule Monthly report
BSD | Optimise infrastructure investment and services | Water and Sewer maintenance and upgrade | Water Works (Upgrade of telemetric system) | 30/06/2013 | 450000 |  | Not applicable this quarter | Not applicable this quarter | Upgrading of telemetric system completed | Waiting for advertisement. Specifications submited to SCM | Not applicable this quarter | Not applicable this quarter |  | Project progress reports
LED | Create a stable and enabling economic environment by attracting suitable investors | Building control | Building plan approvals and inspections | 30/06/2013 |  |  | Monitor building control services ensure that building plans are approved and inspections done and clients given feedback within the required timeframes. | Ongoing activities and plans are approved as and when required. | Monitor building control services ensure that building plans are approved and inspections done and clients given feedback within the required timeframes. | Ongoing activities and plans are approved as and when required. | Monitor building control services ensure that building plans are approved and inspections done and clients given feedback within the required timeframes. | Monitor building control services ensure that building plans are approved and inspections done and clients given feedback within the required timeframes. |  | Building control register of activities
LED | Create community beneficiation and empowerment opportunities | Extended Public Works | Facilitating EPWP | 30/06/2013 | 935000 |  | Monitor progress with the implementation of EPWP and report progress to Council on a monthly basis. Submit job creation statistics to PED | Only 79 job opportunities were created and the reports are forwarded monthly to provincial deparment | Monitor progress with the implementation of EPWP and report progress to Council on a monthly basis. Submit job creation statistics to PED | Only 79 job opportunities were created and the reports are forwarded monthly to provincial deparment | Monitor progress with the implementation of EPWP and report progress to Council on a monthly basis. Submit job creation statistics to PED | Monitor progress with the implementation of EPWP and report progress to Council on a monthly basis. Submit job creation statistics to PED |  | Monthly EPWP reports Incentive agreement
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance monitoring & evaluation | 30/06/2013 |  |  | Participate in the Annual Performance Assessment for 2011/12. Ensure that scoresheets are completed in time & POEs are complete | No assesments have been done | Conduct an informal assessment of 1st Quarter Performance of relevant employees in the Department and send report to the MM by 21 October '12 | No assesments have been done | Participate in the mid-year employee performance evaluations for 2012/13. Ensure that scoresheets are completed in time & POEs are complete | Conduct an informal assessment of the 3rd Quarter Performance of relevant employees in the Department and submit report to the MM by 20 April '13 | Director newly appointed | 1st & 3rd Qtr Informal Departmental Individual Performance Reports Correspondence
SR/LED | Integrated Developmental Planning | Integrated Development Planning | IDP implementation monitoring | 30/06/2013 |  |  | Arrange quarterly Service Delivery Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | No thrust meeting arranged during the 1st quarter | Arrange quarterly Service Delivery Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | No thrust meeting arranged during the 2nd quarter | Arrange quarterly Service Delivery Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | Arrange quarterly Service Delivery Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM |  | Stakeholder list Minutes proof of submission to MM

## CSD KPIs
Key Performance Indicators (KPIs) - Community Services Department
KPA/ Theme | Strategic Objective | Programme | Departmental KPI | Baseline (end June 2012) | Target Sept '12 | Actual Sept '12 | Target Dec '12 | Actual End Dec '12 | Target Mar '13 | Target Jun '13 | Reason for deviation | Means of verification
BSD | Effective and Efficient administration | Safety and Security | % reduction in R-value of Council property lost through theft and damages by year end | new indicator | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 50% |  | Theft & damages register
BSD | Improve access to sustainable and affordable services | Licensing Services | R-value generated for vehicle registration (Agency agreement) | 1231232 | Reporting only - no target | 318912 | Reporting only - no target | 601128 | Reporting only - no target | Reporting only - no target |  | Records and monthly reports
BSD | Improve access to sustainable and affordable services | Licensing Services | R-value generated by the issuing of learners and drivers licenses | 6380115 | Reporting only - no target | 114932 | Reporting only - no target | 169136 | Reporting only - no target | Reporting only - no target |  | Records and monthly reports
BSD | Improve access to sustainable and affordable services | Traffic Services | % decrease in road accidents | new indicator | Not applicable this quarter | Not applicable this quarter | 5% | 5% | Not applicable this quarter | 10% |  | Road accident register
BSD | Improve access to sustainable and affordable services | Traffic Services | % decrease in traffic offenders | new indicator | Not applicable this quarter | Not applicable this quarter | 5% | 10% | Not applicable this quarter | 10% |  | Register of fines
BSD | Improve access to sustainable and affordable services | Traffic Services | R-value revenue collected through law enforcement | 3062070 | No target - Reporting only | 515975 | No target - Reporting only | 3093800 | No target - Reporting only | No target - Reporting only |  | Revenue reports
BSD | Improve access to sustainable and affordable services | Traffic Services | Rand value received for fines issued / R value of fines issued (%) | 80% | 70% | 60% | 70% | 75% | 70% | 70% |  | Revenue reports
BSD | Improve access to sustainable and affordable services | Traffic Services | # traffic fines issued per quarter | 8738 | No target - Reporting only | 12769 | No target - Reporting only | 10230 | No target - Reporting only | No target - Reporting only |  | System printout
BSD | Improve access to sustainable and affordable services | Waste Management | # of service delivery interruptions (solid waste removal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Waste Management | # of households affected through interruptions (solid waste removal) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Waste Management | Number of households with access to refuse removal at least once per week (O9) | 10775 | No target - Reporting only | 10775 | No target - Reporting only | 10775 | No target - Reporting only | No target - Reporting only |  | Consolidated statistical report
BSD | Improve access to sustainable and affordable services | Waste Management | Nr of households with access to basic (or higher) refuse removal (Urban) | 10775 | 9892 | 10775 | 9892 | 10775 | 9892 | 9892 |  | Monthly reports
BSD | Improve access to sustainable and affordable services | Waste Management | Nr of households with access to basic (or higher) refuse removal (Rural) | 6979 | 6979 | 6979 | 6979 | 6979 | 6979 | 6979 |  | Monthly reports
BSD | Optimise infrastructure investment and services | Cemetery maintenance and upgrade | # of Cemeteries with amenities | 89 | Not applicable this quarter | Not applicable this quarter | 91 | 89 | Not applicable this quarter | 91 | Lenyenye cemetery not yet completed | Cemetery register
BSD | Promote environmentally sound practices and social development | Library Services | # people using the GTM libraries | 95957 | 21125 | 25022 | 42250 | 47935 | 63375 | 84500 |  | Statistics and reports
BSD | Promote environmentally sound practices and social development | Parks and Open space Management | % of households with access to parks | 12% | Not applicable this quarter | Not applicable this quarter | 12% | 12% | Not applicable this quarter | 12% |  | Stats SA
BSD | Promote environmentally sound practices and social development | Parks and Open space Management | # of dedicated parks maintained (developed) | 7 | 7 | 7 | 7 | 7 | 7 | 7 |  | Parks maintenance plan
BSD | Promote environmentally sound practices and social development | Sport and Recreation | # of households with access to formal Sport and recreation facilities | 18963 | Not applicable this quarter | Not applicable this quarter | 18963 | 18963 | Not applicable this quarter | 18963 |  | Stats SA (Nkowankowa, Tzaneen, Lenyenye, Julesburg, Burgersdorp and Rhelela)
BSD | Promote environmentally sound practices and social development | Waste Management | % Service delivery backlog for solid waste | 87.5% | 87.5% | 88% | 87.5% | 88% | 87.5% | 87.5% |  | Monthly reports
BSD | Financial Viability | Free Basic Services | R-Value of Free Basic waste removal to affected households | 3500000 | Reporting only - no target | Reporting only - no target | Reporting only - no target | Reporting only - no target | Reporting only - no target | 3800000 |  | Revenue reports
GG | Effective and Efficient administration | Council Support | % of Departmental Council resolutions implemented | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Departmental Resolution register
GG | Effective and Efficient administration | Management and Administration | # of departmental meetings | 4 | 1 | 5 | 2 | 0 | 3 | 4 | Director newly appointed | Minutes and Attendance registers of Departmental meetings
GG | Effective and Efficient administration | Performance monitoring and reporting | # of Community Services Departmental monthly reports submitted on time | 12 | 3 | 3 | 6 | 6 | 9 | 12 |  | Monthly, quarterly, half yearly and annual reports
GG | Effective and Efficient administration | Safety and Security | R-value of council property lost through theft and damages | 9000 | Reporting only - no target | 21000 | Reporting only - no target | 5000 | Reporting only - no target | Reporting only - no target |  | Theft & damages register
GG | Effective and Efficient administration | Safety and Security | # of internal theft cases reported | 5 | 0 | 2 | 0 | 2 | 0 | 0 |  | Theft register
GG | Effective and Efficient administration | Safety and Security | # of personnel/visitor cards issued per annum | 2800 | Reporting only - no target | 1900 | Reporting only - no target | 3200 | Reporting only - no target | Reporting only - no target |  | Security Register
GG | Effective and Efficient administration | Safety and Security | # complaints received with regard to the non-availability of security | 20 | 0 | 0 | 0 | 3 | 0 | 0 |  | Complaints register
GG | Effective and Efficient administration | Sound Governance | % of Internal Audit queries responded to within 10 days | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Register of Internal Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Budget management | % of departmental budget spent | 91% | 25% | 19.86% | 50% | 49.08% | 75% | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Financial reporting | % of AG queries responded to within 2 working days | 100% | Not applicable this quarter | Not applicable this quarter | 100% | 100% | Not applicable this quarter | Not applicable this quarter |  | Register of Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Municipal Assets | # of departmental asset verifications done | 1 | 0 | 0 | 1 | 1 | 1 | 2 |  | Asset verification checklist
LED | Integrated developmental planning | Integrated Spatial Development | % of departmental capital spent in the priority areas identified in Spatial Development Framework | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Revised SDF vs Capital Expenditure
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | % of CSD Manager's with signed performance plans by 31 July | 100% | 100% | 0% | 100% | 0% | Not applicable this quarter | Not applicable this quarter | Director newly appointed | Signed Performance Plans
Note on C22: Frieda Human: Same programme, use old programmes as projects - Check with Mr. Mienie

## CSD Projects
Quarterly targets per Project - Community Services Department
KPA/ Theme | Strategic Objective | Programme | Project | Planned end date | Opex 2012/2013 | Capex 2012/2013 | Qtr Ending Sept '12 | Actual Achieved Sept '12 | Qtr Ending - Dec '12 | Actual End Dec '12 | Qtr Ending - Mar '13 | Qtr Ending - Jun '13 | Reason for deviation | Means of verification
BSD | Improve access to sustainable and affordable services | Library Infrastructure | Construct and establish new libraries (Shiluvane Library) | 30/06/2013 | 1000000 | 135000 | Attend Shiluvane Library site meetings. Appoint and train GTM staff for library or train staff appointed by DSAC | No Shiluvane site meetings conducted this quarter. Shiluvane staff appointments pending. Detailed lists of books needed at the Shiluvane Library compiled and submitted to the DSAC. | Attend Shiluvane Library site meetings. Train staff upon appointment. Folow up on furniture, equipment, cabling, IT networking, security systems etc. needed for the Shiluvane Library and advise the DSAC on placement in the Shiluvane Library. | No Shiluvane site meetings were conducted this quarter. Short listing of 2nd Shiluvane Librarian pending DSAC appointments pending. Followed up on progress Shiluvane Library with DASC and drafted a report for the Sports, Arts and Culture Cluster Committee. | Manage the Shiluvane Library | Manage the Shiluvane Library |  | Minutes of meetings, reports and correspondence
BSD | Improve access to sustainable and affordable services | Licensing Services | Learners and Drivers and Professional Drivers Permits | 30/06/2013 |  |  | Ensure that applications for learners, drivers and Professional Drivers permits are processed | Learners 1646 Drivers Licence 4450 Prdp's 830 | Ensure that applications for learners, drivers and Professional Drivers permits are processed | Learners R3601 Driver's Licence 8513 Prdp's 1622 | Ensure that applications for learners, drivers and Professional Drivers permits are processed | Ensure that applications for learners, drivers and Professional Drivers permits are processed |  | Records and monthly reports
BSD | Improve access to sustainable and affordable services | Licensing Services | Vehicle registration and licensing | 30/06/2013 |  |  | Ensure that all vehicle registration and licensing applications are processed within a reasonable time | Vehicle registration 3277 and vehicle licenses 13305 | Ensure that all vehicle registration and licensing applications are processed within a reasonable time | Vehicle registration 6248 and licenses 28715 | Ensure that all vehicle registration and licensing applications are processed within a reasonable time | Ensure that all vehicle registration and licensing applications are processed within a reasonable time |  | Records and monthly reports
LED | Integrated Developmental Planning | Township revitalisation | Community Parks(PP5) | 30/06/2013 |  |  | Provide inputs into the development of community parks and attend NDPG task team meeting | Attended NDGP meetings for indoor sport facility development. I was a member of panel during interviews for coaches appointment | Provide inputs into the development of community parks and attend NDPG task team meeting | 2 Baloyi graves were exhumed at Erf 345C and reburried at Mariveni. 22 coaches are trained and giving support to 4 High schools and Primary schools | Provide inputs into the development of community parks and attend NDPG task team meeting | Provide inputs into the development of community parks and attend NDPG task team meeting |  | Minutes and attendance register Correspondence
BSD | Improve access to sustainable and affordable services | Public Transport | Transport Master plan | 30/06/2013 |  |  | Liasise with the MDM to develop a Transport Master Plan for GTM | Liasing on Master Plan not ready yet. | Liasise with the MDM to develop a Transport Master Plan for GTM | Development in process | Liasise with the MDM to develop a Transport Master Plan for GTM | Liasise with the MDM to develop a Transport Master Plan for GTM |  | Correspondence
BSD | Improve access to sustainable and affordable services | Traffic Services | Burgersdorp cattle pound | 30/06/2013 | 15000 |  | Manage and co-ordinate impounding of stray animals. Report to Council | No impounded animals for the period | Manage and co-ordinate impounding of stray animals. Report to Council | No Impoundment animals, No budget | Manage and co-ordinate impounding of stray animals. Report to Council | Manage and co-ordinate impounding of stray animals. Report to Council |  | Monthly Report
BSD | Improve access to sustainable and affordable services | Traffic Services | GTM Law Enforcement in rural areas and scrappings | 30/06/2013 | 100000 |  | Conducting rural traffic program as per schedule. Manage and follow up on vehicle scrappings | Rural operations planned and executed, scrapping on-going. | Conducting rural traffic program as per schedule. Manage and follow up on vehicle scrappings | Pragramme in progress | Conducting rural traffic program as per schedule. Manage and follow up on vehicle scrappings | Conducting rural traffic program as per schedule. Manage and follow up on vehicle scrappings |  | Monthly report
BSD | Improve access to sustainable and affordable services | Traffic Services | Kukula Ndlela drunken-driving blitz project | 30/06/2013 | 55000 |  | Additional roadblocks - 2 (Drunken driving Blitz) | Drager challenges drunken driving arrests with help of hospitals | Additional roadblocks - 2 (Drunken driving Blitz) | On hold, machine stolen. Rely on blood tests. | Additional roadblocks - 2 (Drunken driving Blitz) | Additional roadblocks - 2 (Drunken driving Blitz) |  | Monthly Reports
BSD | Improve access to sustainable and affordable services | Traffic Services | Minitzani-Bonatsela Traffic centres scholar Education | 30/06/2013 | 40000 |  | Staging of Minitzani safety week during June/July holidays | Challenges of unavailability of funds cater only for visitors from schools. | Conduct road safety education campaigns at rural schools. Report schools attendance in monthly reports | On hold, No budget | Conduct road safety education campaigns at rural schools. Report schools attendance in monthly reports | Conduct road safety education campaigns at rural schools. Report schools attendance in monthly reports | No budget | Monthly Reports
BSD | Improve access to sustainable and affordable services | Traffic Services | Scholar patrols and cluster control points | 30/06/2013 | 40000 |  | Ensure that road traffice is controlled at schools on busy routes to ensure scholar safety. (Laerskool Tzaneen, Unicorn, Florapark & Nkowankowa & Rita) | Effective control at specific points. | Ensure that road traffice is controlled at schools on busy routes to ensure scholar safety. (Laerskool Tzaneen, Unicorn, Florapark & Nkowankowa & Rita) | Effective control at specific points. | Ensure that road traffice is controlled at schools on busy routes to ensure scholar safety. (Laerskool Tzaneen, Unicorn, Florapark & Nkowankowa & Rita) | Ensure that road traffice is controlled at schools on busy routes to ensure scholar safety. (Laerskool Tzaneen, Unicorn, Florapark & Nkowankowa & Rita) |  | Monthly Reports
BSD | Improve access to sustainable and affordable services | Waste management | Bulk Bin Waste Collections in Urban areas | 30/06/2013 | 5300000 |  | Monitor the collection of Bulk Bin waste in Tzaneen, Lenyene, Letsitele, Haenersburg, Nkowankowa ensure compliance to SLA. Report volumes removed | 100% compliance to Bulk Bin Collections in Tzaneen, Lenyenye, Nkowankowa, Haenertsburg and Letsitele and 25% expenditure | Monitor the collection of Bulk Bin waste in Tzaneen, Lenyene, Letsitele, Haenersburg, Nkowankowa ensure compliance to SLA. Report volumes removed | 100% compliance to Bulk Bin Collections in Tzaneen, Lenyenye, Nkowankowa, Haenertsburg and Letsitele and 50% expenditure. | Monitor the collection of Bulk Bin waste in Tzaneen, Lenyene, Letsitele, Haenersburg, Nkowankowa ensure compliance to SLA. Report volumes removed | Monitor the collection of Bulk Bin waste in Tzaneen, Lenyene, Letsitele, Haenersburg, Nkowankowa ensure compliance to SLA. Report volumes removed | The tender of Bulk-removals already expired and was NOT re-advertised due to a decision of by the A.O. | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Composting of incoming clean greens @ Tzaneen Landfill | 30/06/2013 | 2000000 |  | Monitor the composting of clean greens at the Landfill and report volumes | No composting yet due to burning down of all "dry clean-greens"Seek new Operator for composting of clean greens at the Landfill and will report volumes | Monitor the composting of clean greens at the Landfill and report volumes | No composting being done yet. Awaiting outcome of BAC appointment of a new Service-Provider for Landfill-operations, where after volumes can be reported | Monitor the composting of clean greens at the Landfill and report volumes | Monitor the composting of clean greens at the Landfill and report volumes | Awaiting outcome of BAC appointment of a new Service-Provider for Landfill-operations, where after volumes can be reported | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Contracted Kerbside collections | 30/06/2013 |  |  | Monitor Contracted Kerbside collections in Nkowankowa & Lenyenye and ensure that services are provided as per the SLA | 100% compliance to Contracted Kerbside collections in Nkowankowa and Lenyenye and 25% expenditure. The tender of Nkowankowa already expired and was re-advertised. | Monitor Contracted Kerbside collections in Nkowankowa & Lenyenye and ensure that services are provided as per the SLA | 100% compliance to Contracted Kerbside collections in Nkowankowa and Lenyenye and 50% expenditure. The tender of The tender of Lenyenye also expired and MUST be re-advertised in early 2013 | Monitor Contracted Kerbside collections in Nkowankowa & Lenyenye and ensure that services are provided as per the SLA | Monitor Contracted Kerbside collections in Nkowankowa & Lenyenye and ensure that services are provided as per the SLA | The tender of Nkowankowa already expired and was NOT re-advertised due to a decision of by the A.O. | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Contracted Litterpicking | 30/06/2013 |  |  | Monitor Litterpicking in the outlying areas and ensure adherence to the route sheets for R/South & R/North | 100% Compliance to Litterpicking schedules in Tzaneen, Lenyenye, Haenertsburg and Nkowankowa and 25% expenditure | Monitor Litterpicking in the outlying areas and ensure adherence to the route sheets for R/South & R/North | 100% Compliance to Litterpicking schedules in Tzaneen, Lenyenye, Haenertsburg and Nkowankowa and 50% expenditure. The 2 x Tenders of Litterpicking already expired and MUST be re-advertised early 2013 | Monitor Litterpicking in the outlying areas and ensure adherence to the route sheets for R/South & R/North | Monitor Litterpicking in the outlying areas and ensure adherence to the route sheets for R/South & R/North |  | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Health Care Waste Collections | 30/06/2013 |  |  | Monitor the collection of Health Care Waste. Report actual removals | 100% compliance to HCW collections schedules and 25% expenditure | Monitor the collection of Health Care Waste. Report actual removals | 100% compliance to HCRW collections schedules and 50% expenditure. Awaiting outcome of BAC recommendation for appointment of a new HCRW Service-Provider | Monitor the collection of Health Care Waste. Report actual removals | Monitor the collection of Health Care Waste. Report actual removals |  | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Landfill site operations | 30/06/2013 |  |  | Monitor Landfill site operations and ensure compliance license conditions | 98% compliance to Lndfill permit conditions and 25% expenditure | Monitor Landfill site operations and ensure compliance license conditions | 98.24% compliance to Landfill permit + legal conditions and 50% expenditure. Awaiting outcome of BAC recommendation for appointment of a new Landfill Service-Provider | Monitor Landfill site operations and ensure compliance license conditions | Monitor Landfill site operations and ensure compliance license conditions |  | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Municipal Kerbside collections | 30/06/2013 |  |  | Monitor Municipal Kerbside collections in Tzaneen, Haenertsburg and Letsitele and ensure that route service schedules are adhered to. Report actual removal volumes | 100% Compliance to Municipal Kerbside collections in Tzaneen, Haenertsburg and Letsitele and 25% expenditure | Monitor Municipal Kerbside collections in Tzaneen, Haenertsburg and Letsitele and ensure that route service schedules are adhered to. Report actual removal volumes | 86% effective compliance to Municipal Kerbside collections in Tzaneen, Haenertsburg and Letsitele and 50% expenditure. | Monitor Municipal Kerbside collections in Tzaneen, Haenertsburg and Letsitele and ensure that route service schedules are adhered to. Report actual removal volumes | Monitor Municipal Kerbside collections in Tzaneen, Haenertsburg and Letsitele and ensure that route service schedules are adhered to. Report actual removal volumes | 4 Vacancies not filled | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Municipal Litterpicking | 30/06/2013 |  |  | Monitor Litterpicking in Tzaneen, Letsitele, Haenertsburg & Nkowankowa and ensure adherance to route- sheets. Report on number of routes serviced | 100% compliance to Litterpicking of Waste Removals calender in Tzaneen, Letsitele and Nkowankowa and 25% expenditure | Monitor Litterpicking in Tzaneen, Letsitele, Haenertsburg & Nkowankowa and ensure adherance to route- sheets. Report on number of routes serviced | 90% effective compliance to Litterpicking schedules in Tzaneen, Letsitele and Nkowankowa and 25% expenditure. | Monitor Litterpicking in Tzaneen, Letsitele, Haenertsburg & Nkowankowa and ensure adherance to route- sheets. Report on number of routes serviced | Monitor Litterpicking in Tzaneen, Letsitele, Haenertsburg & Nkowankowa and ensure adherance to route- sheets. Report on number of routes serviced | 2 Vacancies not filled | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Pollution awareness calender | 30/06/2013 |  |  | Planning for Waste removal calender | 25% Compliance to distribution of Waste Removal calenders in Tzaneen, Letsitele and Nkowankowa and no budget for expenditure. | Planning for Waste removal calender | 50% Compliance to planning of the 2013-2014 Waste-removal calendars in Tzaneen, Letsitele, Lenyenye, Haenertsburg and Nkowankowa and no budget for expenditure | Correspondence with ADDS4U | Distribution of Waste removal calender |  | Correspondence Waste Removal Calender
BSD | Improve access to sustainable and affordable services | Waste management | Public Toilets operations | 30/06/2013 |  |  | Monitor the implementation of the cleansing schedule for public toilets in Tzaneen(6), Nkowankowa(1), Letsitele(1), Lenyenye (1) and Haenertsburg (1) | 100 daily compliance to public toilet operations and schedules and 25% expenditure | Monitor the implementation of the cleansing schedule for public toilets in Tzaneen(6), Nkowankowa(1), Letsitele(1), Lenyenye (1) and Haenertsburg (1) | 92% effective daily compliance to public toilet operations and schedules and 50% expenditure. | Monitor the implementation of the cleansing schedule for public toilets in Tzaneen(6), Nkowankowa(1), Letsitele(1), Lenyenye (1) and Haenertsburg (1) | Monitor the implementation of the cleansing schedule for public toilets in Tzaneen(6), Nkowankowa(1), Letsitele(1), Lenyenye (1) and Haenertsburg (1) | 3 Vacancies not filled | Consolidated monthly statistics
BSD | Improve access to sustainable and affordable services | Waste management | Recycling at source | 30/06/2013 |  |  | Manage the SLA of service provider | SLA was developed but not signed yet. | Manage the SLA of service provider | Sec 25 Service Level Conditions was handed to the Sec. 25 "Transporter of Waste" for signing + acceptance | Manage the SLA of service provider | Manage the SLA of service provider |  | SLA Recycling statistics
BSD | Improve access to sustainable and affordable services | Waste management | Regional Landfill site | 30/06/2013 |  |  | Liaise with Mopani District Municipality to facilitate the establishment of a regional landfill site. | Continous liason with MDM to facilitate the establishment of a regional landfill site via E-mail | Liaise with Mopani District Municipality to facilitate the establishment of a regional landfill site. | Continuous liaison with MDM to facilitate the establishment of a regional landfill site via e-mail. Recent Land-Survey indicates still a minimum of 10 x years lifespan for the Landfill existence | Liaise with Mopani District Municipality to facilitate the establishment of a regional landfill site. | Liaise with Mopani District Municipality to facilitate the establishment of a regional landfill site. | No response from MDM | Correspondence with MDM Minutes of Meetings
BSD | Improve access to sustainable and affordable services | Waste management | Replacement of bins | 30/06/2013 |  |  | Replace depleted bins as and when required | Did not replace depleted bins as and when required | Replace depleted bins as and when required | Did not replace depleted bins as and when required due to slow S.C.M. Process. Appointments of Service-Providers not finalised | Replace depleted bins as and when required | Replace depleted bins as and when required | S.C.M.U. Failed to provide the advertised S.C.M.Q 08/2012 timiously | Proof of purchase
BSD | Improve access to sustainable and affordable services | Waste management | Solid waste Landfill audit | 30/06/2013 |  |  | Conduct internal audit of landfill by 30 September andcontinuously monitor compliance of license conditions | 1st Internal Audit scheduled did not take place as planned | Conduct internal audit of landfill by 30 December andcontinuously monitor compliance of license conditions | 2 nd Internal Audit take place as planned on the 28 Dec`12 | Conduct internal audit of landfill by 30 March andcontinuously monitor compliance of license conditions | Ensure that an external audit of the landfill is conducted by 30 June. Conduct internal audit of landfill by 30 June andcontinuously monitor compliance of license conditions |  | Internal Audit reports (4) External Audit report
BSD | Improve access to sustainable and affordable services | Waste management | Village waste collection | 30/06/2013 |  |  | Prioritisation of 13 Waste Service Areas and Draft of individual SLA's. | 13 x Waste Service Areas demarcated and of individual DRAFT SLA's being workshopped with 7 x Pilot Groups being concluded | Submit prioritised list of WSA's to Council and submit to IDP for budgeting | 66 x Rural Waste Service Areas is demarcated and Service Level Conditions ((SLC`s)) was work shopped with 7 x Pilot Groups successfully. The position of WMO for this tasks is now vacant for 6 x months + now further progress can be made | Ensure inclusion in 2013/14 IDP for prioritisation |  | The position of WMO for this tasks is now vacant for 6 x months. Still awaiting Pilots-Groups to sign the Sec 25 "Registration" as "TRANSPORTERS OF WASTE" | SLA Council Item
BSD | Improve access to sustainable and affordable services | Waste management | Waste Management mass containers - 10mx6m³ | 30/06/2013 |  | 100000 | Draft Specifications for quotations, obtain quotations via Supply Chain | Busy with draft specifications for quotations, not yet quotations requested via Supply Chain | Technical evaluation and recommendations for purchasing | Finalised specifications for quotations, to be forwarded in 2013 for quotations via Supply Chain | Place order for Skips | Supply by service provider | Awaiting Consultants proposals for design costs | Specifications Proof of payment
BSD | Improve access to sustainable and affordable services | Waste management | Wise-up on Waste | 30/06/2013 |  |  | Arrange training for Eco Clubs at municipal training facility. | No training for Eco Clubs arranged | Arrange training for Eco Clubs at municipal training facility. | No training for Eco Clubs arranged | Arrange training for Eco Clubs at municipal training facility. | Arrange training for Eco Clubs at municipal training facility. | The position of WMO for this tasks is now vacant for 6 x months and training cannot proceed. The DEA-funded "Training-Centre" still on hold due to DEA`s internal control-processes | Training programme & attendance registers
BSD | Improve access to sustainable and affordable services | Waste management | Solid waste management contraventions | 30/06/2013 |  |  | Monitor issueing of Intention to Prosecute's. (ITP). Report number of ITP's issued. Submit to Law Enforcement | 5 I.T.P's issued per Team Leader per month. | Monitor issueing of Intention to Prosecute's. (ITP). Report number of ITP's issued. Submit to Law Enforcement | 5 ITP's issued per Team Leader per month. | Monitor issueing of Intention to Prosecute's. (ITP). Report number of ITP's issued. Submit to Law Enforcement | Monitor issueing of Intention to Prosecute's. (ITP). Report number of ITP's issued. Submit to Law Enforcement | 2 x Environmental Enforcement Officers positions vacant for more than 5 x years resulting 0 x prosecutions to take place | ITP register
BSD | Optimise infrastructure investment and services | Maintenance and upgrade of cemeteries | Cemetery Management | 30/06/2013 |  |  | Maintain existing cemeteries and liaise with Land, Property and Housing Division for the acquisition of land for new cemeteries | Existing cemetry maintenance is on going. Land was acquired for Lenyenye cemetery but became not suitable for cemetery development. | Maintain existing cemeteries and liaise with Land, Property and Housing Division for the acquisition of land for new cemeteries | Land was acquired for Lenyenye Cemetry and the land was paid by PED, only left with land transfere so the Environmental Impact Assessment Study can resume. Existing cemetries maintenance at proclaimed towns is on going. | Maintain existing cemeteries and liaise with Land, Property and Housing Division for the acquisition of land for new cemeteries | Maintain existing cemeteries and liaise with Land, Property and Housing Division for the acquisition of land for new cemeteries |  | Maintenance Schedule, Records of correspondence
BSD | Optimise infrastructure investment and services | Maintenance and upgrade of cemeteries | Cemetery Register (Rural) | 30/06/2013 |  |  | Train ward committee members on the utilisation of the cemetry register. Capture rural cemetery register data on a monthly basis | Requested qoutes from SCMU for registers so training can start. | Monitor the usage of the rural cemetery register and capture data on a monthly basis | Cemetry registers purchase is still awaiting for quotations from the SCMU so the training can follow. | Monitor the usage of the rural cemetery register and capture data on a monthly basis | Monitor the usage of the rural cemetery register and capture data on a monthly basis |  | Cemetery Register Training attendance register Consolidated data
BSD | Optimise infrastructure investment and services | Maintenance and upgrading of municipal buildings | Expansion of storeroom at Nkowankowa DLTC | 30/06/2013 |  | 40000 | Not applicable this quarter | Not applicable this quarter | Planning for alterations. Monitor Alterations to existing structure | Planning in progress | Not applicable this quarter | Not applicable this quarter |  | Correspondence
BSD | Optimise infrastructure investment and services | Municipal assets | Furniture - Tzaneen DLTC | 30/06/2013 |  | 25000 | Purchase new furniture for Tzaneen DLTC | Not yet purchased | Not applicable this quarter | Not yet purchased | Not applicable this quarter | Not applicable this quarter |  | Invoice & Proof of payment
BSD | Optimise infrastructure investment and services | Municipal assets | Furniture for Letsitle, Haenertsburg and Tzaneen Libraries | 30/06/2013 |  | 30000 | Procure furniture for the Libraries | No furniture purchased | Not applicable this quarter | Furniture not yet purchased | Not applicable this quarter | Not applicable this quarter |  | Invoice & Proof of payment
BSD | Promote environmentally sound practices and social development | Community Safety | Community Safety Forums | 30/06/2013 |  |  | Arrange Community Safety Forum meetings and attend to problems | Meeting held in July and August 2012 | Arrange Community Safety Forum meetings and attend to problems | Safety Forum Meetings are held once a month | Arrange Community Safety Forum meetings and attend to problems | Arrange Community Safety Forum meetings and attend to problems |  | Community Safety Forum Action Plan Minutes & Attendance Registers of meetings
BSD | Promote environmentally sound practices and social development | Environmental management | Agatha Cemetery Environmental Impact Assessment | 30/06/2013 |  | 100000 | Prepare tender specifications and submit to SCM. | Specifications prepared and submitted to SCMU | Appointment of service provider | 87% Implementation of the EHP (affected by filling of vacancy of pest control attendant) 65% review of the plan. | Monitor the drafting of the EIA | Monitor the drafting of the EIA. |  | Correspondence with SCM
BSD | Promote environmentally sound practices and social development | Environmental management | Environmental Health Plan | 30/06/2013 |  |  | Implement Environmental Health plan. Review Environmental Health Plan | Environmetnal Health Plan implemented. 25% progress on review of the plan | Implement Environmental Health plan. Review Environmental Health Plan | 65% Implementation of the plan. | Implement Environmental Health plan. Submit revised Environmental Health plan for inclusion in the IDP | Implement Environmental Health plan |  | Environmental Health Plan
BSD | Promote environmentally sound practices and social development | Environmental management | Environmental management plan | 30/06/2013 |  |  | Implement Environmental Management plan | Implemented Environmental Management Plan | Implement Environmental Management plan. Review current Environmental management plan | Specifications developed and forwarded to supply chain for processing | Implement Environmental Management plan. Review current Environmental management plan and submit for inclusion in draft IDP | Implement Environmental Management plan. |  | Environmental management plan EIAs/ Environmental Management reports & monitoring reports
BSD | Promote environmentally sound practices and social development | Environmental management | Hawkers Esplanade - Letsitele | 30/06/2013 |  | 70000 | Plan and design hawkers esplanade | Hawkers esplanades draft designs completed awaiting comments and finalisation | Procure service provider | Awaiting appointment of service provider | Construction of Hawkers Esplanade | Construction of Hawkers Esplanade |  | Plans, Designs & progress report
BSD | Promote environmentally sound practices and social development | Environmental management | Industrial impact management | 30/06/2013 |  |  | Evaluate industrial premises Respond to air pollution incidents Issue contravention notices and follow up on contraventions Attend training course for EMI's (Industrial) | 22 Industrial premises evaluated. 2 incidents of air pollution responded to and one forwaded to MDM Air Pollution Control Officer. 4 Contravention notices issued. | Evaluate industrial premises Respond to air pollution incidents Issue contravention notices and follow up on contraventions Attend training course for EMI's (Industrial) | 97 evaluations, 226 condeminations. 1x blitz operation in Nkowankowa 38 contravention notices and 27 follow up notices. | Evaluate industrial premises Respond to air pollution incidents Issue contravention notices and follow up on contraventions Attend training course for EMI's (Industrial) | Evaluate industrial premises Respond to air pollution incidents Issue contravention notices and follow up on contraventions Attend training course for EMI's (Industrial) |  | Monthly report
BSD | Promote environmentally sound practices and social development | Environmental management | Star grading system (Food handling premises monitoring) | 30/06/2013 |  |  | Evaluation of food handling premises Issue contravention notices and follow up on contraventions Issuing of certificates of acceptability | Evaluation of food handling premises issue contravention notices and follow up on contraventions issuing of certificates of acceptability | Evaluation of food handling premises Issue contravention notices and follow up on contraventions Issuing of certificates of acceptability | Larviciding started at the beginning of the raining season. Areas cannot be covered as scheduled due to the delay in the filling of the vacancy for a pest control attendant | Evaluation of food handling premises Issue contravention notices and follow up on contraventions Issuing of certificates of acceptability. Host Food hygiene Seminar | Evaluation of food handling premises Issue contravention notices and follow up on contraventions Issuing of certificates of acceptability and star grading certificates |  | Monthly report Seminar Report
BSD | Promote environmentally sound practices and social development | Environmental management | Vector control | 30/06/2013 | 6500 |  | Procurement of insecticide and implementation of vector control program | Insecticide procured and vector control program is implemented as scheduled. | Implementation of vector control program | 80 water samples collected from Oct to Dec period. 75 samples meet the minimum requirements for drinking water as set out in the SANS 241 | Procurement of insecticide and implementation of vector control program | Implementation of vector control program |  | Vector control program
BSD | Promote environmentally sound practices and social development | Environmental management | Water quality monitoring | 30/06/2013 | 72000 |  | 100% compliance to water quality monitoring schedule and 25% expenditure. Liaise with Dpt Water Affairs to roll out water Quality monitoring programme | 97 water samples collected. Meeting with DWAF held to roll out water quality programme | 100% compliance to water quality monitoring schedule and 50% expenditure. Liaise with Dpt Water Affairs to roll out water Quality monitoring programme | Monitoring 6 wetlands with the weed control committee to observe any re-invasion of the wetlands | 100% compliance to water quality monitoring schedule and 75% expenditure. Liaise with Dpt Water Affairs to roll out water Quality monitoring programme | 100% compliance to water quality monitoring schedule and 100% expenditure. Liaise with Dpt Water Affairs to roll out water Quality monitoring programme |  | Water monitoring schedule Monthly reports Correspondence with DWA
BSD | Promote environmentally sound practices and social development | Environmental management | Wetland Management | 30/06/2013 |  |  | Assist with wetland management by ensuring alien vegetation control | Assessment of 6 wetlands done and reques forwarded to Parks and week control committee | Assist with wetland management by ensuring alien vegetation control | Wetland invader weed control on going outside of the water | Assist with wetland management by ensuring alien vegetation control | Assist with wetland management by ensuring alien vegetation control |  | Wetland maintenance programme
BSD | Promote environmentally sound practices and social development | Library Services | Annual GTM library Competition | 30/11/2012 | R 6,000 & Donations |  | Library competition drafted, announced & publicized | Competition drafted, announced and publicized. 679 Entries received so far. | Competition adjudicated, awards function held. At least 500 entries received | 1039 entries in Xitsonga; English; Sepedi and Afrikaans were received, sorted and adjudicated. Donations for prizes were arranged and ceritificates designed printed and laminated by library staff. Prizes and certificates were distributed to 31 wineers. | Completed 500 Learners participating in annual library competition | Completed 500 Learners participating in annual library competition |  | Competition entry form, samples of entries, list of participating schools, awards function programme, press
BSD | Promote environmentally sound practices and social development | Library Services | Assistance to community libraries | 30/06/2013 | Donations |  | Assist with the establishment of community Libraries through facilitating Biblionef donations providing a simplified Library management guide and rudimentary training. | Library management guide and Biblionef forms for requesting book donations given to one school and one fledgeling community library. 21 Books and 50 magazines donated to schools and 100 paperback books donated to a fledgeling community library. | Assist with the establishment of community Libraries through facilitating Biblionef donations providing a simplified Library management guide and rudimentary training. | Library management guide and Biblionef forms given to two fledgeling community libraries and two schools. 121 Books and 250 National Geographic magazines donated to schools and fledgeling community libraries. Rudimentary training in accessioning given to the library staff of the Lenyenye Community Library. | Assist with the establishment of community Libraries through facilitating Biblionef donations providing a simplified Library management guide and rudimentary training. | Assist with the establishment of community Libraries through facilitating Biblionef donations providing a simplified Library management guide and rudimentary training. |  | Reports to Arts & Culture cluster
BSD | Promote environmentally sound practices and social development | Library Services | Book related events | 30/06/2013 | R6,000 & Donations |  | 2 Book related arts and culture events arranged and hosted. | 3 Big and 3 smaller book related arts and culture events arranged and hosted. | 2 Holiday programmes and 3 Book related arts and culture events arranged and hosted. | Library management guide and Biblionef forms given to two fledgeling community libraries and two schools. 121 Books and 250 National Geographic magazines donated to schools and fledgeling community libraries. Rudimentary training in accessioning given to the library staff of the Lenyenye Community Library. | 2 Holiday programmes and 5 book related arts and culture events arranged and hosted. | 3 Holiday programmes and 6 book related arts and culture events arranged and hosted. |  | Relevant section from annual report , dates, programmes, photos, press
BSD | Promote environmentally sound practices and social development | Library Services | Molati Library support | 30/06/2013 |  |  | Attend Molati Library site meetings. | Site meeting attended on the 13th of September. Detailed lists of furniture, books and equipment needed at the Molati Library compiled and submitted to the DSAC. | Attend Molati Library site meetings. Compile list of furniture and equipment needed and forward to DSAC | 1 Holiday programme, 5 big and 7 smaller book related events arranged and hosted. | Attend Molati Library site meetings. Combile list of books neede and forward to DSAC | Attend Molati Library site meetings. Prepare staff requisitions for staff to be appointed |  | Site reports Correspondence with DSAC
BSD | Promote environmentally sound practices and social development | Library Services | Library development and reading promotion | 30/06/2013 | 3968179 |  | Ensure that accurate information services, continues user education, prompt lending services and balanced collection development takes place | 25022 Library users; 23855 Library items circulated; 45 Displays mounted; 18 School groups hosted; 211 School project themes assisted with; 239 Donated books processed; DSAC 2nd quarter performance assessment documents finalized and submitted. | Ensure that accurate information services, continues user education, prompt lending services and balanced collection development takes place | Two site meetings at the Molati Library attended. Lists of furniture, books and equipment for the library compiled and submitted. EXCO item on the Molati Library drafted and distributed to directors for comments. | Ensure that accurate information services, continues user education, prompt lending services and balanced collection development takes place | Ensure that accurate information services, continues user education, prompt lending services and balanced collection development takes place |  | Monthly reports
BSD | Promote environmentally sound practices and social development | Library Services | Computerised library lending function | 30/06/2013 | 30000 |  | 100% of Letsitele and Haenertsburg Library books barcoded. 60% of Tzaneen Library books barcoded | 100% of Letsitele and Haenertsburg Library books barcoded. 50% of Tzaneen Library books barcoded | 50% of Letsitele and Haenertsburg library books linked to SLIMS system and 100% of Tzaneen library books barcoded | 100% of Letsitele and Haenertsburg Library books barcoded. 90% of Tzaneen Library books barcoded. 0% of Haenertsburg books barcoded | 100% of Haenertsburg and Letsitele library books linked to SLIMS system. 40% of Tzaneen libary books linked to SLIMS | SLIMS fully operation at Letsitele and Haenertsburg libraries. 100% of Tzaneen library books linked to SLIMS | The Haenertsburg Librarian could not link books as she still does not have an assistant due to long delays in the appointment process and the library is still without internet connectivity. 10% Of Tzaneen Library books still to be barcoded due to books issued and not yet returned and lack of staff. | Reports to DSAC
BSD | Promote environmentally sound practices and social development | Maintenance and upgrade of parks and open spaces | Garden management | 30/06/2013 |  |  | Maintain all gardens, attend to complaints from the public and keep a register | All gardens maintained monthly and complaints register is kept. | Maintain all gardens, attend to complaints from the public and keep a register | All gardens maintained according to schedule | Maintain all gardens, attend to complaints from the public and keep a register | Maintain all gardens, attend to complaints from the public and keep a register |  | Maintenance Schedule -Complaints register
BSD | Promote environmentally sound practices and social development | Maintenance and upgrade of parks and open spaces | Open space management | 30/06/2013 |  |  | Supervise service provider to ensure compliance to the SLA | Open spaces maintained done monthly. | Supervise service provider to ensure compliance to the SLA | Thender expired and withdrawn from tender advertisement in favour of EPWP which is still not in place. A month to month renewal of contract was applied but no requisitions are signed by finance department and currently unable to maintain open spaces and they are over grown. | Supervise service provider to ensure compliance to the SLA | Supervise service provider to ensure compliance to the SLA |  | Parks maintenance schedule
BSD | Promote environmentally sound practices and social development | Maintenance and upgrade of parks and open spaces | Sports and Recreation facility management | 30/06/2013 |  |  | Co-ordinate the maintenance of play apparatus, recreational facilities and stadiums | Play apparatus repairs request was sent to maintenance Division but not yet attednded it. Repainted Play aparratus at Maritz Park. | Co-ordinate the maintenance of play apparatus, recreational facilities and stadiums | Maintance of sports and recretion facility is ongoing | Co-ordinate the maintenance of play apparatus, recreational facilities and stadiums | Co-ordinate the maintenance of play apparatus, recreational facilities and stadiums |  | Sport and Recreational Facility maintenance schedule
BSD | Promote environmentally sound practices and social development | Sport and recreation | GTM Jazz Festival | 30/06/2013 | 1000000 |  | Plan GTM Jazz festival, coordinate weekly planning meetings | Events committee resumed with preparatory meetings for jazz festival. | Host GTM Jazz festival on the 6th of October '12 | Jazz in the Garden Festival was held on the 01 Dec 2012 at Nkowankowa stadium and 15 artists were hosted |  | Plan GTM Jazz festival for 2013 |  | Number of Tickets, sold, report, photos, advertisement
BSD | Promote environmentally sound practices and social development | Sport and recreation | Arts and Culture monitoring | 30/06/2013 | 70000 |  | Organise workshop for new Arts and Culture Council to train them on requirements. Monitor preparations and implementation of Arts and Culture programme by Arts and Culture Council | Arts and culture community members became involved in Letaba Expo in August 2012, exhibited,making and sold their hand work. Requested training assistance from HR. | Monitor preparations and implementation of Arts and Culture programme by Arts and Culture Council | Choral Music Event will be hosted in June 2013 at Lenyenye Community Hall | Monitor preparations and implementation of Arts and Culture programme by Arts and Culture Council | Monitor preparations and implementation of Arts and Culture programme by Arts and Culture Council |  | Arts & Culture Programme Training attendance register Correspondence
BSD | Promote environmentally sound practices and social development | Sport and recreation | Sports and Recreation monitoring | 30/06/2013 | 140000 |  | Monitor preparations and implementation of Sports programme by the Sport and Recreation Council | Purchased 300 medals in support of the 5th Bulamahlo Cluster Sport Arts and Culture annual event. Held Clusters Indegenous Games and hosted Local indegenous games. GTM participants participated in District Indegenous games at Namakgale. | Monitor preparations and implementation of Sports programme by the Sport and Recreation Council | Tzaneen Sports Day was held at Nkowankowa stadium on the 08 Dec 2012 and only soccer and netball were played. 500 medals were sponsored by Arbore Park Lodge | Monitor preparations and implementation of Sports programme by the Sport and Recreation Council | Monitor preparations and implementation of Sports programme by the Sport and Recreation Council |  | Attendance registers for proof of attendance. Programme and report.
BSD | Promote environmentally sound practices and social development | Sport and recreation | SAIMSA Games | 30/06/2013 | 500000 |  | Co-ordinate and facilitate SAIMSA Games to b held during 22-29 September in Botswana | 103 participants inclusive 3 Councillors, and Acting Director attended the SAIMSA event on the 22-29/09/12. | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter |  | Advertisements and Programmes , Reports and minutes.
GG | Effective and Efficient administration | Regulatory Framework | Hawkers Policy & By-law | 30/06/2013 |  |  | Review Hawkers policy and By-law | No progress | Submit Hawkers Policy to Council for adoption and the By-law for public participation | No progress | Submit Hawkers Bylaw to CORP for gazetting |  |  | Council Resolution on Hawkers Policy
GG | Effective and Efficient administration | Safety and Security | Building Access control | 30/06/2013 |  |  | Ensure that access to all Council buildings are monitored and access controlled by managing the Security Service Provider. Manage Morphy access control system upon installation. Keep records of complaints regarding security | Tender advertised in August. | Ensure that access to all Council buildings are monitored and access controlled by managing the Security Service Provider. Manage Morphy access control system upon installation. Keep records of complaints regarding security | Bid Evaluated and waiting for Adjudication process | Ensure that access to all Council buildings are monitored and access controlled by managing the Security Service Provider. Manage Morphy access control system upon installation. Keep records of complaints regarding security | Ensure that access to all Council buildings are monitored and access controlled by managing the Security Service Provider. Manage Morphy access control system upon installation. Keep records of complaints regarding security |  | Security Monthly reports -Complaints Register -Morphy Access Control System functionality report
GG | Effective and Efficient administration | Safety and Security | Securing Council Property | 30/06/2013 |  |  | Ensure that Security Service Provider guard Council property. Keep record of all stolen property and follow all the necessary steps to report theft to the Police. | Theft register opened in July 2012 | Ensure that Security Service Provider guard Council property. Keep record of all stolen property and follow all the necessary steps to report theft to the Police | Theft register opened in July 2012 | Ensure that Security Service Provider guard Council property. Keep record of all stolen property and follow all the necessary steps to report theft to the Police | Ensure that Security Service Provider guard Council property. Keep record of all stolen property and follow all the necessary steps to report theft to the Police |  | Security Monthly Reports -Stolen property register including case numbers e
LED | Create a stable and enabling economic environment by attracting suitable investors | By-Law enforcement | Dog licenses and temporary advertisement | 30/06/2013 |  |  | Attend to and resolve all complaints received relating to Dog licenses and temporary advertisements. Keep a register of complaints | No complaints received | Attend to and resolve all complaints received relating to Dog licenses and temporary advertisements. Keep a register of complaints | No complaints received | Attend to and resolve all complaints received relating to Dog licenses and temporary advertisements. Keep a register of complaints | Attend to and resolve all complaints received relating to Dog licenses and temporary advertisements. Keep a register of complaints |  | Register of complaints regarding Dog licenses & Temporary advertisements
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance monitoring & evaluation | 30/06/2013 |  |  | Participate in the Annual Performance Assessment for 2011/12. Ensure that scoresheets are completed in time & POEs are complete | Not done | Conduct an informal assessment of 1st Quarter Performance of relevant employees in the Department and send report to the MM by 21 October '12 | Not done | Participate in the mid-year employee performance evaluations for 2012/13. Ensure that scoresheets are completed in time & POEs are complete | Conduct an informal assessment of the 3rd Quarter Performance of relevant employees in the Department and submit report to the MM by 20 April '13 | Director newly appointed | 1st & 3rd Qtr Informal Departmental Individual Performance Reports Correspondence

## PED KPIs
Key Performance Indicators (KPIs) - Planning and Economic Development
KPA/ Theme | Strategic Objective | Programme | Departmental KPI | Baseline (end June 2012) | Target Sept '12 | Actual Sept '12 | Target Dec '12 | Actual end Dec '12 | Target Mar '13 | Target Jun '13 | Reason for deviation | Means of verification
BSD | Improve access to sustainable and affordable services | Human Settlements | # of housing units constructed | 733 | 100 | 0 | 200 | 21 | 333 | 333 | There was a delay on approval and provision of Geo-tech report by COGSHTA | Provincial PMU reports
BSD | Promote environmentally sound practices and social development | Youth, Gender & Disability support | # of jobs created for youth, women and people with disabilities through LED initiatives | 2052 | Reporting only - no target | FY = 762 FA = 330 MY = 439 MA = 294 DIS = 2 | Reporting only - no target | 1825 | Reporting only - no target | Reporting only - no target |  | Job creation register
GG | Effective and Efficient administration | Council Support | % of Departmental Council resolutions implemented | 22 | 100% | 36% | 100% | 100% | 100% | 100% |  | Departmental Resolution register
GG | Effective and Efficient administration | Information management | % Of land use changes captured on GIS | 34 | 100% | 85% | 100% | 90% | 100% | 100% | Slow submission from Consultant | Human & Financial Resource commitments for GIS/MIS List of requests for cadastre changes submitted to services provider
GG | Effective and Efficient administration | Management and Administration | # of departmental meetings | 6 | 2 | 5 | 3 | 1 | 5 | 6 |  | Minutes and Attendance registers of Departmental meetings
GG | Effective and Efficient administration | Management and Administration | # of Manager meetings | 6 | 1 | 1 | 3 | 2 | 4 | 6 |  | Minutes and Attendance registers of Manager meetings
GG | Effective and Efficient administration | Management and Administration | # of Stakeholder meetings held | 8 | 1 | 4 | 2 | 5 | 3 | 4 | ADM - 2 LED - 3 | Minutes and Attendance Registers Correspondence with stakeholders Signed TOR/MOU's with stakeholders
GG | Effective and Efficient administration | Performance monitoring and reporting | # of PED Departmental monthly reports submitted on time | 12 | 3 | 2 | 6 | 6 | 9 | 12 |  | Monthly, quarterly, half yearly and annual reports
GG | Effective and Efficient administration | Performance monitoring and reporting | # of LED Thrust meetings held | 0 | 1 | 0 | 2 | 1 | 3 | 4 |  | Minutes and Attendance Registers Correspondence with stakeholders
GG | Effective and Efficient administration | Regulatory Framework | # of Departmental policies developed/reviewed | 3 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 8 |  | 1. Regulation of Spaza Shops policy 2. Tavern policy 3. Alienation of municipal owned land policy 4. Policy on Allocation and occupation of municipal houses 5. Prevention of illegal occupation of Land Policy 6. Pioneers Policy 7. Review of SDF 8, Housing Plan
GG | Effective and Efficient administration | Sound Governance | % of Internal Audit queries responded to within 10 days | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Register of Internal Audit queries & corresponding reports
GG / MFVM | Increase financial viability | Budget management | % of departmental budget spent | 85% | 25% | 19% | 50% | 46.57% | 75% | 100% |  | Monthly financial budget reports
GG / MFVM | Increase financial viability | Financial reporting | % of AG queries responded to within 2 working days | 100% | Not applicable this quarter | Not applicable this quarter | 100% | 70% | Not applicable this quarter | Not applicable this quarter |  | Register of Audit queries & corresponding reports
LED | Create a stable economic environment by attracting suitable investors | Economic Growth and Investment | # of GTEDA board meetings attended | 8 | 1 | 2 | 2 | 2 | 3 | 4 |  | Attendance Registers
LED | Create Community beneficiation and empowerment opportunities | Community Works Programme | Number of job opportunities created through the CWP | 2052 | No target -reporting | 1800 | No target -reporting | 2000 | No target -reporting | No target -reporting |  | CWP Employment register
LED | Create Community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | R-value sourced for LED initiatives | R3,5M | Not applicable this quarter | Not applicable this quarter | 1M | R300,000 from LDA, R10,000 from ABSA, R48m from Coghsta. | Not applicable this quarter | 2.5M |  | Signed MOU
LED | Integrated developmental planning | Township Revitalisation | # of NDPG projects finalised | 2 | Not applicable this quarter | Not applicable this quarter | Not applicable this quarter | 0 | Not applicable this quarter | 3 | Projects in progress | Reports from Project Manager
LED | Integrated developmental planning | Township Revitalisation | % of monthly NDPG reports submitted on time | 12 | 3 | 3 | 6 | 5 | 9 | 12 |  | Proof of submission of NDPG reports
LED | Integrated developmental planning | Township Revitalisation | # of monthly NDPG meetings | 9 | 3 | 3 | 6 | 6 | 9 | 12 |  | Minutes of NDPG meetings
LED/ MTOD | Develop a high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | % of PED Manager's with signed performance plans by 31 July | 100% | 100% | 0% | Not applicable this quarter | 100% | Not applicable this quarter | Not applicable this quarter |  | Signed Performance Plans

## PED Projects
Quarterly targets per Project - Planning and Economic Development
KPA/ Theme | Strategic Objective | Programme | Project | Planned end date | Opex 2012/2013 | Capex 2012/2013 | Qtr Ending Sept '12 | Actual Achieved Sept '12 | Qtr Ending - Dec '12 | Actual End Dec '12 | Qtr Ending - Mar '13 | Qtr Ending - Jun '13 | Reason for deviation | Means of verification
BSD | Improve access to sustainable and affordable services | Human settlements | 560 units for un blocking of the blocked project. Wards- 4,5,10,11,16,19,23,24,28,29, 30 and 34 | 30/06/2013 | 20000 |  | Verification of beneficiaries and effect changes on status quo report where possible | 417 blocked has been unblocked. The remaining 143 units is submmitted to COGHSTA. | Continuous monitoring through meetings and site visits | 417 blocked has been unblocked. The remaining 143 units is submitted to COGHSTA. | Continuous monitoring through meetings and site visits | Continuous monitoring through meetings and site visits | Waiting approval by COGHSTA | Correspondence with COGHSTA Minutes and attendance registers Quarterly Council reports /items
BSD | Improve access to sustainable and affordable services | Human settlements | Acquisition of land parcels for development | 30/06/2013 |  | 364300 | Liaise with all relevant stakeholders for the acquisition of land for the realisation of the 2030 vision (Berlyn, Pusela, Portion 36 & 37 of Hamawasha, Muhlaba's Location, Gelukaut Farm, Haenertsburg town, Shivurali and Ledzee) | 25% The identified land for transfer has been submmitted to houising development agency to facilited the negotiation and transfer on behalf of GTM. | Liaise with all relevant stakeholders for the acquisition of land for the realisation of the 2030 vision (Berlyn, Pusela, Portion 36 & 37 of Hamawasha, Muhlaba's Location, Gelukaut Farm, Haenertsburg town, Shivurali and Ledzee) | 25% The identified land for transfer has been submitted to housing development agency to facilitate the negotiation and transfer on behalf of GTM. | Liaise with all relevant stakeholders for the acquisition of land for the realisation of the 2030 vision (Berlyn, Pusela, Portion 36 & 37 of Hamawasha, Muhlaba's Location, Gelukaut Farm, Haenertsburg town, Shivurali and Ledzee) | Liaise with all relevant stakeholders for the acquisition of land for the realisation of the 2030 vision (Berlyn, Pusela, Portion 36 & 37 of Hamawasha, Muhlaba's Location, Gelukaut Farm, Haenertsburg town, Shivurali and Ledzee) |  | Correspondence Minutes of meetings with TA, PW, Rural Development and Land reform, HDA, COGHSTA
BSD | Improve access to sustainable and affordable services | Human settlements | Administration of tenants at Portion 6 of Pusela 555LT and development of plans | 30/06/2013 |  |  | Allocation and administration of tenants Handling of queries | the Lease Agreements has expired | Administration of tenants and handling of queries | The Lease Agreements has expired we requested the Director to extend the lease agreement. The Director referred the matter to the Cluster committee. however the continue to pay for rental and services. | Administration of tenants and handling of queries | Administration of tenants and handling of queries | The lessees has been notified about the lapse of the lease agreements. We are waiting for the approval of renewal lease agreements by the acting municipal manager. | Lease agreements
BSD | Improve access to sustainable and affordable services | Human settlements | Emergency Housing (44 units) | 30/06/2013 | 20000 |  | Completion of beneficiary lists and attach documents and details Submission of forms to COGHSTA Verification of beneficiaries Monitor project implementation to be completed by end of September | The beneficairy lists has been completed and application forms summitted to COGHSTA and captured and approved in the housing subsidy system(HSS). Progress Report: Foundation : 34 Wall Plate : 26 Roof & Finishes :16 . VIPToilets : 30 | Monitor implementation and report progress | 42 units completed and 2 units at roof and finish. 30 Toilets | Monitor implementation and report progress | Monitor implementation and report progress | The Units are too vast. | Updated RDP Housing Beneficiary list Correspondence regarding Housing Project steering Committee minutes & attendance registers
BSD | Improve access to sustainable and affordable services | Human settlements | Low Cost housing - RDP Housing (333 units) | 30/06/2013 |  | COGHSTA | Completion of beneficiary lists and attach documents and details Submission of forms to COGHSTA Verification of beneficiaries Monitor project implementation | 100% of beneficairy lists and application forms has been submmitted to COGHSTA. and verification of beneficiaries has been done. | Monitor Projec implementation and report progress on the building of houses at the allocated villages | 21 foundations completed | Monitor Projec implementation and report progress on the building of houses at the allocated villages | Monitor Projec implementation and report progress on the building of houses at the allocated villages | The was delay on the approval and issuing of Geo-Technical reports | Report on Marirone (22), Mulati (20), Bordeaux (20), Serututung (20), Matsilapata (20), Ramotshinyadi (18), Moleketla (19), Nsako (10), Bonn(10), Rikhotso (10), Mawa Block 6(10), Xihoko (10), Mookgo (10), Pharare (10), Ezekhanya(10), Makhubedung(10), Mogapeng(10), Ga-Wally(10), Nyakelani(10), Radoo (10), Ramotshinyadi(10), Burgersdorp (8), Rwanda (6), Mkambako (4), Mugwazeni (4), Fobeni (3), Nyakelang (3), Motupa (2), Nwajaheni(2), Mandlakazi (2), Lefara(2), Maramofase (2), Bokhuta (1), Mapitlula (1), Radoo (1), Myakayaka (1), Runnymede(1), Sunnyside(1), Mariveni(1), Relela(1), Pulanen(1), Dan(1), Mphame(1), Mogoboya(1), Mamitwa(1), Mavele(1), Serare(1), Leolo(1), Mookgo(1).
BSD | Improve access to sustainable and affordable services | Human settlements | Pioneer housing administration | 30/06/2013 |  |  | Allocation and administration of tenants. Attend to queries and complaints | Two unit were allocated to beneficiaries for the quarter. thus: unit 10 and 30 | Allocation and administration of tenants. Attend to queries and complaints | one beneficiary was allocated unit 11 | Allocation and administration of tenants. Attend to queries and complaints | Allocation and administration of tenants. Attend to queries and complaints | none | Correspondence Monthly reports Complaints register
LED | Integrated Developmental Planning | Township revitalisation | Community Parks(PP5) | 30/06/2013 | 600000 |  | Monitor the development of community parks and report progress | Service Provider appointed. Designs in place. | Monitor the development of community parks and report progress | Relocation of grave site needs to take place | Monitor the development of community parks and report progress | Monitor the development of community parks and report progress | Process held in abeyance by family | Minutes of meetings and monthly reports
BSD | Optimise infrastructure investment and services | Municipal assets | Furniture for PED offices | 30/06/2013 |  | 50000 | Procure new furniture for the PED office | No progress. | Not applicable this quarter | In process of finalizing appointment of town planner and office for LED | Not applicable this quarter | Not applicable this quarter | Director newly appointed | Invoice & Proof of payment
GG | Effective and Efficient administration | Information management | Archiving (Filing) for PED | 30/06/2013 |  | 60000 | Establish nature of filing system required at Town Managers Offices in conjuction with Records | No progress. | Establish filing system with the assistance of the Records section | No progress | Ensure that filing system are maintained with the assistance of Records | Ensure that filing system are maintained with the assistance of Records | Corporate Services (Records) to take over the process | Proof of purchase Communiques
LED | Integrated Developmental Planning | Township revitalisation | Rural Broadband connectivity (PP4) | 30/06/2013 |  | 5000000 | Monitor the implementation of the Rural Broadband connectivity and report to Council | Service provider on site intial work already commenced. | Monitor the implementation of the Rural Broadband connectivity and report to Council | 7 sites sattelite office connected and online (Lenyenye & Nkowankowa Town Managers offices, Nkowankowa testing ground, Letsitele Library, Bulamahlo,Relela & Runnymeded Thusong Centres). | Monitor the implementation of the Rural Broadband connectivity and report to Council | Monitor the implementation of the Rural Broadband connectivity and report to Council |  | Minutes of meetings & Monthly reports
LED | Create a stable and enabling economic environment by attracting suitable investors | Economic Growth and Investment | Alienation of sites | 30/06/2013 |  |  | Identify available land for alienation. Manage the alienation of sites. Prepare documentation for the servicing of sites and implementation to ESD and submit to CFO for advertising and awarding of bids. | Awaiting Council Resolution | Identify available land for alienation and submit proposals and recommendations to Director PED by 31 October 2012 Manage the alienation of sites. Identify available land for alienation. Prepare documentation for the servicing of sites and implementation to ESD and submit to CFO for advertising and awarding of bids. | Still waiting for Council resolution for approval of alienation of sites at Dan Ext 2 and for the 30 erven in Nkowankowa Industrial site waiting for valuation price | Manage the alienation of sites . Identify available land for alienation. Prepare documentation for the servicing of sites and implementation to ESD and submit to CFO for advertising and awarding of bids. | Manage the alienation of sites . Identify available land for alienation. Prepare documentation for the servicing of sites and implementation to ESD and submit to CFO for advertising and awarding of bids. |  | Deed of sale for all alienated sites
LED | Create community beneficiation and empowerment opportunities | Agriculture | Land Reform/Agriculture project support | 30/06/2013 | 100000 |  | Facilitate land reform forum meeting Attend monthly and quarterly meetings for identified agricultural projects and facilitate services to be provided to the identified projects (Tours, Mokgolobotho, Sapekoe, Banareng, Bathlabine, Kgatle, Mkomomonto, Maitjeng and Balepye). Engange stakeholder in freight study throug DRT and support during events | Mokgolobotho: Faciliatated meetings with Land Reform on Capespan's intened to withdraw from the partnership Adjudicated the Bid aplications with Vumelana on the 21st of Septemeber. Nkomomonto: Assisting the Coop in reviewing the composting project. Batlhabine: facilitated meetings with Land Reform on CPA issues and wages. | Facilitate land reform forum meeting Attend monthly and quarterly meetings for identified agricultural projects and facilitate services to be provided to the identified projects (Tours, Mokgolobotho, Sapekoe, Banareng, Bathlabine, Kgatle, Mkomomonto, Maitjeng andBalepye). Engange stakeholder in freight study throug DRT and support during events | Land Reform: Coordinated the land reformm meeting on the 9th of November. Batlahabine: Held 3 meetings for Batlhabine with rural development on 5th,11th and 16th of October. Mamahlola: Still in process of acquisition of Strategic partnner/investor for Mamahlola through Vumelana. Managemnet appointed and payments done to employees. Mokgolobotho: Withdrawal by Capespan. Tours: Still on halt due to allegations by potential funder. Farmers continue with subsitance farming of mealies. Nkomomnto: Held poultry farmers meeting on 18th of October for Adluck presentation. | Facilitate land reform forum meeting Attend monthly and quarterly meetings for identified agricultural projects and facilitate services to be provided to the identified projects (Tours, Mokgolobotho, Sapekoe, Banareng, Bathlabine, Kgatle, Mkomomonto, Maitjeng and Balepye). Engange stakeholder in freight study throug DRT and support during events | Facilitate land reform forum meeting Attend monthly and quarterly meetings for identified agricultural projects and facilitate services to be provided to the identified projects (Tours, Mokgolobotho, Sapekoe, Banareng, Bathlabine, Kgatle, Mkomomonto, Maitjeng and Balepye). Engange stakeholder in freight study throug DRT and support during events |  | Monthly reports Minutes & agendas
LED | Create community beneficiation and empowerment opportunities | Agriculture | Renovation of Sapekoe staff compound | 30/06/2013 | 1000000 |  | Report on progress with the implementation of the Renovation of the Sapekoe staff compound by GTEDA | Sapekoe steering committee held on the 20th August. | Report on progress with the implementation of the Renovation of the Sapekoe staff compound by GTEDA | 1. Provided on-going administrative support to Makgoba tea estate management and staff. 2. Facilitated the payment of salaries to 447 employees at a cost of R766 441.89. (October 2012) 3. Held feasibility sessions with representatives of Almac Cosmocare (Mr. Ballal Chandrachud and Dr. Goswani) on the 15th , 16th and 17th October 2012 who have signed an MOU with LADC to conduct the following a. Feasibility study b. Due diligence and c. Development of Business Proposal 4. Steering committee meeting was successfully hosted on the 29th October 2012 5. Facilitated the payment of 500 workers employed at Grenshoek at a cost of R604 695.00 under Extended Public Works Programme. 6. Submitted and presented a proposal for the tea estate to the Jobs fund on the 5th October 2012, a follow up presentation was done again on the 19th October 2012. All these sessions were facilitated by the Economic Cluster of the Limpopo Premier’s office 7. Facilitated the payment of salaries to 445 employees at a cost of R755 061,46 (November 2012). 8. Monthly progress reports were developed and submitted to LADC. 9. Facilitated a monthly management meeting on the 4th December 2012 to discuss the performance of the Estate, challenges encountered and interventions taken and planning for the future. 10. Successfully hosted a steering committee meeting on the 5th December 2012 Facilitated the payment of salaries to 437 employees at a cost of R762 070,00 (December 2012) 11. Attended Management meeting to address water crisis as Sapekoe on 03 December 2012. 12. Facilitated a monthly management meeting on the 4th December 2012 to discuss the performance of the Estate, challenges encountered and interventions taken and planning for the future. 13. Held a meeting on the 31st December 2012 with a representative of Public Investment Cooperation (PIC) about the possibility of project funding. Pruning Plan To date a total of 501.4 hectares have been completed at Middlekop, workers are doing scheduled maintenance.(on-going activity) 60.87 hectares have been pruned at Grenshoek over a one month period by workers from the EPWP. 25 workers from Middlekop have been deployed to continue with maintenance on the pruned area the pruning process at Grenshoek. | Report on progress with the implementation of the Renovation of the Sapekoe staff compound by GTEDA | Report on progress with the implementation of the Renovation of the Sapekoe staff compound by GTEDA |  | GTEDA Progress reports
LED | Create community beneficiation and empowerment opportunities | Community Works | Community works support | 30/06/2013 |  |  | Facilitation and identification of areas for the implementation of community works programme. Chair meetings of Reference Committee. Report quarterly on jobs created through the CWP | The project is extended to 5 wards: 22,29,30,32. New local agent appointed as Golang Kulani and Currently 1800 participants are on site. Mvula Trust as the Service Provider. Coordinators appointed in ward 22 and 29 to finalize appointments in October. Participants have not yet been appointed. | Support, attend and chair meetings and liaise with internal departments regarding the implementation and maintenance of the identified projects. Report quarterly on jobs created through the CWP | Supported and attended 1 meeting on 29th Nov and 3 events for CWP on the 3rd Nov, 10th Dec and 13th Dec. Jobs created is still standing at 1800. | Support, attend and chair meetings and liaise with internal departments regarding the implementation and maintenance of the identified projects. Report quarterly on jobs created through the CWP | Support, attend and chair meetings and liaise with internal departments regarding the implementation and maintenance of the identified projects. Report quarterly on jobs created through the CWP |  | Quarterly Job reation report Correspondence Minutes of meetings and attendance registers
LED | Create community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | Commercialisation of the Tzaneen Airfield | 30/06/2013 |  |  | Liaise with MDM on implementing the Airfield Feasibility study | Waiting for Mopani to take over | Liaise with MDM on implementing the Airfield Feasibility study | Negotiations between MDM and Greater Tzaneen Municipality underway | Liaise with MDM on implementing the Airfield Feasibility study | Liaise with MDM on implementing the Airfield Feasibility study |  | Correspondence
LED | Create community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | GTEDA Sustainability | 30/06/2013 | 2500000 |  | Provide continuous support to GTEDA to ensure self- sustainability. Attend board and monthly meetings as per invitation and scheduled. Monitor implementation of SLA. Monitor progress with Business Support hub. | Sustainability plan is finalized and approved by board. | Provide continuous support to GTEDA to ensure self-sustainability. Attend board and monthly meetings as per invitation and schedule. Monitor adherence to SLA | Board meeting attended on the 27th of October and Strategic workshop from the 30th Nov to 2nd December 2012. | Provide continuous support to GTEDA to ensure self-sustainability. Attend board and monthly meetings as per invitation and schedule. Monitor adherence to SLA | Provide continuous support to GTEDA to ensure self-sustainability. Attend board and monthly meetings as per invitation and schedule. Monitor adherence to SLA |  | Monthly reports Minutes & agendas
LED | Create community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | LED strategy review | 30/06/2013 | 150000 |  | Submit LED projects from revised strategy to GTEDA & IDP for prioritisation and implementation. Monitor progress | Final copy of the LED strategy is submitted. | Not applicable this quarter | Final copy submitted and Division to work on the implementation plan and genertae item for approval to Council. | Not applicable this quarter | Not applicable this quarter |  | LED Strategy
LED | Create community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | Partnerships and Stakeholder meetings | 30/06/2013 | 10000 |  | Faciltate the development of MOU's with LDA, Hand in Hand and Limpopo LED Resource Center. Facilitate meetings with identified stakeholders Establish and conclude clear terms of references for the establishment of the LED forum. | MOU with Seda is reviewed. MOU with TIL is signed awaiting signatures from TIL. Finalizing the MOU with Univen on Poverty Research and Monitoring Pilot. The following MOU are still to be facilitated: LTPA, Hand in Hand and Business Chamber. | Facilitate the breakfast session for LED report and planned projects.Faciltate the development of MOU's with LDA, Hand in Hand and Limpopo LED Resource Center. Strenthening of partnerships and facilitate bi-monthly meetings with LED forum members. | Supported and attended 1 meeting on 29th Nov and 3 events for CWP on the 3rd Nov, 10th Dec and 13th Dec. Jobs created is still standing at 1800. | Faciltate the development of MOU's with LDA, Hand in Hand and Limpopo LED Resource Center. Strenthening of partnerships and facilitate bi-monthly meetings with LED forum members. | Faciltate the development of MOU's with LDA, Hand in Hand and Limpopo LED Resource Center. Strenthening of partnerships and facilitate bi-monthly meetings with LED forum members. | LED breakfast session earmarked for 3rd quarter due to other programmes running. Facilitation of MOU's for Limpopo Resource Center and LDA delayed. | 3 signed MOU's LED forum meeting minutes and attendance registers
LED | Create community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | SMME strategy development | 30/06/2013 | 150000 |  | Facilitate meetings with relevant stakeholders for the development of the SMME strategy. | The development of the SMME strategy is delayed awaiting approval of the LED Strategy. | Advertising for the development of the SMME strategy. Appointment of the service provider | The development of the SMME strategy is delayed awaiting approval of the LED Strategy. | Monitoring the service provider for the development of the strategy | Presentation of the final document and Council resolution. | Project on halt due to finalization of the LED strategy. | Minutes and monthly reports
LED | Create community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | SMME Support | 30/06/2013 | 200000 |  | Facilitate the establishment of partnerships with development agencies Facilitate establishment of cooperatives within CWP projects and other cooperatives and build relationships | MOU with Seda is reviewed. Relationship is maintained. | Facilitate the establishment of partnerships with development agencies Facilitate establishment of cooperatives within CWP projects and other cooperatives and build relationships | Board meeting attended on the 27th of October and Strategic workshop from the 30th Nov to 2nd December 2012. Partnership with SEDA in place for support on SMME's. Report on cooperatives establishment for report from SEDA. | Facilitate the establishment of partnerships with development agencies Facilitate establishment of cooperatives within CWP projects and other cooperatives and build relationships | Facilitate the establishment of partnerships with development agencies Facilitate establishment of cooperatives within CWP projects and other cooperatives and build relationships | The Division to follow on agreements on submission of reports by Seda to Council. | Monthly reports Co-operatives establishment records
LED | Create community beneficiation and empowerment opportunities | Enterprise Development (SMME support) | Tannery and Leather making | 30/06/2013 | 800000 |  | Report on progress with the implementation of the Tannery and Leather making project by GTEDA | The development of the SMME strategy is delayed awdaiting approval of the LED Strategy. | Report on progress with the implementation of the Tannery and Leather making project by GTEDA | 1. Facilitated a meeting between GTEDA management, Monye-le-shako staff and Mawasha Chemicals cc on the 27th November 2012 at GTEDA offices, the following resolutions were taken. a. The close-out report must be re-worked to include inputs of all stakeholders and submitted to GTEDA on the 06th December 2012. b. The evaluation process of learners must be fast tracked and POEs must be completed by the 5th December 2012 . c. Monye-Le-Shako must be helped with quotations for materials and firms where they can buy leather making raw materials at a reasonable price in the future. 2. Facilitated a strategic planning meeting of Monye-Le-shako Cooperative with SEDA where the following resolutions were taken. a. A production line must be set up to enable smooth operation at the factory b. Lucrative markets must be identified and SABS must be engaged for quality assurance of prototypes. c. Operational policies and procedures and systems must be established to ensure the factory complies with applicable laws. d. Assist the Cooperative to identify strategic partners that will assist with funding to expand the factory. e. Speed up turn around time of responding to the Co-operatives requests for assistance. 3. A site visit was conducted to the factory on the 17th October to assess progress made to date and to provide support to staff members. 4. Training on leather making and product development has been completed and members of the Co-operative have commenced with production of belts and sandals. 5. A meeting was held between GTEDA and SEDA on the 06th December 2012 to discuss the wayforward on the strategic plan Report. 6. The evaluation process of learners was doe on the 18th December 2012. 7. Facilitated the assessment of learners by an independent assessor on the 19th December 2012 at the factory in Nkowankowa, a report of the assessment will be available in January 2013. 8. Attended a prayer session held on the 14th December 2012 by different Pastors at the factory to wish the project well for the future. 9. Training on leather making and product development has been completed and members of the Co-operative have commenced with production of belts and sandals. 10. Held a meeting on the 31st December 2012 with a representative of Public Investment Cooperation (PIC) about the possibility of project funding. | Report on progress with the implementation of the Tannery and Leather making project by GTEDA | Report on progress with the implementation of the Tannery and Leather making project by GTEDA |  | GTEDA Progress reports
LED | Create community beneficiation and empowerment opportunities | Poverty reduction & Empowerment | Employment Database Development | 30/06/2013 | 400000 |  | Arrangements for Job Creation Summit. Cleaning of Jobcreation Database | MOU with Seda is reviewed. Relationship is maintained. | Host Employment Creation Summit for the District and report to Council | Not done | Maintain Employment Creation Database | Maintain Employment Creation Database | Awaiiting finalization of the LED Strategy. | Job Creation summit report
LED | Create community beneficiation and empowerment opportunities | Poverty reduction & Empowerment | Poverty Alleviation strategy | 30/06/2013 | 450000 |  | Pilot the development of a Poverty Alleviation strategy in Ward 1. Report progress. Ensure capacity building of Municipal Employees by UNIVEN | Job creation summit still in plan.Job creation data acquired and submitted for CWP/EPWP projects. | Pilot the development of a Poverty Alleviation strategy in Ward 1. Report progress. Ensure capacity building of Municipal Employees by UNIVEN | Project launched on the 8th of November and training of enumerators started on the 9th to the 13th of November. Actual data capturing started on the 11th of December. | Pilot the development of a Poverty Alleviation strategy in Ward 1. Report progress. Ensure capacity building of Municipal Employees by UNIVEN | Pilot the development of a Poverty Alleviation strategy in Ward 1. Report progress. Ensure capacity building of Municipal Employees by UNIVEN |  | Progress Reports
LED | Create community beneficiation and empowerment opportunities | Tourism | Tourism Support | 30/06/2013 | 150000 |  | Facilitate LTA meetings and ensure inclusive participation by other community Tourism structures. Coordinate monthly meetings and share information based on Tourism. Database and finalize the TOR/MOU. | Item on the project is approved and a meeting held with University on 21st of August. 2 meetings held with stakeholders in ward 1 on 10th and 21st of September. 13 fieldworkers identified. Awaiting revise process plan and signing of MOU to start with trainings. | Facilitate LTA meetings and ensure inclusive participation by other community Tourism structures. Coordinate monthly meetings and share information based on Tourism. | A workshop on Tourism Signage was held on the 30/11/2012. | Facilitate LTA meetings and ensure inclusive participation by other community Tourism structures. Coordinate monthly meetings and share information based on Tourism. | Facilitate LTA meetings and ensure inclusive participation by other community Tourism structures. Coordinate monthly meetings and share information based on Tourism. |  | Monthly reports Minutes & agendas Database of tourism stakeholders/beneficiaries
LED | Create community beneficiation and empowerment opportunities | Tourism | Tourism Events | 30/06/2013 | 270000 |  | Co-ordinate tourism activities as per annual calendar and in conjunction with business and marketing division Finalisation and adoption of events calendar Letaba Show Springfair. Support Tourism month & Arrive Alive | Held meetings iwth Tzaneen Info Inpreparation for the Letaba Expo. Partnered with LEDET during the Tourism road show. | Co-ordinate tourism activities as per annual calendar and in conjunction with business and marketing division Facilitate Getaway show Tourism month Mohlaba day Tzaneen flea market. Coordinate the funding for the Crisis Centre. Facilitate Tourism route meeting | Getaway show attended 30th August to 3rd September. Muhlaba day held on the 1st of December. | Co-ordinate tourism activities as per annual calendar and in conjunction with business and marketing division Facilitate Arrive alive, Marula festival and 4X4 Rally. Advertise and appoint the service provider to develop the tourism route. | Co-ordinate tourism activities as per annual calendar and in conjunction with business and marketing division Facilitate Indaba, Flea market. Finalis and adopt the developed route |  | Minutes and agendas Tourism Route Marketing plan
LED | Create community beneficiation and empowerment opportunities | Tourism | Tourism Framework | 30/06/2013 | 200000 |  | Draft Tender documentation and follow Supploy Chain processess for the acquisition of a service provider | No progress. | Appointment of a service provider. Monitor progress with the drafting of a framework and report progress | No progress. | Monitor progress with the drafting of a framework and report progress | Monitor progress with the drafting of a framework and report progress. Draft Framework ready for dicussion | GTEDA project | Draft Tourism Framework
LED | Integrated Developmental Planning | Land administration | Development of Portion 11 of Mohlaba's location (Bindzulani) | 30/06/2013 |  |  | Not applicable this quarter | Not applicable this quarter | Re-open negotiations with Limpopo Provincial Department of Public Works, LIMDEV, Cief Moghlaba to develop Bindzulani | No progress yet | n/a | n/a | The investor is in contact with the Chieftain and discussions are underway. | Correspondence document with LIMDEV and Public Works
LED | Integrated Developmental Planning | Land administration | Land administration | 30/06/2013 |  |  | Monitoring and follow up on month-to-month lease agreements | Only one lease agreement renewed | Monitoring and follow up on month-to-month lease agreements | Only one lease agreement signed for Erf 1072 Tzn Ext 12 | Monitoring and follow up on month-to-month lease agreements | Monitoring and follow up on month-to-month lease agreements |  | Correspondence Monthly reports
LED | Integrated Developmental Planning | Land administration | Nkowankowa & Lenyenye land ownership data cleansing | 30/06/2013 | 300000 |  | Confirm beneficiary and ownership of land and houses (pre & post 1994) | 400 registered at Dan Ext 1 150 registered at Lenyenye | Confirm beneficiary and ownership of land and houses (pre & post 1994) | No progress still waiting for remaining erven to be registered | Confirm beneficiary and ownership of land and houses (pre & post 1994) | Confirm beneficiary and ownership of land and houses (pre & post 1994) | Waiting for the remaining erven to be registered | Project Progress reports
LED | Integrated Developmental Planning | Land administration | Transfer of state owned land | 30/06/2013 |  |  | Negotiate with Public Works and LIMDEV and co-Ordinate the transfer of Haenertsburg Town and other state land to Greater Tzaneen Municipality | Matter referred to Housing Development Agency to negotiate on behalf of Greater Tzaneen Municipality | Negotiate with Public Works and LIMDEV and co-Ordinate the transfer of Haenertsburg Town and other state land to Greater Tzaneen Municipality | No transfers done for this quarter | Negotiate with Public Works and LIMDEV and co-Ordinate the transfer of Haenertsburg Town and other state land to Greater Tzaneen Municipality | Negotiate with Public Works and LIMDEV and co-Ordinate the transfer of Haenertsburg Town and other state land to Greater Tzaneen Municipality |  | Correspondence -Minutes of meetings
LED | Integrated Developmental Planning | Township revitalisation | Nkowankowa Central Activity Development initiative (PP6) | 30/06/2013 | 5000000 |  | Monitor progress with implementation of Nkowankowa Central Activity Development Initiative and report to Council | design completed , public participation underway with communitty and business sector | Monitor progress with implementation of Nkowankowa Central Activity Development Initiative and report to Council | Consultants busy, awaiting inputs from public participation. | Monitor progress with implementation of Nkowankowa Central Activity Development Initiative and report to Council | Monitor progress with implementation of Nkowankowa Central Activity Development Initiative and report to Council |  | Minutes Monthly reports
LED | Integrated Developmental Planning | Township revitalisation | Nkowankowa East Integrated (PP8) | 30/06/2013 | 23000000 |  | Monitor progress with PP8 implementation and report to Council | Tender for the construction of the ring Road readvertised and awaitng ajudication | Monitor progress with PP8 implementation and report to Council | tender pending appointment of contractor by Adjudication committee | Monitor progress with PP8 implementation and report to Council | Monitor progress with PP8 implementation and report to Council |  | Minutes and Attendance Registers
LED/ MTOD | Develop high performance culture for a changed, diverse, efficient and effective local government | Employee Performance Management | Performance monitoring & evaluation | 30/06/2013 |  |  | Participate in the Annual Performance Assessment for 2011/12. Ensure that scoresheets are completed in time & POEs are complete | Annual performance assessment has not taken place | Conduct an informal assessment of 1st Quarter Performance of relevant employees in the Department and send report to the MM by 21 October '12 | Annual performance assessment has not taken place | Participate in the mid-year employee performance evaluations for 2012/13. Ensure that scoresheets are completed in time & POEs are complete | Conduct an informal assessment of the 3rd Quarter Performance of relevant employees in the Department and submit report to the MM by 20 April '13 | Pending due to late appointments | 1st & 3rd Qtr Informal Departmental Individual Performance Reports Correspondence
SR/LED | Integrated Developmental Planning | Integrated Development Planning | Demarcation of rural sites | 30/06/2013 |  | COGHSTA | Submit list or requirements to COGHSTA | received general plans of Leollo 1 and Mugwazeni and submitted same to Engineering for their attention. | Monitor submission list for allocation of funds | Submitted to Rural Development for finalization. | Faciliate the process of demarcation with service providers | Submit progress report to Council on the the demarcation process. Hand over of sites to Traditional Authority for allocation |  | Copies of reports Minutes Correspondence General Plans
SR/LED | Integrated Developmental Planning | Integrated Development Planning | Departmental Strategic Sessions and staff development | 30/06/2013 | 30000 |  | Not applicable this quarter | Not applicable this quarter | Conduct Departmental Strategic Session by December | Postponed to May 2013 | not applicable this quarter | Conduct Departmental Strategic Session by 30 June | Alignment purposes with development of 2013/14 scorecards in May 2013 | 2 Strategic Session Reports Resolution register
SR/LED | Integrated Developmental Planning | Integrated Development Planning | IDP implementation monitoring | 30/06/2013 |  |  | Arrange quarterly LED Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | None | Arrange quarterly LED Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | None | Arrange quarterly LED Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | Arrange quarterly LED Thrust meetings. Ensure involvement of relevant Sector Departments and other stakeholders and submit minutes to the MM | A Management decision was taken that an approach on the matter will be finalized. | Stakeholder list Minutes proof of submission to MM
SR/LED | Integrated Developmental Planning | Integrated Development Planning | Partial Cancellation of General plan of Tz Ext 13,15 of Erf 3078 | 30/06/2013 | 50000 |  | Appoint service provider to create a park site | documents at for advertisements to procure service provider. | Submission of application to surveyor general | tender specification submitted to Supply Chain for appointment. | Monitor the approcal of General Plan by Serveyor General | Approcal of General plan | slow process of supply chain | General Plan SG diagram
SR/LED | Integrated Developmental Planning | Integrated Development Planning | Rural Development Strategy | 30/06/2013 |  |  | Appoint service provider for drafting a Rural Development Strategy. Monitor the drafting of a Rural Development Strategy. Ensure that all Departments are actively involved in the drafting of the strategy | Project on hold to be undertaken simuitaneouly with the 2030 Vision document. | Monitor the drafting of a Rural Development Strategy. Ensure that all Departments are actively involved in the drafting of the strategy | Projects not undertaken | Draft Rural Development Strategy Ready by 30 March '13 for public consultation. | Submit Rural Development Strategy to Council for adoption along with the IDP. | no budget provision for the current financial year | Correspondence & public Participation records Rural Development Strategy Council Minutes on Rural Development Strategy
SR/LED | Integrated Developmental Planning | Integrated Development Planning | Rural Nodal Development Plans Bulamahlo (Community Centre) | 30/06/2013 | 500000 |  | Appointment of Service Provider | Township Apllication submitted to Department Of Rural Development for processing. | Appointment of service provider to implement identified project | Draft application submitted to Rural Development , pending adoption. | Draft feasibility study presented to Councillors. Approve Conditions of Establishment | Proclaimed township |  | Township approval
SR/LED | Integrated Developmental Planning | Integrated Development Planning | Socio - Economic survey | 30/06/2013 |  |  | Investigate possible service providers for the Socio - Economic survey. Appoint service provider. Ensure that TOR covers poverty alleviation, indicators of economic growth & indigent management | Council has resolved the partnership between Greater Tzaneen Municipality and Univen on Socio-economic Survey. Univen to sign the MOU for the implementation of the survey in Ward 1. | Monitor the Socio - Economic Survey processes and report progress to Council | Adopted by Council on 4 July 2012- Item B42 | Monitor the Socio - Economic Survey processes and report progress to Council | Submit report to Council on the findings of the Socio - Economic survey |  | Signed SLA Progress Reports Council Item
SR/LED | Integrated Developmental Planning | Integrated Development Planning | Thusong Services | 30/06/2013 | 170000 |  | Visiting Thusong services centres on quarterly basis and marketing department during visits | total of 4 (four ) visits conducted in all Thusong Centres | Visiting Thusong services centres on quarterly basis and marketing department during visits | Seven visits conducted to date | Visiting Thusong services centres on quarterly basis and marketing department during visits | Visiting Thusong services centres on quarterly basis and marketing department during visits |  | Minutes of Departmental Meeting at Thusong Centres
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Digital Camera | 30/06/2013 |  | 10000 | Source quotations | quotations obtained in the process of procuring | Procure digital cameras | Two cameras purchased | Not applicable this quarter | Not applicable this quarter |  | Proof of aquisition
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Formulation of Density Policy (social contribution) | 30/06/2013 | R150 000 |  | Appointment of Service Provider. Report progress of service provider | Resubmiited to for readvertising due to poor responces | Draft Density Policy ready. Report progress of service provider | Pending adverts by supply chain. | Council adoption. Report progress of service provider | Implementation of Policy. Report progress of service provider |  | Council Item Density Policy
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Formulation of Tavern Policy | 30/06/2013 |  |  | Implement Tavern Policy and report number of applications received and approved | Policy adopted by Coucil on the 28.08.2012. | Implement Tavern Policy and report number of applications received and approved | finalised and adopted by Council on the 07th August 2012 | Implement Tavern Policy and report number of applications received and approved | Implement Tavern Policy and report number of applications received and approved |  | Applications Register
SR/LED | Integrated Developmental Planning | Integrated Spatial development | GPS | 30/06/2013 |  | 9000 | Source quotations | Quotations obtained inthe process of procuring | Procure digital cameras | Purchased and registered in the asset register. | Not applicable this quarter | Not applicable this quarter |  | Proof of Purchase
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Implementation of Nkowankowa Local Area Plan (Aquisition of shopping mall site) | 30/06/2013 | R200 000 |  | Negotiation with the Traditional Authorities through the Councillors to releace Bindzulani land for development. Report progress | land for development identified , negotiations with the T.A commenced | Negotiation with the Traditional Authorities through the Councillors to releace Bindzulani land for development. Report progress | Negotiations underway with investor and Chief Mohlaba for land release. | Formation of a partnership for the development of land into a shopping Mall upon release. | Formation of a partnership for the development of land into a shopping Mall upon release. |  | Service level agreement Correspondence
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Metal Detector | 30/06/2013 |  | 5500 | Source quotations | Quotations obtained in the process of procuring | Procure digital cameras | Acquired and registered in our inventory. | Not applicable this quarter | Not applicable this quarter |  | Proof of aquisition
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Monitoring of compliance to town planning scheme | 30/06/2013 |  |  | Issuing of contravention notices, monitoring and recommendation for litigation | o total of 3 (three) contravetion notices issued. | Issuing of contravention notices, monitoring and recommendation for litigation | 5 contraventions issued and two are pending legal action. | Issuing of contravention notices, monitoring and recommendation for litigation | Issuing of contravention notices, monitoring and recommendation for litigation |  | Contravention register Copy of Notices
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Pusela 6 - Township Establishment (former Public Works prefab houses) | 30/06/2013 | 450000 |  | Appointment of Service Provider. Report progress of service provider | Township establishment application submitted by Consultants, currently on circulation to internal Departments. | Report progress of service provider | application pending cluster approval | Report progress of service provider | Implementation of Policy. Designs for land development. Handover to Housing Division to secure funding for Gap-Market houses. Report progress of service provider |  | Proclamation Handover report
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Review of Nodal Plans | 30/06/2013 | 100000 |  | Re-advertisement. Appointment of Service Provider | Resubmited to for readvertising due to poor responces | Draft Nodal plan ready | Documents at supply chain for readers | Council adoption | Proclamation of Nodal Plan |  | Nodal Plan
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Talana (Erf 292 & 293) Township establishment | 30/06/2013 |  | COGHSTA | Negotiate with COGHSTA to establish a township at Talana. Report progress | The housing development agency has appointed a service provider to conduct a feasibility study. 25% | Negotiate with COGHSTA to establish a township at Talana. Report progress | The project is in the pipeline. Projects of COGHSTA programme | Negotiate with COGHSTA to establish a township at Talana. Report progress | Negotiate with COGHSTA to establish a township at Talana. Report progress |  | Correspondence with COGHSTA
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Township establishment - Shiluvane Library | 30/06/2013 |  | 500000 | Appointment of Service Provider. Report progress of service provider | application for land acquisition submitted by consultant to the Deparment of Rural Development. | Report progress of service provider | Draft application pending approval by Rural Department | Report progress of service provider | Implementation of Policy. Report progress of service provider. |  | Township establishment approval
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Tzaneen Ext 89 Township establishment | 30/06/2013 | 240000 | COGHSTA | Negotiate with COGHSTA to establish a township at Talana. Report progress | Awaiting COGHSTA with regards to funding. | Negotiate with COGHSTA to establish a township at Talana. Report progress | Draft feasibility study presented to Councillors. Approve Conditions of Establishment | Negotiate with COGHSTA to establish a township at Talana. Report progress | Negotiate with COGHSTA to establish a township at Talana. Report progress |  | Correspondence with COGHSTA
SR/LED | Integrated Developmental Planning | Integrated Spatial development | Wheel Tape measure | 30/06/2013 |  | 1200 | Source quotations | quotations obtained inthe process of procuring | Procure digital cameras | Purchased and registered in the asset register. | Not applicable this quarter | Not applicable this quarter |  | Proof of aquisition

## Capital Works
CAPITAL WORKS PLAN 2012/13 - 2015/16
WARD | CAPTIAL ITEM | START DATE | END DATE | CAPITAL BUDGET 2012/13 | Projected Expenditure | [5 empty] | Projected Expenditure | [5 empty] | TOTAL EXPENDITURE 2012/2013 | CAPITAL BUDGET 2013/2014 | CAPITAL BUDGET 2014/2015 | Source of Funding
[5 empty] | Jul '12 | Aug '12 | Sep '12 | Oct '12 | Nov '12 | Dec '12 | Jan '13 | Feb '13 | Mar '13 | Apr '13 | May '13 | Jun '13
OWN SOURCE & LOANS
Office of the Municipal Manager
All | Furniture - MM | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
Office of the Chief Financial Officer
All | Furniture -CFO | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | tbd | 0 | 0 | GTM
All | Revenue enhancement | 01/07/2012 | 30/06/2013 | 1000000 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | tbd | 0 | 0 | GTM
Corporate Services Department
All | Mayoral Furniture (Banquet and Entertainment Hall) | 01/07/2012 | 30/06/2013 | 105000 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
All | Task software | 01/07/2012 | 30/06/2013 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
All | Digital Cameras | 01/07/2012 | 30/06/2013 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
All | Municipal Audio System | 01/07/2012 | 30/06/2013 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
All | Municipal Branding Eqiupment | 01/07/2012 | 30/06/2013 | 100000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
All | Public Loud Hailing system | 01/07/2012 | 30/06/2013 | 70000 | 0 | 0 | 0 | 0 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
All | Video cameras | 01/07/2012 | 30/06/2013 | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
All | Records Binding Machine | 01/07/2012 | 30/06/2013 | 60000 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd | 0 | 0 | GTM
Electrical Engineering Department
12 | Capacity to Rainbow Chickens (phase 1) | 01/07/2012 | 30/06/2013 | 1000000 | 0 | 0 | 100000 | 200000 | 200000 | 0 | 0 | 200000 | 200000 | 0 | 100000 | 0 | tbd | 15000000 |  | GTM own funds
13/15 | Electricity Capacity Building in phases | 01/07/2012 | 30/06/2013 | 14000000 | 89340 | 188021 | 171701 | 34340 | 244932 | 244932 | 1496303 | 1800000 | 5000590 | 2077671 | 1609092 | 1043078 | tbd | 18000000 | 7300000 | GTM own funds
All Wards | Auto Reclosers | 01/07/2012 | 30/06/2013 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 150000 | 150000 | 200000 | tbd | 1500000 | 1650000 | GTM
All Wards | Capital Tools (Outlying) | 01/07/2012 | 30/06/2013 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | tbd | 300000 | 400000 | GTM
All Wards | Capital Tools (Town) | 01/07/2012 | 30/06/2013 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | 41666.6667 | tbd | 180000 | 300000 | GTM
All Wards | Electricity network upgrading | 01/07/2012 | 30/06/2013 | 5000000 | 0 | 0 | 300000 | 300000 | 600000 | 300000 | 300000 | 300000 | 300000 | 800000 | 800000 | 1000000 | tbd |  |  | GTM
All wards | Rebuilding of Lines | 01/07/2012 | 30/06/2013 | 3000000 | 0 | 0 | 200000 | 0 | 200000 | 500000 | 300000 | 400000 | 400000 | 400000 | 400000 | 200000 | tbd |  |  | GTM
14, 15, 16 | Upgrading Tzaneen Town network including cables | 01/07/2012 | 30/06/2013 | 2,000,000 (carried over) | 0 | 0 | 0 | 1000000 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
15 | 33kv Sub Agatha | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 3000000
13 | 66 kv Tarentaalrand to Tzaneen | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd |  | 16000000
tbd | Strategic Lights | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 200000 | 220000 | GTM
tbd | Streetlights (25) | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 240000 | 260000 | GTM
13 | Tarentaalrand 60MVA Transformer | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd |  | 15000000 | GTM
14, 15, 16 | Transformers Tzaneen Main Sub | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 10000 |  | GTM
5, 13, 14, 15, 16, 19, 23 | Installation of Fire wall protection | 01/07/2012 | 30/06/2013 | none | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 750000 | 900000 | GTM
13, 14, 15 | Protection Equipment | 01/07/2012 | 30/06/2013 | none | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 800000 | 880000 | GTM
14, 15, 16 | Replace LT cables | 01/07/2012 | 30/06/2013 | none | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 200000 | 220000 | GTM
Enigneering Services Department
31 | Lenyenye new cemetery tar road | 01/07/2012 | 30/06/2013 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 160000 | 640000 | 1000000 | tbd | 2000000 |  | GTM
22/25 | Mafarana to Sedan Tar (6km) | 01/07/2012 | 30/06/2013 | 10500000 | 749999 | 749999 | 749999 | 749999 | 1000000 | 1000000 | 1000000 | 1000000 | 874999 | 874999 | 874999 | 875007 | tbd | 16728000 |  | GTM & MIG
8 | Khwekhwe Low level bridge | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 60000 | 80000 |  | 90000 | 90000 | 90000 | 90000 | tbd |  |  | GTM
2 | Mawa Block 12 Low level bridge | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 60000 | 80000 |  | 90000 | 90000 | 90000 | 90000 | tbd |  |  | GTM
32 | Mokonyane low level bridge | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 60000 | 80000 |  | 90000 | 90000 | 90000 | 90000 | tbd |  |  | GTM
4 | Rikhotso low level bridge | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 60000 | 80000 |  | 90000 | 90000 | 90000 | 90000 | tbd |  |  | GTM
2 & 3 | Ramotshinyadi to Mokhwati Tar road (Phase 2)(3.5km) | 01/07/2012 | 30/06/2013 | 12751569 | 2758096 | 2758096 | 2758096 | 1492425 | 1492425 | 1492431 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM & MIG
21/24 | Sasekani to Nkowankowa Tar road (Phase 2) | 01/07/2012 | 30/06/2013 | 8473559 | 2824519 | 2824519 | 2824521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM & MIG
1 | Senakwe to Maropalala Tar (Phase 2) | 01/07/2012 | 30/06/2013 | 31285000 | 2607083 | 2607083 | 2607083 | 2607083 | 2607083 | 2607083 | 2607083 | 2607083 | 2607084 | 2607084 | 2607084 | 2607084 | tbd |  |  | GTM & MIG
All | Speed humps | 01/07/2012 | 30/06/2013 | 2200000 | 0 | 0 | 0 | 244444.4444 | 244444.4444 | 244444.4444 | 244444.4444 | 244444.4444 | 244444.4444 | 244444.4444 | 244444.4444 | 244444.4444 | tbd |  |  | GTM
7&11 | Thapane to Moruji Tar | 01/07/2012 | 30/06/2013 | 11144700 | 928725 | 928725 | 928725 | 928725 | 928725 | 928725 | 928725 | 928725 | 928725 | 928725 | 928725 | 928725 | tbd | 40890300 |  | GTM & MIG
Civic Centre | Additional Office space | 01/07/2012 | 30/06/2013 | 3000000 | 0 | 0 | 500000 | 500000 | 250000 | 0 | 500000 | 0 | 500000 | 500000 | 250000 | 0 | tbd |  |  | GTM
Civic Centre | Replaceing Aircon and furniture in Engineering Department | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 100000 | 100000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
All | Capital Equipment | 01/07/2012 | 30/06/2013 | 150000 | 0 | 0 | 0 | 50000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd
15 | Tzaneen Airfield Fencing | 01/07/2012 | 30/06/2013 | 650000 | 0 | 0 | 0 | 0 | 0 | 100000 | 200000 | 200000 | 100000 | 50000 | 0 | 0 | tbd | 1000000 |  | GTM
15 | Refursbishment of Tzaneen Airfield Runway | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd |  |  | GTM
| Upgrading and expansion of public toilets (ablution facilities) | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 2000000 | 1650000 | GTM
All | Vehicle replacement - waste management | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 3000000 |  | GTM
2 & 3 | Ramotshinyadi Bridge | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 18250000 |  | GTM & MIG
15 | Refurbishment of streets - Haenertsburg | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 2000000 |  | GTM
31 | Refurbishment of streets - Lenyenye | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 2000000 |  | GTM
23 | Refurbishment of streets - Letsitele | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 2000000 |  | GTM
19/21 | Refurbishment of streets - Nkowankowa | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 2000000 |  | GTM
15 | Refurbishment of streets - Tzaneen Town | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 2000000 |  | GTM
Community Services Department
8 & 27 | Construct and establish new libraries (Shiluvani Library) | 01/07/2012 | 30/06/2013 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | tbd |  |  | GTM
ALL | Waste Management mass containers - 10mx6m³ | 01/07/2012 | 30/06/2013 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | tbd |  |  | GTM
16 | Expansion of storeroom at Nkowankowa DLTC | 01/07/2012 | 30/06/2013 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
16 | Furniture - Tzaneen DLTC | 01/07/2012 | 30/06/2013 | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
16 | Agatha Cemetery Environmental Impact Assessment | 01/07/2012 | 30/06/2013 | 100000 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | tbd |  |  | GTM
23 | Hawkers Esplanade - Letsitele | 01/07/2012 | 30/06/2013 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 35000 | tbd |  |  | GTM
23/14/15 | Furniture for Letsitle, Haenertsburg and Tzaneen Libraries | 01/07/2012 | 30/06/2013 | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
31 | New Registration Authority and Drivers Licence Testing Centre at Lenyenye | 01/07/2012 | 30/06/2013 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | tbd | 6000000 | 100000 | Dpt Road and Transport & GTM
Planning and Economic Development
All | Acquisition of land parcels for development | 01/07/2012 | 30/06/2013 | 364300 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 314300 | tbd | 1500000 |  | GTM
ALL | Furniture for PED offices | 01/07/2012 | 30/06/2013 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd
19/20/21 | Archiving (Filing) for PED | 01/07/2012 | 30/06/2013 | 60000 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
ALL | Digital Camera | 01/07/2012 | 30/06/2013 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
ALL | GPS | 01/07/2012 | 30/06/2013 | 9000 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
ALL | Metal Detector | 01/07/2012 | 30/06/2013 | 5500 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
27 | Township establishment - Shiluvane Library | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | tbd
ALL | Wheel Tape measure | 01/07/2012 | 30/06/2013 | 1200 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | GTM
All | Rural Broadband connectivity (PP4) | 01/07/2012 | 30/06/2013 | 5000000 | 0 | 0 | 2666000 | 0 | 0 | 2334000 | 0 | 0 | 0 | 0 | 0 | 0 | tbd |  |  | NDPG
Total |  |  |  | 119154828

## Capital Expenditure
ACTUAL CAPITAL EXPENDITURE 2012/13
WARD | CAPTIAL ITEM | START DATE | END DATE | CAPITAL BUDGET 2012/13 | Actual Expenditure | [5 empty] | Actual Expenditure | [5 empty] | TOTAL EXPENDITURE 2012/2013 | Source of Funding
[5 empty] | Jul '12 | Aug '12 | Sep '12 | Oct '12 | Nov '12 | Dec '12 | Jan '13 | Feb '13 | Mar '13 | Apr '13 | May '13 | Jun '13
OWN SOURCE & LOANS
Office of the Municipal Manager
All | Furniture - MM | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
Office of the Chief Financial Officer
All | Furniture -CFO | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All | Revenue enhancement | 01/07/2012 | 30/06/2013 | 1000000 | 0 | 0 | 0 | 0 | 10510.87 | 0 | [6 empty] | 10510.87 | GTM
Corporate Services Department
All | Mayoral Furniture (Banquet and Entertainment Hall) | 01/07/2012 | 30/06/2013 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All | Task software | 01/07/2012 | 30/06/2013 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All | Digital Cameras | 01/07/2012 | 30/06/2013 | 15000 | 6000 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 6000 | GTM
All | Municipal Audio System | 01/07/2012 | 30/06/2013 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All | Municipal Branding Eqiupment | 01/07/2012 | 30/06/2013 | 100000 | 2000 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2000 | GTM
All | Public Loud Hailing system | 01/07/2012 | 30/06/2013 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All | Video cameras | 01/07/2012 | 30/06/2013 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All | Records Binding Machine | 01/07/2012 | 30/06/2013 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
Electrical Engineering Department
12 | Capacity to Rainbow Chickens (phase 1) | 01/07/2012 | 30/06/2013 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM own funds
13/15 | Electricity Capacity Building in phases | 01/07/2012 | 30/06/2013 | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM own funds
All Wards | Auto Reclosers | 01/07/2012 | 30/06/2013 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All Wards | Capital Tools (Outlying) | 01/07/2012 | 30/06/2013 | 250000 | 0 | 0 | 17231.62 | 0 | 0 | 36165.59 | [6 empty] | 53397.21 | GTM
All Wards | Capital Tools (Town) | 01/07/2012 | 30/06/2013 | 250000 | 0 | 0 | 0 | 0 | 0 | 21971 | [6 empty] | 21971 | GTM
All Wards | Electricity network upgrading | 01/07/2012 | 30/06/2013 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All wards | Rebuilding of Lines | 01/07/2012 | 30/06/2013 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
14, 15, 16 | Upgrading Tzaneen Town network including cables | 01/07/2012 | 30/06/2013 | 2,000,000 (carried over) | 0 | 0 | 20781.56 | 13950 | 304992.4 | 291912.74 | [6 empty] | 631636.7 | GTM
Enigneering Services Department
31 | Lenyenye new cemetery tar road | 01/07/2012 | 30/06/2013 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
22/25 | Mafarana to Sedan Tar (6km) | 01/07/2012 | 30/06/2013 | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM & MIG
8 | Khwekhwe Low level bridge | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
2 | Mawa Block 12 Low level bridge | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
32 | Mokonyane low level bridge | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
4 | Rikhotso low level bridge | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
2 & 3 | Ramotshinyadi to Mokhwati Tar road (Phase 2)(3.5km) | 01/07/2012 | 30/06/2013 | 12751569 | 2444666.44 | 0 | 1795272 | 4349661.63 | 1733107.24 | 0 | [6 empty] | 10322707.31 | GTM & MIG
21/24 | Sasekani to Nkowankowa Tar road (Phase 2) | 01/07/2012 | 30/06/2013 | 8473559 | 0 | 0 | 1764635.27 | 0 | 0 | 0 | [6 empty] | 1764635.27 | GTM & MIG
1 | Senakwe to Maropalala Tar (Phase 2) | 01/07/2012 | 30/06/2013 | 31285000 | 0 | 0 | 0 | 224869.77 | 0 | 0 | [6 empty] | 224869.77 | GTM & MIG
All | Speed humps | 01/07/2012 | 30/06/2013 | 2200000 |  |  |  | 0 | 0 | 0 | [6 empty] | 0 | GTM
7&11 | Thapane to Moruji Tar | 01/07/2012 | 30/06/2013 | 11144700 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM & MIG
Civic Centre | Additional Office space | 01/07/2012 | 30/06/2013 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
Civic Centre | Replaceing Aircon and furniture in Engineering Department | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
All | Capital Equipment | 01/07/2012 | 30/06/2013 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
15 | Tzaneen Airfield Fencing | 01/07/2012 | 30/06/2013 | 650000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
Community Services Department
8 & 27 | Construct and establish new libraries (Shiluvani Library) | 01/07/2012 | 30/06/2013 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
ALL | Waste Management mass containers - 10mx6m³ | 01/07/2012 | 30/06/2013 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
16 | Expansion of storeroom at Nkowankowa DLTC | 01/07/2012 | 30/06/2013 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
16 | Furniture - Tzaneen DLTC | 01/07/2012 | 30/06/2013 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
16 | Agatha Cemetery Environmental Impact Assessment | 01/07/2012 | 30/06/2013 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
23 | Hawkers Esplanade - Letsitele | 01/07/2012 | 30/06/2013 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
23/14/15 | Furniture for Letsitle, Haenertsburg and Tzaneen Libraries | 01/07/2012 | 30/06/2013 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
Planning and Economic Development
All | Acquisition of land parcels for development | 01/07/2012 | 30/06/2013 | 364300 | 0 | 0 | 40000 | 0 | 0 | 0 | [6 empty] | 40000 | GTM
ALL | Furniture for PED offices | 01/07/2012 | 30/06/2013 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
19/20/21 | Archiving (Filing) for PED | 01/07/2012 | 30/06/2013 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | GTM
ALL | Digital Camera | 01/07/2012 | 30/06/2013 | 10000 | 0 | 0 | 4500 | 0 | 0 | 0 | [6 empty] | 4500 | GTM
ALL | GPS | 01/07/2012 | 30/06/2013 | 9000 | 0 | 0 | 3000 | 0 | 0 | 0 | [6 empty] | 3000 | GTM
ALL | Metal Detector | 01/07/2012 | 30/06/2013 | 5500 | 0 | 0 | 1500 | 0 | 0 | 0 | [6 empty] | 1500 | GTM
27 | Township establishment - Shiluvane Library | 01/07/2012 | 30/06/2013 | 500000 | 0 | 0 | 147000 | 0 | 0 | 0 | [6 empty] | 147000
ALL | Wheel Tape measure | 01/07/2012 | 30/06/2013 | 1200 | 0 | 0 | 600 | 0 | 0 | 0 | [6 empty] | 600 | GTM
All | Rural Broadband connectivity (PP4) | 01/07/2012 | 30/06/2013 | 5000000 | 0 | 238000 | 0 | 0 | 0 | 2814356 | [6 empty] | 3052356 | NDPG
Total |  |  |  | 119154828 | [12 empty] | 16286684.13

## Risk Management
Top 10 Risks identified for 2012/13
Number | Link to objective | Risk description | Background to the risk | Impact | Likelihood | Inherent risk | Current controls | Perceived control effectiveness | Residual risk | Risk owner | Actions to improve management of the risk | Action owner | Time scale
18 | Optimise infrastructure services | Dangerous encroaching of vegetation into the power lines | Insuffient human resource to clear underlines | Critical (5) | Common (5) | Maximum (25) | currently in sourcing | Unsatisfactory (0.9) | Maximum (22.5) | Directors: Electrical | Optimizing limited human resource available Encourage partnership with private land owner Implementation of EPWP | Manager: Outlying | Quarterly Quarterly March 2013
25 | Improve access to sustainable and affordable services | Poor provision of water services | Non compliance to water service agreement by WSA | Critical (5) | Common (5) | Maximum (25) | water service agreement | Unsatisfactory (0.9) | Maximum (22.5) | MM | Escalate non compliance of the agreement to IGR | Director: Engineering services. | Quaterly
29 | To Improve access to sustainable and affordable services | High accidents | Speeding;unmarked crossing,missing road signs and theft of fences,driving under the influence of alcohol and un roadworthy vehicles | Critical (5) | Common (5) | Maximum (25) | Speed trap cameras and roadblocks | Unsatisfactory (0.9) | Maximum (22.5) | MM | Reporting on vandalised fences to RAL Regular roadblocks Replacement of road signs | C.S.D.-TRAFFIC | 31 November Bi-monthly April 2013
32 | Promote environmental sound practices and social development | Lack of road signs in rural areas | Lack of prioritazation road sign projects | Critical (5) | Common (5) | Maximum (25) | Scholar Patrol | Unsatisfactory (0.9) | Maximum (22.5) | MM | Prioritazation of roads sign projects Registration of EPWP projects on traffic control | C.S.D.-TRAFFIC | March 2013 March 2013
33 | Promote environmental sound practices and social development | Inadequate maintenance of municpal parks | Increased number of developed parks. Insufficient personnel | Critical (5) | Common (5) | Maximum (25) | Rotation of staff. | Unsatisfactory (0.9) | Maximum (22.5) | C.S.D. | INSTITUTIONALIZATION // ORGANOGRAM Extend the current contract of parks Implementation of EPWP projects | MANAGER PARKS | May 2013 Dec 2012 March 2013
39 | Improve access to sustainable and affordable services | Lack of cemetries (burial space) at Lenyenye Nkowankowa & Agatha cemetires | Unavailability of land | Critical (5) | Common (5) | Maximum (25) | Communication with PED for land. | Unsatisfactory (0.9) | Maximum (22.5) | C.S.D. | Development of regional burial sites. Encourage families for stacking burial, cremations and do EIA | MANAGER PARKS | 4/30/2013 Annually
50 | Effective and Efficient administration | New Connection | New applications not captured in the billing system | Critical (5) | Common (5) | Maximum (25) | Follow up of procedures and verification of new connection implementation of new connection with technical department | Unsatisfactory (0.9) | Maximum (22.5) | MM | To ensure that all the systems are in place and implemented | CFO MANGER REVENUE | 31.12.2012
51 | Effective and Efficient administration | Delays in procurement process | Poor adherence to the procurement quarterly targets in the SDBIP | Critical (5) | Common (5) | Maximum (25) | Constant correspondence with the procurement unit. IMPLENETATION OF REGISTERs TO FOLLOW TIME FRAMES | Unsatisfactory (0.9) | Maximum (22.5) | MM | Intervention strategy and training | Manager:Supply Chain Management and CFO and MM and RELEVANT DE[ARTMENT | 31.12.2012
54 | Effective and Efficient administration | Immovable assets | Asset without physical location and Asset not recorded on the fixed asset register | Critical (5) | Common (5) | Maximum (25) | Interin audit on the asset register | Satisfactory (0.65) | Maximum (22.5) | MM | Updating asset register | CFO | On going
57 | Effective and Efficient administration | Insufficient capacity to audit performance information | Increased focus of AG on performance Audit | Critical (5) | Common (5) | Maximum (25) | None | Unsatisfactory (0.9) | Maximum (22.5) | MM | Training of internal audit staff on audit of performance information | MM | 31/01/2013