## STRATEGIC RISKS 2023 2024 FY (hidden)
No | Link to objective |  | Link Objectives | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | Rating | Current controls | Perceived control effectiveness | Rating | Residual risk | RRR | Risk owner | Actions to improve management of the risk | Means of verification | Action owner | QRT 1 | QRT 2 | QRT 3 | QRT 4 | Budget
|  | 1 | Efficient and effective administration | Good governance | Agency not established in line with MFMA Sec 84 as a municipal entity subsection 1 (a) and (b) | 1. The mandate of the entity is not transferred which poses a threat to the entity’s going concern.. 2. No collaboration between the entity and LED-PED 3. Registration of Tax liabilities( removed) | Duplications of functions between PED (LED) and Gteda (municipal entity) | Critical | 5 | Common | 5 | High | 25 | SLA betweeen GTM and GTEDA Draft report on the legal status of the agency | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1&2.Continue to advice the municipal council ro comply in terms of MFMA Section 84 subsec 1(a) and (b) 2. Appoint CEO ( removed) 3. Request Treasury to advise on the step by step process of regularising the municipal entity( removed) 3.The parent municipality must write the letter to the entity to agree on the tax liabilities.( removed) 4. The entity to apply for tax exemption from SARS upon receipt of the letter from the parent municipality.( removed) | 1. Minutes of meeting between GTM and GTEDA 2. Appointment letter of CEO( removed) 3. Feedback from treasury( removed) 4. Letter fom municipality to entity costituting the municipal stand-point with regard to tax liability( removed) 5. Approval from SARS partaining to tax exemption( removed) | Director PED and CEO GTEDA | 1&2 Feedback From COGHSTA(Report) |  |  |  | R0.00
1 | Efficient and Effective administration | 2 | Efficient and effective administration | Good governance | 1. Excessive Overtime hours | 1.Excessive payments done beyond what is indicated in the overtime policy as approved by Council. 2.Non implementation of overtime ministerial threshold (R241 110.59 - 1 March 2023) ( removed) 3.Non-compliance with the overtime guiding tool.( removed) | Audit findings, Health of the affected officials due to possible fatigue Abuse of overtime Litigation Possible financial Loss Negative impact on service delivery | Critical | 5 | Common | 5 | High | 25 | Approved overtime policy, Overtime guiding tool Basic Conditions of Employment Act, Internal Circular on Pre -Approvals of overtime Gazzette about the ministerial threshold | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Monitoring of overtime trends in respective departments. 1b.Ensure departments limit overtime hours and align them to what has been prescibed as per the overtime policy 2.Seek clarity from department of labour to assist with the clarification of law on the interpretation of law of the overtime threshold( removed) 2.Ensure the implementation of overtime Ministerial threshhold by monitoring pre approval of overtime( proposal) 3.Reviewal of the overtime policy and send it to council for approval and amend the overtime guiding tool ( removed) | Council resolution, Management minutes on Reviewed overtime tool, Quarterly Council Resolution for approval of overtime above threshold. Letter and response from the Department of Labour for clarity seeking. | Directors | 1.Quarterly overtime monitoring report 1b.Overtime monitoring Report 2. Letter to the Department of Labour for clarity seeking. ( removed) | 1.Quarterly overtime monitoring report 1b. Pre-Approvals , Emergency Memorandums. 3.Management minutes on Reviewed overtime tool( removed) | 1.Quarterly overtime monitoring report 1b.Pre-Approvals , Emergency Memorandums | 1.Quarterly overtime monitoring report 1b.Pre-Approvals , Emergency Memorandums | R0.00
|  | 3 | Optimise and sustain infrastructure investment and services | Service Delivery | Aging infrastructure | 1.Inadequate implementation of maintenance plans and (outdated)Master Plans 2. Insufficient mantainance budget | Poor delivery of services Public protest High costs of maintenance & replacements | Critical | 5 | Common | 5 | High | 25 | Infrastucture Maintenance plan Electrical Master Plans Monthly Inspection report Outage and Mantainance Report | Weak | 0.8 | High | 20 | Accounting Officer | 1.Ensure the implentation of the maintenance plans and Master Plans and perform reactive maintenance as and when required. 1b. Advocate for the appointment of a service provider to review the Master plans. 2.Advocate for Budget increase at the end of the financial year | Quarterly inspections report | 1&2.Directors: Electrical Services. Director Engineering Services | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports and Approved master plans 1b. Internal Memo(budget increase) 2. Approved IDP | R0.00
2 | Optimize and sustain infrastructure investment and services | 4 | Improve access to sustainable and affordable services | Service Delivery | Non adherence of the service level agreement between Water Service Authority ( Mopani District Municipality) and Water Service Provider (Greater Tzaneen Municipality) | 1.Lepele is invoicing GTM for bulk purchases of which is the responsibility of the WSA according to the agreement.( bill not being paid) | Financial loss, GTM incurring the costs of maintenance of infrastructure on behalf of the MDM cash flow constraints Poor service delivery Community Protests | Critical | 5 | Common | 5 | High | 25 | IGR meetings about the SLA between MDM & GTM (Water service authority & Water service provider) Continuos meetings between GTM and MDM, service level agreement | weak | 0.8 | High | 20 | Accounting Officer | Conduct meetings with Lepele, MDM and GTM(Bill settlent). | Progress reports on the implementation of the SLA, | Director: Civil Engineering Services | attendance register and minutes | attendance register and minutes | attendance register and minutes | attendance register and minutes | R0.00
4 | Efficient and Effective administration | 5 | Efficient and effective administration | Good governance | Fraud and corruption - (abuse of municipal vehicles, abuse of fuel, abuse of overtime) | 1.Weak systems of control, 2.manipulation of internal controls, 3.unethical behaviour, | Audit findings; Financial loss, Reputational damage, | Critical | 5 | Common | 5 | High | 25 | awareness to all staff and municipal stakeholders, Approved policies: anti-fraud and corruption, Whistle blowing, fraud prevention plan Anti-corruption hotline Fraud risk register has been developed, Anti-corruption strategy | saisfactory | 0.65 | High | 16.25 | MM | 1-3. Continue to conduct/ raise Awareness on fraud , ethics and corruption. | Investigation report (if any), attendance regsiter for attendance of the workshop, request send to Communications and Marketing about the anti-corruption messages) | CRO | 1-3. Attendance register/communique sent on awareness |  | 1-3. Attendance register/communique sent on awareness |  | R0.00
5 | Efficient and Effective administration | 6 | Efficient and effective administration | Good governance | Non adherence with the reporting format in the Electronic Performance management System. | 1.Inaccurate performance management reporting(Actuals reported and PoEs submmitted/ attached not addressing KPIs (not aligned with reported information) | Audit findings, Lack of credible reports Misalignment of information | Critical | 5 | Common | 5 | High | 25 | Quarterly performance report, APR, SDBIP, Internal Audit reports on performance of information Refresher trainings/workshops | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Continue to conduct refresher trainings/workshops as and well required. | Quarterly SDBIP report | Directors | 1. Attendance register( confirm Quarterly POE) | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | R0.00
To be reviewed by the Risk Office |  | 7 | Efficient and effective administration | Good governance | 1% of personnel budget not fully allocated as per the requirements of Skills Development Act [SDA] | 1.Insufficient training budget on all functions of compliance | Low staff morale, incompetences, Fines & penalties, | Critical | 5 | Common | 5 | High | 25 | WSP, Training plans, | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Accept the risk | Signed Budget Council Resolution. | CFO Director Corporate Services | Continuos training | Continuos training | Continuos training | 1. Approved budget by Council.( confirm POE) | R0.00
6 | Improve access to affordable basic services | 8 | Improve access to sustainable and affordable services | service delivery | Increasing theft and loss of infrastructure | 1.Social issues in the country (unemployment, loadshedding) 2.Absence of security at certain areas. 3.Non-adherence with asset management policy 4.Negligence and lack of safeguarding of municipal assets(loss through theft) | Financial loss, Loss of critical information/data, audit findings, Inconsistent security checks, | Critical |  |  |  |  | 25 | security guards, cameras, security technology penalties imposed equivalent to the cost of the item, community policing forums | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Ensure establishment of community policing forums . 1b.Conduct awareness workshops to address social crimes with the comminities 2.Identify and list all Municipal assests to be safeguarged. 3.Inform council about the stolen and replaced assests. 4..Conduct awareness workshops to address negligence and lack of safeguarding of municipal assets | Number of SAPS cases partaning reported cases | Director Comminity Services. | 1. Quartely Report | 1. Quartely Report 1b.Invitation and Attendance Registers 2.Report(Municipal Assets and Municipal Assets location) 4.Invitation and Attendance Registers | 1. Quartely Report | 1. Quartely Report 1b.Invitation and Attendance Registers 3. Council Resolution 4.Invitation and Attendance Registers | R0.00
7 | Efficient and Effective administration | 9 | Efficient and effective administration | Good governance | Non-compliance with SCM policy and regulations. | 1. Lack of forward planning 2. Non-adherence to SCM policy and regulations | Increasing irregular expenditures law suits, unjustified deviations audit findings | Critical |  |  |  |  | 25 | Deviation register, Approved memo for deviation SCM policy and regulations MFMA circulars | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Ensure adherence to proper forward planning procedures by relevant stakeholders. 2.Training of the bid committee members and SCM officials, 2b. Ensure that the approved written deviations are inline with the SCM Policy. | Training plan, attendance register of the bid committee training, approved written quotations | CFO | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report 2. Agenda and attendance Registers. | R0.00
|  | 10 | Increase Financial Viability | Revenue Collection | Low collection of revenue collection at the municipal townships (Nkowankowa, Lenyenye) | 1. Credit control of Business properties in the townships on water availability. Restriction of water availability to residential properties. 2. Non provision of services in particular roads, sidewalk library etc. non complaince to national building regulations.(To be removed) | Financial loss | Critical |  |  |  |  | 25 | Credit control policy, Debt collection policy, revenue enhancement strategy, Indigent register maintained annually Approved building Plans. National Building Regulations. | weak | 0.8 | High | 20 | Accounting Officer | 1.Implement credit control and debt collection policies. 1b.Improved communication with the communities. 2. Ensure visibility of building inspectors..(To be removed) | Means of communications to the communities, Quarterly reports on the implementation of credit control and debt collection. | 1.CFO 1b. Director Corporate Services. 2. Director Engineering | 1.Quarterly reports on the implementation of credit control and debt collection actions 1b.Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | R0.00
3 | To promote corporate governance excellence | Good governance | Non-compliance with MSA (individual performance management not cascaded to all officials) | Ineffective implementation of performance management system | Audit findings, Poor performance management | [6 empty] | Approved disaster Relief policy; Disaster Management Plan District risk assessment
Note on U2: C Stanley: Consider Linking Actions to improve management of risk with Root Causes
Note on W2: C Stanley: Consider mapping Action owners with Action Plans
Note on X2: C Stanley: Are these quarterly milestones, how should we treat them on the system? There is also need to map the milestones with the action plans

## STRATEGIC RISKS 2026 2027 FY
NO | Risk description | Background to the risk/Risk Root Cause | Impact | Rating | Likelihood | Rating | Inherent risk | IRR | Current controls | Perceived control effectiveness | Rating | Residual risk | RRR | Risk owner | Actions to improve management of the risk | Action timeline | Action owner | POE
1. | Excessive hours of overtime | 1. Organisational structure no longer fit for purpose. 2. Operating hours are not aligned with the nature of trading services | Critical | 5 | Common | 5 | High | 25 | 1. Approved overtime policy, 2. Basic Conditions of Employment Act, 3. Internal Circular on Pre -Approvals of overtime 4. Collective agreement 5. conditions of employment with new appointment | Weak | 0.8 | High | 20 | Accounting Officer | 1. To implement shift system strategies to reduce overtime claims. 2. Review organisational structure 3. Research study by legal office 4. Introduce 6/7-day operational arrangements | 1a) Quarter 2 and Quarter 4 1b) Quarterly 1c)Quarterly | Director Corporate Services
2. | Aging infrastructure (Roads, Buildings, Electrical) [aged to a point where to replace will be costly to the municipality]. | Electrical Poor electrical infrastructure maintenance plans. Civil Insuficient resources | Critical | 4 | Common | 5 | High | 20 | 1. Infrastucture Maintenance plan 2. Existing Electrical and Roads Master Plans 3. Monthly Inspection report 4. Outage and Maintenance Report 5. Pool of service providers for maintenance. | satisfactory | 0.65 | Medium | 13 | Accounting Officer | Electrical: 1. Implementation of the maintenance plans (Re-active and pro-active maintenance) 2. Conduct audit of the current infrastructure 2026/2027 3. Ensure the procurement of the software to assist in managing the maintenance of infrastructure-2026/2027 Civil: 4. Ensure the reviewal of the Roads Master Plan in 2026/2027-civil | 1a)Quarterly 1b) Quarter 3 2a)Quarter 2 2b) Quarter 4 | Directors: Civil Engineering and Electrical
3 | Inadequate implementation of SLA of WSA/WSP | No adequate coordination between MDM/GTM. No reimbursement of water services costs | Critical | 5 | Common | 5 | High | 25 | 1. IGR meetings 2. Service level agreement 3. Monthly invoices to WSA 4. Meetings between the 5. WSA (water service authority( and WSP (water service provider) | Weak | 0.8 | High | 20 | Accounting Officer | Establish the committee meetings Engage WSA to prioritise water services infrasture during budget processes Review SLA conditions | Quarter 1 Quarterly | Directors: Civil Engineering CFO
4 | Fraud and corruption occuring at the municipality | 1.Weak systems of control, 2.manipulation of internal controls, 3.unethical behaviour, | Critical | 5 | Common | 5 | High | 25 | 1. awareness to all staff and municipal stakeholders, 2. Approved policies: anti-fraud and corruption, Whistle blowing, fraud prevention plan 3. Anti-corruption hotline 4. Anti-corruption strategy | saisfactory | 0.65 | High | 16.25 | Accounting Officer | 1&3)Conduct continuous awareness on fraud and corruption through various platforms 2)Investigate and refer cases reported on the anti-corruption hotline. | 1&3) Quarterly 2)Bi- Annually(Q2&4) | Manager: Risk and Compliance
5 | Increasing theft of infrastructure | 1.Social challenges in the country (unemployment,poverty) 2.Inadequate safeguarding of municipal assets | Critical | 5 | Common | 5 | High | 25 | 1. Surveillance cameras 2. Physical security 3. Bio-metrics 4. CPF Forum | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1.Escalate cases to SAPS 2. Community crime awareness quarterly with SAPS under GTM jurisdiction of the area on copper theft during the customer forums (both Safety & Security and Electrical) 3.Conduct awareness workshops on proper safeguarding of municipal assets. 4. Implement access control systems that can significanty reduce unauthorised access. | 1a) Quarterly 1b) Quarter 3 1c)Quarter 4 2a) Quarterly 2b)Quarterly | 1a& b and all on number 2 )Director: Community Services 1c)CFO
6 | Slow economic growth in the area of GTM (national challenge) | Inadequate implementation of LED strategy Inadequate prioritisation of economic infrstructure through budgeting process Inadequate implementation of SDF | Critical | 5 | Common | 5 | High | 25 | 1. Incentive policy 2. LED strategy 3. SMME support strategy 4. Spatial Development Framework | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Implement the projects in the LED strategy 2. Implementation of SDF 3. Approval of tourism strategy (developed by the service provider) 4. Prioritisation of economic infrastructure projects in the budget & IDP | Quarterly Quarter 2 and Quarter 4 Quarter 2 and Quarter 4 | Director PED
7 | Community protests | Inadequate delivery of services Political instability Inadequate community feedback | Critical | 5 | Common | 4 | High | 20 | 1. Rapid response team 2. IDP rep forum 3. Councillors feedback 4. PP IDP/Budget consultation 5. Mayoral Imbizo 6. Energy forums 7. Water and sanitation 8. MPAC public hearing 9. Customer call centre | Satisfactory | 0.65 | Medium | 13 | Accounting Officer | Prioritize the concerns from the communities | Quarterly | Director Corporate Services
8 | Inadequate revenue generation | 1,Revenue concentration (high dependence on two revenue sources) 2, Limited revenue streams 3, Underdeveloped land/ under-utilised land 4, Poor revenue collection in townships 5, Revenue leakage | Critical | 4 | Common | 4 | High | 16 | 1. Debt collection and credit control policy 2. Revenue enhancement strategy 3. Revenue enhancement steering committee meetings 4. Automated meter reading | Satisfactory | 0.65 | Medium | 10.4 | Accounting Officer | 1)Review revenue enhancement strategy(RES) 2)Establishment of RES task team to engage on economic growth and generation 3)Conduct Customer education and awareness campaign 4)Collaborate with PED on under-utilized land for income generation (spatial referencing) 5) Monitoring pre-paid buyers 6) Meter auditing 7) Data cleansing | Quarter 4 Quarterly Quarterly Quarter 3 | CFO
9 | Delay in the implementation of infrastructure projects | 1)Construction mafias disturbing the projects 2)Ommission in the designs 3) Poor performance of the service providers | Critical | 5 | Common | 5 | High | 25 | 1. Project steering committee 2. Improve social facilitation by PP and Councillors 3. Monthly service providers meetings 4. Risk assessment on BOQ | Weak | 0.8 | High | 20 | Accounting Officer | Civil 1. Review of the designs presented by the consultants 2. Minutes of meetings with SPs | Quarter 2 and Quarter 4 Quarter 2 and Quarter 4 Quarterly | Director Civil Engineering
10 | Extreme weather events (floods, storms and others) | Climate change Instutional issues (governance) | Critical | 5 | Likely | 5 | High | 25 | 1. Disaster advisory forum 2. Contigency plans 3. Disaster Management plan 3. By-laws 4. Environmental implementation plan 5. Community awareness | Weak | 0.9 | High | 22.5 | Accounting Officer | 1. Develop Disaster Management Framework 2. Development of the disaster risk management profile 3. Develop climate change response strategy 4. Conduct climate and weather risk assessments for all operational sites 5. Perform scenario planning for severe weather disruptions |  | Snr Disaster Management Officer
11 | Cyber attacks | opening pishing emails, Unauthorised acess. Damage of information and disruption of services, infringement of data | Common | 5 | Likely | 4 | High | 20 | cyber security awareness. Systems activities review ICT security policies | satisfactory | 0.65 | Medium | 13 | Accounting Officer | Conduct Cyber security and Regular user access reviews cyber crime awareness (to security officer) |  | Directors: Corporate and Community Services