## STRATEGIC RISKS 2023 2024 FY
No | Link to objective |  | Link Objectives | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | Rating | Current controls | Perceived control effectiveness | Rating | Residual risk | RRR | Risk owner | Actions to improve management of the risk | Means of verification | Action owner | QRT 1 | QRT 2 | QRT 3 | QRT 4 | Budget
|  | 1 | Efficient and effective administration | Good governance | Agency not established in line with MFMA Sec 84 as a municipal entity subsection 1 (a) and (b) | 1. The mandate of the entity is not transferred which poses a threat to the entity’s going concern.. 2. No collaboration between the entity and LED-PED 3. Registration of Tax liabilities( removed) | Duplications of functions between PED (LED) and Gteda (municipal entity) | Critical | 5 | Common | 5 | High | 25 | SLA betweeen GTM and GTEDA Draft report on the legal status of the agency | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1&2.Continue to advice the municipal council ro comply in terms of MFMA Section 84 subsec 1(a) and (b) 2. Appoint CEO ( removed) 3. Request Treasury to advise on the step by step process of regularising the municipal entity( removed) 3.The parent municipality must write the letter to the entity to agree on the tax liabilities.( removed) 4. The entity to apply for tax exemption from SARS upon receipt of the letter from the parent municipality.( removed) | 1. Minutes of meeting between GTM and GTEDA 2. Appointment letter of CEO( removed) 3. Feedback from treasury( removed) 4. Letter fom municipality to entity costituting the municipal stand-point with regard to tax liability( removed) 5. Approval from SARS partaining to tax exemption( removed) | Director PED and CEO GTEDA | 1&2 Feedback From COGHSTA(Report) |  |  |  | R0.00
1 | Efficient and Effective administration | 2 | Efficient and effective administration | Good governance | 1. Excessive Overtime hours | 1.Excessive payments done beyond what is indicated in the overtime policy as approved by Council. 2.Non implementation of overtime ministerial threshold (R241 110.59 - 1 March 2023) ( removed) 3.Non-compliance with the overtime guiding tool.( removed) | Audit findings, Health of the affected officials due to possible fatigue Abuse of overtime Litigation Possible financial Loss Negative impact on service delivery | Critical | 5 | Common | 5 | High | 25 | Approved overtime policy, Overtime guiding tool Basic Conditions of Employment Act, Internal Circular on Pre -Approvals of overtime Gazzette about the ministerial threshold | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Monitoring of overtime trends in respective departments. 1b.Ensure departments limit overtime hours and align them to what has been prescibed as per the overtime policy 2.Seek clarity from department of labour to assist with the clarification of law on the interpretation of law of the overtime threshold( removed) 2.Ensure the implementation of overtime Ministerial threshhold by monitoring pre approval of overtime( proposal) 3.Reviewal of the overtime policy and send it to council for approval and amend the overtime guiding tool ( removed) | Council resolution, Management minutes on Reviewed overtime tool, Quarterly Council Resolution for approval of overtime above threshold. Letter and response from the Department of Labour for clarity seeking. | Directors | 1.Quarterly overtime monitoring report 1b.Overtime monitoring Report 2. Letter to the Department of Labour for clarity seeking. ( removed) | 1.Quarterly overtime monitoring report 1b. Pre-Approvals , Emergency Memorandums. 3.Management minutes on Reviewed overtime tool( removed) | 1.Quarterly overtime monitoring report 1b.Pre-Approvals , Emergency Memorandums | 1.Quarterly overtime monitoring report 1b.Pre-Approvals , Emergency Memorandums | R0.00
|  | 3 | Optimise and sustain infrastructure investment and services | Service Delivery | Aging infrastructure | 1.Inadequate implementation of maintenance plans and (outdated)Master Plans 2. Insufficient mantainance budget | Poor delivery of services Public protest High costs of maintenance & replacements | Critical | 5 | Common | 5 | High | 25 | Infrastucture Maintenance plan Electrical Master Plans Monthly Inspection report Outage and Mantainance Report | Weak | 0.8 | High | 20 | Accounting Officer | 1.Ensure the implentation of the maintenance plans and Master Plans and perform reactive maintenance as and when required. 1b. Advocate for the appointment of a service provider to review the Master plans. 2.Advocate for Budget increase at the end of the financial year | Quarterly inspections report | 1&2.Directors: Electrical Services. Director Engineering Services | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports and Approved master plans 1b. Internal Memo(budget increase) 2. Approved IDP | R0.00
2 | Optimize and sustain infrastructure investment and services | 4 | Improve access to sustainable and affordable services | Service Delivery | Non adherence of the service level agreement between Water Service Authority ( Mopani District Municipality) and Water Service Provider (Greater Tzaneen Municipality) | 1.Lepele is invoicing GTM for bulk purchases of which is the responsibility of the WSA according to the agreement.( bill not being paid) | Financial loss, GTM incurring the costs of maintenance of infrastructure on behalf of the MDM cash flow constraints Poor service delivery Community Protests | Critical | 5 | Common | 5 | High | 25 | IGR meetings about the SLA between MDM & GTM (Water service authority & Water service provider) Continuos meetings between GTM and MDM, service level agreement | weak | 0.8 | High | 20 | Accounting Officer | Conduct meetings with Lepele, MDM and GTM(Bill settlent). | Progress reports on the implementation of the SLA, | Director: Civil Engineering Services | attendance register and minutes | attendance register and minutes | attendance register and minutes | attendance register and minutes | R0.00
4 | Efficient and Effective administration | 5 | Efficient and effective administration | Good governance | Fraud and corruption - (abuse of municipal vehicles, abuse of fuel, abuse of overtime) | 1.Weak systems of control, 2.manipulation of internal controls, 3.unethical behaviour, | Audit findings; Financial loss, Reputational damage, | Critical | 5 | Common | 5 | High | 25 | awareness to all staff and municipal stakeholders, Approved policies: anti-fraud and corruption, Whistle blowing, fraud prevention plan Anti-corruption hotline Fraud risk register has been developed, Anti-corruption strategy | saisfactory | 0.65 | High | 16.25 | MM | 1-3. Continue to conduct/ raise Awareness on fraud , ethics and corruption. | Investigation report (if any), attendance regsiter for attendance of the workshop, request send to Communications and Marketing about the anti-corruption messages) | CRO | 1-3. Attendance register/communique sent on awareness |  | 1-3. Attendance register/communique sent on awareness |  | R0.00
5 | Efficient and Effective administration | 6 | Efficient and effective administration | Good governance | Non adherence with the reporting format in the Electronic Performance management System. | 1.Inaccurate performance management reporting(Actuals reported and PoEs submmitted/ attached not addressing KPIs (not aligned with reported information) | Audit findings, Lack of credible reports Misalignment of information | Critical | 5 | Common | 5 | High | 25 | Quarterly performance report, APR, SDBIP, Internal Audit reports on performance of information Refresher trainings/workshops | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Continue to conduct refresher trainings/workshops as and well required. | Quarterly SDBIP report | Directors | 1. Attendance register( confirm Quarterly POE) | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | R0.00
To be reviewed by the Risk Office |  | 7 | Efficient and effective administration | Good governance | 1% of personnel budget not fully allocated as per the requirements of Skills Development Act [SDA] | 1.Insufficient training budget on all functions of compliance | Low staff morale, incompetences, Fines & penalties, | Critical | 5 | Common | 5 | High | 25 | WSP, Training plans, | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Accept the risk | Signed Budget Council Resolution. | CFO Director Corporate Services | Continuos training | Continuos training | Continuos training | 1. Approved budget by Council.( confirm POE) | R0.00
6 | Improve access to affordable basic services | 8 | Improve access to sustainable and affordable services | service delivery | Increasing theft and loss of infrastructure | 1.Social issues in the country (unemployment, loadshedding) 2.Absence of security at certain areas. 3.Non-adherence with asset management policy 4.Negligence and lack of safeguarding of municipal assets(loss through theft) | Financial loss, Loss of critical information/data, audit findings, Inconsistent security checks, | Critical | 5 | Common | 5 | High | 25 | security guards, cameras, security technology penalties imposed equivalent to the cost of the item, community policing forums | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Ensure establishment of community policing forums . 1b.Conduct awareness workshops to address social crimes with the comminities 2.Identify and list all Municipal assests to be safeguarged. 3.Inform council about the stolen and replaced assests. 4..Conduct awareness workshops to address negligence and lack of safeguarding of municipal assets | Number of SAPS cases partaning reported cases | Director Comminity Services. | 1. Quartely Report | 1. Quartely Report 1b.Invitation and Attendance Registers 2.Report(Municipal Assets and Municipal Assets location) 4.Invitation and Attendance Registers | 1. Quartely Report | 1. Quartely Report 1b.Invitation and Attendance Registers 3. Council Resolution 4.Invitation and Attendance Registers | R0.00
7 | Efficient and Effective administration | 9 | Efficient and effective administration | Good governance | Non-compliance with SCM policy and regulations. | 1. Lack of forward planning 2. Non-adherence to SCM policy and regulations | Increasing irregular expenditures law suits, unjustified deviations audit findings | Critical | 5 | Common | 5 | High | 25 | Deviation register, Approved memo for deviation SCM policy and regulations MFMA circulars | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Ensure adherence to proper forward planning procedures by relevant stakeholders. 2.Training of the bid committee members and SCM officials, 2b. Ensure that the approved written deviations are inline with the SCM Policy. | Training plan, attendance register of the bid committee training, approved written quotations | CFO | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report 2. Agenda and attendance Registers. | R0.00
|  | 10 | Increase Financial Viability | Revenue Collection | Low collection of revenue collection at the municipal townships (Nkowankowa, Lenyenye) | 1. Credit control of Business properties in the townships on water availability. Restriction of water availability to residential properties. 2. Non provision of services in particular roads, sidewalk library etc. non complaince to national building regulations.(To be removed) | Financial loss | Critical | 5 | Common | 5 | High | 25 | Credit control policy, Debt collection policy, revenue enhancement strategy, Indigent register maintained annually Approved building Plans. National Building Regulations. | weak | 0.8 | High | 20 | Accounting Officer | 1.Implement credit control and debt collection policies. 1b.Improved communication with the communities. 2. Ensure visibility of building inspectors..(To be removed) | Means of communications to the communities, Quarterly reports on the implementation of credit control and debt collection. | 1.CFO 1b. Director Corporate Services. 2. Director Engineering | 1.Quarterly reports on the implementation of credit control and debt collection actions 1b.Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | R0.00
3 | To promote corporate governance excellence | Good governance | Non-compliance with MSA (individual performance management not cascaded to all officials) | Ineffective implementation of performance management system | Audit findings, Poor performance management | [6 empty] | Approved disaster Relief policy; Disaster Management Plan District risk assessment
Note on U2: C Stanley: Consider Linking Actions to improve management of risk with Root Causes
Note on W2: C Stanley: Consider mapping Action owners with Action Plans
Note on X2: C Stanley: Are these quarterly milestones, how should we treat them on the system? There is also need to map the milestones with the action plans

## STRATEGIC RISKS 2024 205FY
2025/2026 FINANCIAL YEAR
NO | Link Objectives | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | IRR | Current controls | Perceived control effectiveness | Rating | Residual risk | RRR | Risk owner | Actions to improve management of the risk | Means of verification | Action owner | Action Owner
1 | Efficient and effective administration | Good governance | Excessive hours of overtime claimed | Payment of overtime in excess of the requirements of the Bascic Conditions of Employment Act and approved policy. &-day week in other departments (CSD-Traffic Officers and Solid Waste officials) | - Audit findings (IA & AGSA) - Might impact negatively on the health of the affected officials due to fatigue - Possible financial Loss - Non-compliance with BCEA and the policy. | Critical | 5 | Common | 5 | High | 25 | Approved overtime policy, Basic Conditions of Employment Act, Internal Circular on Pre -Approvals of overtime Introduce overtme shift | satisfactory | 0.65 | High | 16.25 | Accounting Officer | To develop shift system strategies to reduce overtime claims. Enhance human capacity in the areaswhere overtime is worked. Implement overtime management tool. | Council resolution for approved shift systemn strategies Quarterly report on overtime management. |  | Director Corporate Services
2 | Optimise and sustain infrastructure investment and services | Service Delivery | Aging infrastructure (Roads, Buildings, Electrical) [aged to a point where to replace will be costly to the municipality]. | 1.Inadequate implementation of maintenance plans and Master Plans (both Electrical and Engineering Master Plans to be reviewed) 2. Insufficient mantainance budget 3. Poor Electrical infrastructure performance | Poor delivery of services Public protest High costs of maintenance & replacements, Re-active maintenance | Critical | 5 | Common | 5 | High | 25 | Infrastucture Maintenance plan Existing Electrical and Roads Master Plans Monthly Inspection report Outage and Mantainance Report Pool of service providers for maintenance. | Weak | 0.65 | High | 16.25 | Accounting Officer | Implementation of the maintenance plans (Re-active and pro-active maintenance) Conduct audit of the current infrastructure | Quarterly progress report on the implementation of maintenance plan. Electrical: Management tool/software to assist in managing the maintenance of infrastructure (Q4) |  | Directors: Civil Engineering, Electrical,
3 | Improve access to sustainable and affordable services | Service Delivery | Non compliance with Water Service Authority ( Mopani District Municipality) and Water Service Provider (Greater Tzaneen Municipality) agreement. | Non-payment of invoices by the Water Service Authority (WSA-District Municipality) who are responsible for according to the service level agreement (SLA) | Financial loss, GTM incurring the costs of maintenance of infrastructure on behalf of the MDM cash flow constraints Poor service delivery Community Protests | Critical | 5 | Common | 5 | High | 25 | IGR meetings Meetings beween the WSA (water service authority( and WSP (water service provider) | weak | 0.2 | High | 5 | Accounting Officer | Intervention by CoGHSTA Withhold the payments to the WSA (district Municipality) for water services. | Progress reports on the implementation of the SLA, |  | Directors: Civil Engineering
4 | Efficient and effective administration | Good governance | Fraud and corruption occuring at the municipality | 1.Weak systems of control, 2.manipulation of internal controls, 3.unethical behaviour, | Audit findings; Financial loss, Reputational damage, | Critical | 5 | Common | 5 | High | 25 | awareness to all staff and municipal stakeholders, Approved policies: anti-fraud and corruption, Whistle blowing, fraud prevention plan Anti-corruption hotline Anti-corruption strategy | saisfactory | 0.65 | High | 16.25 | Accounting Officer | Conduct awareness on fraud , ethics and corruption. | Continuous awareness on fraud and corruption through various platforms. Investigate and refer cases reported on the anti-corruption hotline. |  | Manager: Risk and Compliance
5 | Improve access to sustainable and affordable services | service delivery | Increasing theft of infrastructure | 1.Social challenges in the country (unemployment,pverty, loadshedding) 2.Inadequate safeguarding of municipal assets | Financial loss, Loss of critical information/data, Inconsistent security checks | Critical | 5 | Common | 5 | High | 25 | Surveillance cameras Revenue protection association | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1.Escalate cases to the district commissioner 2.Community awareness on copper theft during the customer forums in Q3 (both Safety & Security and Electrical) 3.Write a report to inform Council about the stolen and replaced assets and the year end to be written off. 4.Conduct awareness workshops to address negligence and lack of safeguarding of municipal assets. 5. Implement access control systems that can significanty reduce unauthorised access. | Number of SAPS cases reported. Reports about theft of infrastructure Council Resolution about the stolen assets. Attendance registers of the awareness workshops conducted. Report about the implementation of the access control. |  | Director: Community Services/CFO
6 | Efficient and effective administration | Good governance | Inadequate implementation of POPI Act | Unlawful processing of personal information | Audit findings Posibble litigations Fines | Critical | 5 | Likely | 4 | High | 20 | POPI Act POPI policy POPI terms of reference of the committee POPI committee | Satisfactory | 0.65 | Medium | 13 | Accounting Officer | POPIA Awareness, in terms of publishing personal information. Implement the requirements of the act relevant for the municipality. | Awareness program and attendance registers of the sessions. |  | Director Corporate Services
7 | Improve access to sustainable and affordable services | service delivery | Slow economic growth in the area of GTM | low investment rate Decline in key sectors Non-implementation of LED strategy Lack of tourism strategy Development of SMME development strategy | Increased unemployment and poverty Strain on the municipal services | Critical | 5 | Common | 5 | High | 25 | Incentive policy LED strategy | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | Implement projects in the LED strategy Develop a tourism develop strategy Integrate the function on SMME support Develop the SMME support strategy | Quarterly reports on the implementation of the projects in the LED strategy. Approved tourism strategy Report on the integration of the SMME support Approved SMME support strategy |  | Director PED
8 | Improve access to sustainable and affordable services | service delivery | Service delivery protest | Water services concerns from ward committees not addressed. | Damage to property/infrastructure Loss of revenue | Critical | 5 | Common | 5 | High | 25 | Ward committee reports | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | Resuccitating rapid response committee chaired by the Mayor (all directrs to be part) Prioritize the concerns from the communities | Quarterly reports from the task team on the issues from the communities. |  | Director Corporate Services
9 | Financial Viability | Financial | Inadequate revenue generation | Revenue concentration (high dependance on few revenue sources) Limited revenue streams Underdeveloped land/under-utilized land Poor revenue collection in particular townships | Lack of financial sustainability and financial distress | Critical | 5 | Common | 5 | High | 25 | Debt collection and credit control policy Revenue enhancement strategy Revenue enhancement steering committee meetings | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | Review revenue enhancement strategy Customer education and awareness campaign during imbizo in townships Establishment of RES task team to engage on economic growth and generation Collaborate with PED on under-utilized land for income generating. | Reviewed revenue enhancement strategy Established RES task team |  | CFO
10 | Improve access to sustainable and affordable services | service delivery | Delay in the implementation of infrastructure projects | Protests/community unrests BOQ incorrectly priced Ommission in the designs Construction mafias disturbing the projects |  | Critical | 5 | Common | 5 | High |  | Project steering committee Unnecessary variation orders Possible litogations | Satisfactory | 1.65 | High | 0 | Accounting Officer | Quarterly feedback reports Project steering committee reports about challenges in the communities Risk assessessment be conducted during Evaluation processes of the SCM Review of the designs and presentations by the consultants | Quarterly reports on the action plans identified |  | Director Civil Engineering