## EESD
No | Link to objective | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | Rating | Current controls | Perceived control effectiveness | Rating | Residual risk | RRR | Risk owner | Actions to improve management of the risk | Action owner | QRT 1 | QRT 2 | QRT 3 | QRT 4 | Budget
1 | Optimize and sustain infrastructure investment and services | Service Delivery | Poor Electrical infrastructure performance | 1.Aging infrastructure | Poor customer satisfaction. Claims/litigations; Accidents/incidents | Critical | 5 | Common | 5 | High | 25 | 2.Maintenance plans. 2. Planned maintenance programs 2. Planned outages 2. Bush clearing 1. For rebuilding of the network: Recapitalisation of the Electrical Network | Satisfactory | 0.65 | High | 16.25 | Director: Electrical | 100% Spending of the maintenance budget | Manager: OP & Maintenance | 2. 10% budget spending . | 50% budget spending | 90% budget spending | 100% budget spending | R30m
|  |  |  | 2. Current budget is less than 6% that is required. (6% of infrastructure budget) |  | Critical | 5 | Common | 5 |  | 25 | [6 empty] | Rebuilding of the Electrical Lines | Bongi Sengwayo | Submission of TOR to SCM | Appointment of contractor | Attendance register for Site handover | Completion certificate | Upon budget approval
2 | Optimise and sustain infrastructure investment and services | Service Delivery | Electrical distribution losses (Technical-line losses [system losses] and non-technical [not-accounted for: bridging, illegal onnections building consumption-not metered, traffic lights etc...), | 1.Faulty and inaccurate meters 2. Electrical infrastructure theft, 3.Non-monitoring of the Prepaid System (non- monitoring system is available). | unaccounted meters, Financial loss, Audit findings | Critical | 5 | Common | 4 | High | 20 | Replacement of defective and inaccurate meters, Meter replacements Automated Meter Readings(AMR) on bulk metering (ongoing) Installation Of Bulk Meter NERSA Guideline | Satisfactory | 0.65 | Medium | 13 | Director: Electrical | 1.Investigate meter reading error report from the revenue department (non-technical report to Revenue). Manager: Manager P&P, Manager Revenue 2. Replacement of reported electrical infrastructure stolen. (Andrew) 3. Installation of bulk Statistical meters (once a year) (Bongi) 4. Monitoring of prepaid system (Manager Revenue Division). | Managers: Projects, Operations & Maintenance, Customer Retail Services, Manager Revenue Management (4) & (1) 3. Manager: P&P | 1.Quartely Report 2.Cases Report , Quartely report on stolen Infrastructure. 3. TOR | 1.Quartely Report 2.Cases Report , Quartely report on stolen Infrastructure. 3.Appointment of contractor | 1.Quartely Report 2.Cases Report , Quartely report on stolen Infrastructure. 3. 2 bulk stats meters completed | 1.Quartely Report 2.Cases Report , Quartely report on stolen Infrastructure. 4. 4 bulk stats meters | R0.00
| Optimise and sustain infrastructure investment and services | Service Delivery | Electrical distribution losses (Technical and non-technical),