## ESD
No | Link to objective/goal | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | Rating | Current controls | Perceived control effectiveness | Rating | Residual risk | Rating | Risk owner | Actions to improve management of the risk | Means of verification | Action owner | Qrt 1 | Qrt 2 | Qrt 3 | Qrt 4 | Budget
ENGINEERING SERVICES
ROADS AND STORMWATER
1 | Improve access to sustainable and affordable services | Basic service delivery | Inadequate repairs and maintenance of aging infrstructure and impaired assets | Insufficient resources to implement the maintenance plans. | Community unrest, High costs of maintenance | Critical | 5 | Common | 5 | High | 25 | Business plan to the MDM as per the SLA between WSA & WSP) Pool of service provider for maintenance Re-active maintenance Master Plan | Weak | 0.65 | High | 16.25 | Director ESD | Annual Review infrastructure maintenance plans Review of Roads Master Plan Implement operational maintenance plan | 1. Maintenance plan 3. Operational maintenance | Managers: Water Services & Roads, Buildings, and Fleet Management | Job cards | Quarterly reports | Quarterly reports | 1.Reviewed maintenance plan 2. Reviewed Roads Master Plan