## CSD
No | Link to objective/goal | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | Rating | Current controls | Perceived control effectiveness | Residual Rating | Residual risk level | Risk owner | Actions to improve management of the risk | Action owner | Qrt 1 | Qrt 2 | Qrt 3 | Qrt 4 | Budget
SAFETY & SECURITY RISKS
1 | Improve access to sustainable and affordable services | Service delivery | Loss of municipal infrastructure (increasing theft of infrastructure) | 1.Non- adherence with safety & security policy 2.Poor monitoring of municipal asset | Financial loss, Negative audit findings, Loss of data/information | High | 5 | Common | 5 | High | 25 | Safety and security policy Physical security CCTV cameras Monitoring of substations (24 hr) Monitoring reaction Panic buttons in case of armed robbery Access control (register at security entrance) Physical searching at the entrance gates | Satisfactory | 0.65 | 16.25: High | Director CSD | 1.Implement safety & security policy 2. Enforce Levy penalties as per service level agreement. | Safety & Security Officer | 1.Monthly Reports 2.Monthly Reports | 1.Monthly Reports 2.Monthly Reports | 1.Monthly Reports 2.Monthly Reports | 1.Monthly Reports 2.Monthly Reports | R0.00 (covered by minicipal insurance as well as service providers.)
Library
2 | Improve access to sustainable and affordable services | Basic Service Delivery | Ineffective markerting and outreach of libraries | 1.Budget constraints(no budget for books and markerting) 2.Lack of tertiary Material 3.Lack Of Vehicle to use in engaging with the Communties for Outreachs 4.Shortage of Staff 5 . Lack of Library Awareness | Decline in number of Library Users | Major | 4 | Common | 4 | High | 16: High | School Outreach(awareness) Library Competitions Outreach programs for Library Users Council Resolution for Outreach Programs. | Satisfactory | 0.65 | 10.4: Medium | Director CSD | 1. Submission to open the library on weekends and public holidays. 2. Sourcing tertiary study materials for the library | Manager Libraries | n/a | 1. End of December as per approved 2. Developments pertining to opening of library on weekends. | n/a | Results (both acton 1 & 2) | R13 000( for buying prizes)
Law Enforcement ,Licencing and Testing
3 | Improve access to sustainable and affordable services | Basic Service Delivery | Ineffective implementation of Law Enforcement | 1. Lack of Proper Law Enforcement resources and by-laws | Loss of Revenue | Major | 4 | Common | 5 | High | 20 | Roadblock Register (12 in a year) including Easter and Festives Speed Measuring Machine (only 1) Execution of Warrants of Arrests Monitoring the traffic fines Awareness workshops Administation of Traffic Fines Systems (Traffic as administrators) | Satisfactory | 65 | 13: Medium | Dir CSD | 3. Appointment of Law Inforcement Officers (HR) 1a. Increase the speed measuring machines 2.Assessment on the status of the current vehicles of the traffic officers be conducted 1b.Conduct Training and Awareness workshops for law enforcement Officers, including awreness on Fraud and corruption. 1c. Monitoring the Administration of Traffic Fines System. | Manager Law Enforcement. | Quarterly progress report | Quarterly progress report | Quarterly progress report | Quarterly progress report