## PED
No | Link to objective/goal | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | Rating | Current controls | Perceived control effectiveness | Rating | Residual Risk Rating | Residual risk level | Risk owner | Actions to improve management of the risk | Means of verification | Action owner | Qrt 1 | Qrt 2 | Qrt 3 | Qrt 4 | Budget
1 | Improve access to affordable basic services | LED | Inadequate enforcement of By-laws for street trading | 1.Mushrooming of informal traders within Greater Tzaneen 2. Resistance meet in enforcing of the By-laws | Inability to attract investment Law suits to the municipality Formal businesses leaving the town of Tzaneen which leads to the financial loss to the municipality, loss of investors in the CBD. -job losses | Major | 4 | Common | 4 | High | 16 | Street trading by-law Informal Tarders Policy | Weak | 0.8 | Medium | 12.8 | Director PED | 1a. Facilitate the appoointment of the stirring committee 1b.Allocation of permits to traders 1c.Conduct meetings with the informal traders. 2.Engage law enforcement to remove illegal traders (CSD-Traffic). 3.Enforce implementation of by-laws(to be addressed upon the appointment of Panel Members)( to be adreesed in the next FY when action 1&2 are achieved) 4.Monitor the collection of revenue from informal traders (R40 per trader(monthly)) to be adreesed in the next FY when action 1&2 are achieved) | 1a. Letters of appointment of stirring committee members 1b. Number of hawkers approved to trade 1c. Minutes and the invitations to the meeting applications approved versus and the hawkers explanage allocated (quarterly report) | 1.Manager: LED 2.Manager LED 3.Manager Safety and Security , Manager Law Enforcement 4.Manager Revenue ManagerTraffic and Manager Safety and Security , Manager Law Enforcement | 1a.Appointment of the stiring committee 1c. Memo 2.Inspection Checklist 3.Quartely Report 4.Proof of Payments 5.Panel Resolution | 1a.Quarterly meetings (including minutes of the meetings) 1c.Invitation Letter to informal trader meeting. 2. Inspection checklist 3.Quartely Report 4.Proof of Payments 5.Panel Resolution | 1a.Quarterly meetings (including minutes of the meetings) 1b.Permit .1c. Minutes and attendance Register 2. Inspection checklist 3.Quartely Report 4.Proof of Payments 5.Panel Resolution | 1a. Quarterly meetings (including minutes o the meetings) 1c. Minutes and attendance Register 2. Inspection checklist 3.Quartely Report 4.Proof of Payments 5.Panel Resolution | R0.00