## Sheet1
1. Final mSCOA Roadmap 2026/2027
No | Pillar |  | Objective/Purpose | Focus Area | Activity | Frequency | Start Date
1 | 1.ICT Architecture | ICT Architecture | e.g. To ensure that the Hardware and Software capacity and capability is responsive to the mSCOA reform and its annual improvements | Hardware | Network Connectivity - Dedicated line with guaranteed uptime | Once Off Activity
2 |  | ICT Architecture |  | Hardware | Android rugged handheld devices | Once Off Activity
3 |  | ICT Architecture |  | Hardware | Regular assessments of ICT Network, back-up (inluding back-up testing) and server performance | Quarterly
4 |  | ICT Architecture |  | Hardware |  | Quarterly
5 |  | ICT Architecture |  | Software |  | Quarterly
6 |  | ICT Architecture |  | Software |  | Select
7 |  | ICT Architecture |  | Software |  | Select
8 |  | ICT Architecture |  | Software |  | Select
9 |  | ICT Architecture |  | Software |  | Select
10 |  | ICT Architecture |  | Software |  | Select
11 |  | ICT Architecture |  | Software |  | Select
12 |  | ICT Architecture |  | Software |  | Select
13 |  | ICT Architecture |  | Licence |  | Select
14 |  | ICT Architecture |  | Licence |  | Select
15 |  | ICT Architecture |  | Security | Perform assessment and enhance cybersecurity measures | Once Off Activity | 2026-08-01
16 |  | ICT Architecture |  | Security |  | Select
17 |  | ICT Architecture |  | Security |  | Select
18 |  | ICT Architecture |  | Security |  | Select
19 |  | ICT Architecture |  |  |  | Select
20 |  | ICT Architecture |  |  |  | Select
21 | 2. Governance and Institutional Arrangments | Governance and Institutional Arrangements | E.g. To ensure that functionality of mSCOA governance structures and Institutional Arragements | PSC Meeting | PSC Meeting - Roadmap Jul - 24 | Monthly | 2026-07-31
22 |  | Governance and Institutional Arrangements |  | PSC Meeting | PSC Meeting - Roadmap July - 25 | Quarterly | 2026-07-07
23 |  | Governance and Institutional Arrangements |  | PSC Meeting | PSC Meeting - Roadmap OCT - 25 | Quarterly | 2026-10-31
24 |  | Governance and Institutional Arrangements |  | PSC Meeting | PSC Meeting - Roadmap January - 26 | Quarterly | 2027-01-31
25 |  | Governance and Institutional Arrangements |  | PSC Meeting | PSC Meeting - Roadmap June - 26 | Quarterly | 2027-06-30
26 |  | Governance and Institutional Arrangements |  | PSC Meeting
27 |  | Governance and Institutional Arrangements |  | PSC Meeting
28 |  | Governance and Institutional Arrangements |  | PSC Meeting
29 |  | Governance and Institutional Arrangements |  | PSC Meeting
30 |  | Governance and Institutional Arrangements |  | PSC Meeting
31 |  | Governance and Institutional Arrangements |  | PSC Meeting
32 |  | Governance and Institutional Arrangements |  | PSC Meeting
33 |  | Governance and Institutional Arrangements |  | ICT policies and governace documents | Review of ICT policies and governance documents | Once Off Activity | 2027-04-30
34 |  | Governance and Institutional Arrangements |  | SLA | The SLA make provision for enhancement of the system (functionality, model update etc), provision for efficiency and updates based on developments or identified gaps | Ongoing | as and when required
35 |  | Governance and Institutional Arrangements |  | Governance meetings | Governance meetings for engagement with the system vendor of system funcitionality, performce, responsiveness, challenges, system upgrades, feedback reports, assessment reports | Periodic | 2026-07-01
36 |  | Governance and Institutional Arrangements |  | Stakeholder engagement | Engage Provincial Treasury on mSCOA updates and awareness to socialise the implementation of mSCOA | Periodic | 2026-07-01
37 |  | Governance and Institutional Arrangements |  | Risk register | Conduct mSCOA risk assessment | Once Off Activity | 2026-07-01
38 |  | Governance and Institutional Arrangements
39 |  | Governance and Institutional Arrangements
40 |  | Governance and Institutional Arrangements
41 | 3.System Functionality | System Functionality | e.g. To ensure optimal system functionality and seamless integration of the 3rd party systems | Prepaid Integration | Integrate vending system and Finacial Management system (FMS) | Monthly | 2026-12-31
42 |  | System Functionality |  | HR and Payroll Integration | Integrate Payroll system and FMS | Monthly | 2027-03-31
43 |  | System Functionality |  | Costing and Reporting | Implementation of costing module | Monthly | 2026-09-30
44 |  | System Functionality |  | Document Management | Document Management Integration to EMS | Monthly | 2027-06-30
45 |  | System Functionality |  |  |  | Select
46 |  | System Functionality |  |  |  | Select
47 |  | System Functionality |  |  |  | Select
48 |  | System Functionality |  |  |  | Select
49 |  | System Functionality |  |  |  | Select
50 |  | System Functionality |  |  |  | Select
51 |  | System Functionality |  |  |  | Select
52 |  | System Functionality |  |  |  | Select
53 |  | System Functionality |  |  |  | Select
54 |  | System Functionality |  |  |  | Select
55 |  | System Functionality |  |  |  | Select
56 |  | System Functionality |  |  |  | Select
57 |  | System Functionality |  |  |  | Select
58 |  | System Functionality |  |  |  | Select
59 |  | System Functionality |  |  |  | Select
60 |  | System Functionality |  |  |  | Select
61 |  | System Functionality |  |  |  | Select
62 |  | System Functionality |  |  |  | Select
63 | 4. User Proficiency and Training | User Proficiency and Training | Capacity buiding on functionality of the system and mSCOA | Training and skills transfer | Training Session - mSCOA and EMS modules | Periodic | 2026-07-31
64 |  | User Proficiency and Training | SCM end to end and contract management module | Training and skills transfer | Contract management module and SCM related trainings | Once Off Activity | 2026-07-31
65 |  | User Proficiency and Training | Assets | Training and skills transfer | readiness assessment Asset Register module training | Once Off Activity | 2026-08-31
66 |  | User Proficiency and Training | Costing | Training and skills transfer | Costing training | Once Off Activity | 2026-08-30
67 |  | User Proficiency and Training | Document management | Training and skills transfer | Document Management training | Once Off Activity | 2027-03-31
68 |  | User Proficiency and Training | Revenue | Training and skills transfer | Reconciliation of valuation roll and billing system Billing reconciliation and other revenue related trainings | bi-annually | 2026-07-01
69 |  | User Proficiency and Training | Reporting | Training and skills transfer | capacity building on Mapping, transacting on the system, data strings | Select | 2026-07-31
70 |  | User Proficiency and Training |  |  |  | Select
71 |  | User Proficiency and Training |  |  |  | Select
72 |  | User Proficiency and Training |  |  |  | Select
73 |  | User Proficiency and Training |  |  |  | Select
74 |  | User Proficiency and Training |  |  |  | Select
75 |  | User Proficiency and Training |  |  |  | Select
76 |  | User Proficiency and Training |  |  |  | Select
77 |  | User Proficiency and Training |  |  |  | Select
78 |  | User Proficiency and Training |  |  |  | Select
79 |  | User Proficiency and Training |  |  |  | Select
80 |  | User Proficiency and Training |  |  |  | Select
81 |  | User Proficiency and Training |  |  |  | Select
82 | 5. Business Components | Business components |  | General Ledger | Host 2 Host (Banking) | Once Off Activity | TBC
83 |  | Business components |  | Billing | SMS Functionality | Once Off Activity | TBC
84 |  | Business components |  | Supply Chain Management | Full utilisation of the module. Tender functionality | Once Off Activity | TBC
85 |  | Business components |  | Asset Management Module | Embark on assessment and readines for activation of asset module Collaboration with the system vendor for alignment with new provision of mSCOA regulations, module integration with core functional system and other modules such as procurement, budgeting and GL processing, data migration and testing, user training and support. | Once Off Activity | 30/09/ 2026 30/04/2027
86 |  | Business components |  | Asset Management Module | Implementation of asset management module. | Once Off Activity | 30/06/2027
87 |  | Business components |  | HR and Payroll | Payday Integration | Once Off Activity | TBC
88 |  | Business components |  | Valuation Roll Management | Revenue Management - Valuation Rolls | Quarterly | 2026-09-30
89 |  | Business components |  | Costing and Reporting | Business Intellegence Reporting | Once Off Activity | 2029-09-30
90 |  | Business components |  | Costing and Reporting | Costing and Reporting | Once Off Activity | 2026-02-01
91 |  | Business components |  |  |  | Select
92 | 6. Business Process | Other Focus Area as may be determined by the municipality |  | Corporate Governance | Document Management related to the financial system | Once Off Activity | 2026/26
93 |  | Other Focus Area as may be determined by the municipality |  | Municipal Budgeting
94 |  | Other Focus Area as may be determined by the municipality |  | Financial Accounting |  | Select
95 |  | Other Focus Area as may be determined by the municipality |  | Costing and Reporting |  | Select
96 |  | Other Focus Area as may be determined by the municipality |  | Project Accounting |  | Select
97 |  | Other Focus Area as may be determined by the municipality |  | Treasury and Cash Management |  | Select
98 |  | Other Focus Area as may be determined by the municipality |  | Procurement Cycle: SCM, Expenditure Management, Contract management |  | Select
99 |  | Other Focus Area as may be determined by the municipality |  | and Accounts |  | Select
100 |  | Other Focus Area as may be determined by the municipality |  | Full Asset life Cycle Management and including Maintenance |  | Select
101 |  | Other Focus Area as may be determined by the municipality |  | Real Estate and Resource Management |  | Select
102 | 7.Business Process | Other Focus Area as may be determined by the municipality |  | Human Resources and Payroll Management |  | Select
103 |  | Other Focus Area as may be determined by the municipality |  | Customer Care, Credit Control and debt collection |  | Select
104 |  | Other Focus Area as may be determined by the municipality |  | Valuation Roll Management |  | Select
105 |  | Other Focus Area as may be determined by the municipality |  | Land Use Building Control |  | Select
106 |  | Other Focus Area as may be determined by the municipality |  | Revenue Cycle billing | Account validation | Once Off Activity | 2026/26
107 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
108 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
109 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
110 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
111 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
112 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
113 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
114 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
115 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
116 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
117 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
118 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
119 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select
120 |  | Other Focus Area as may be determined by the municipality |  |  |  | Select