## Sheet1
mSCOA risk register
NO | Link Objectives | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | IRR | Current controls | Perceived control effectiveness | Rating | Residual risk | RRR | Risk owner | Actions to improve management of the risk | Action timeline | Action Owner
1 | Financial Viability | Financial | Inadequate integration systems between FMS and other systems i.e payroll, | System procured and implemented in different period(s) | monthly data from other systems may be incorrectly recorded in the general ledger Errors, inefficient reconciliation | Critical | 5 | Likely | 5 | High | 25 | Manual reconciliation Review of exception and variance report and controlled data uploads of salary control and prepaid meters | satisfactory | 0.65 | High | 16.25 | CFO | Implement system intergration Continous review of reconciliation | 1a) Quarter 2 and Quarter 4 1b) Quarterly 1c)Quarterly | Manager: Expenditure, revenue and financial reporting
2 | Financial Viability | Financial | Inadequate mapping of transaction to mscoa segments | poor understanding of mscoa segment structure | misclassification of transactions inaccurate financial reporting | Critical | 5 | Common | 5 | High | 25 | Perform reconciliations Mapping template Segregation of duty | satisfactory | 0.65 | High | 16.25 | CFO | Perform regular data quality reviews training on mscoa segments system validation for segment allocation | 1a)Quarterly 1b) Quarter 3 2a)Quarter 2 2b) Quarter 4 | All BTO managers
3 | Financial Viability | Financial | Inadequate data migration to new FMS (current FMS lapse in 2025/26) | Poor migration planning and testing, Poor reconcilation | Loss of data distorted opening balances | Critical | 5 | Likely | 5 | High | 25 | Back data and testing Migration plan ICT assessment report | satisfactory | 0.2 | High | 5 | CFO | Develop comprehensive data migration plan Parallel runs and testing Ensure adequate documentation on transfer of data with system vendors | Quarter 1 Quarterly | Manager ICT
4 | Financial Viability | Financial | Noncompliance with mSCOA requirements and error on data strings | Inadequate awareness of mscoa regulations, circular and related updates lnadequate engagements to monitor compliance | Non adeherence to Treasury and reporting requirements and audit finding | Critical | 5 | Common | 5 | High | 25 | mscoa regulations and circulars system configuration for compliance with mSCOA | saisfactory | 0.65 | High | 16.25 | CFO | Develop and implement an action plan to address non compliance and findings issued by LPT Training Implement compliance check list | 1&3) Quarterly 2)Bi- Annually(Q2&4) | All BTO managers
5 | Financial Viability | Financial | Limited understanding of mSCOA requirements by some of the officials | Minimal practical exposure | Misclassification of transactions Human errors | Critical | 5 | Common | 5 | High | 25 | Regulations and guidelines | Satisfactory | 0.65 | High | 16.25 | CFO | Training and workshop Institutionalise guidelines and regulations register and complete mSCOA elearning programs | 1a) Quarterly 1b) Quarter 3 1c)Quarter 4 2a) Quarterly 2b)Quarterly | Manager Budget and financial reporting