## MUNICIPAL MANAGER
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MHANGWANA D
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2022/2023 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 14 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | Preparation of BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own Funds | (Own/MIG/INEP/DBSA)
Sıra No |  |  |  | Sözleşme No.su | Tahimini Bedel (Euro 1000) |  |  | Satınalma Yöntemi |  |  | Sözleşme İmza Tarihi | Sözleşme Tamamlanma Tarihi
[5 empty] | Toplam | Banka Finansmanı | Belediye Finansmanı
GELIBOLU MUNICIPALITY
OFFICE OF THE MUNICIPAL MANAGER
1
2
3
4
5
6
7
8
9
10
3
4 | [14 empty] | December 2010

## BUDGET & TREASURY
Name of Municipality GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MHANGWANA D
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2022/2023 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022' | 2022/2023' | 2023/2024' | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own Funds | (Own/MIG/INEP/DBSA)
BUDGET & TREASURY
General valuation roll | Compiling of general valuation roll period 1 Jul 2024 to Jun 2029 | Operational |  | 8M |  | 8M |  |  | R2.5m | R2.7m | Gen valaution roll 2024-01-31 + supplementary for 5 years. | Appointed valuer must deliver new roll end of Jan 2024 for implementation 1 July 2024
Meter reading contract | Meterreading services | Operational |  | 5M |  | 5M |  |  | R1.8m | R2m | 2025-06-01 | Awaiting apoointment of SP, BAC already done
Credit Control | Credit control, reconnection and disconenction services | Operational |  | 3m |  | 3m |  |  | R1m | R1m | 2025-06-01 | Awaiting apoointment of SP, BAC already done
Debt collection | Debt collection services | Operational |  | 6M |  | 6M |  |  | R2m | R2m | 2022-07-01 | 2022-08-01

## ELECTRICAL ENGINEERING SERVICES
Name of Municipality GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MHANGWANA D
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2022/2023 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022' | 2022/2023' | 2023/2024' | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
ELECTRICAL ENGINEERING SERVICES
| Sampling and purification of Transformer oil | Sampling and purification of Transformer oil at Various substations | Operational |  | 100000 | N | Y | OWN | 100000 | 100000 | 100000 |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Maintenance of substation breakers | Maintenance of breakers at various substations | Operational |  | 350000 | N | Y | OWN | 350000 | 350000 | 350000 |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Maintenance of Transformer tap changers | Maintenance of Transformer tap changers | Operational |  | 500000 | N | Y | OWN | 500000 | 500000 | 500000 |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Maintenance of Transformers, bushings and Isolators | Maintenance of Transformers, bushings and Isolators at various substations | Operational |  | 2000000 | N | Y | OWN | 2000000 | 2000000 | 2000000 |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Maintenance of substation protection schemes | Maintenance of substation protection schemes at various substations | Operational |  | 60000 | N | Y | OWN | 60000 | 60000 | 60000 |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Maintenance of substation battery systems | Maintenance of substation battery systems at various substations | Operational |  | 25000 | N | Y | OWN | 25000 | 25000 | 25000 |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Maintenance of miniature substations | Maintenance of miniature substations at various locations | Operational |  | 250000 | N | Y | OWN | 250000 | 250000 | 250000 |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Procurement of 11kV neutral current transformers for 33/11kV substations | Procurement of 11kV neutral current transformers for 33/11kV substations | Operational |  | 400000 | N | Y | OWN | 400000 |  |  |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Procurement of Protection relays spares: SCEM cards, Batteries, Protection relays & Auxiliaries | Procurement of Protection relays spares: SCEM cards, Batteries, Protection relays & Auxiliaries | Operational |  | 50000 | N | Y | OWN | 50000 | 250000 | 300000 |  | 2022-07-15 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Installation of High Mast Lights at Xihoko | Install Apollo lights | Capital |  | 700000 | Y | N | MIG | 700000 |  |  |  | 2022-08-01 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT, increased scope due to surface condition | Waiting for approval of budgets | Prioritize work based on requirements
| Installation of High Mast Lights at Mandlakazi | Install Apollo lights | Capital |  | 700000 | Y | N | MIG | 700000 |  |  |  | 2022-08-01 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT, increased scope due to surface condition | Waiting for approval of budgets | Prioritize work based on requirements
| Installation of High Mast Lights at Mariveni | Install Apollo lights | Capital |  | 700000 | Y | N | MIG | 700000 |  |  |  | 2022-08-01 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT, increased scope due to surface condition | Waiting for approval of budgets | Prioritize work based on requirements
| Installation of High Mast Lights at Nkowankowa | Install Apollo lights | Capital |  | 700000 | Y | N | MIG | 700000 |  |  |  | 2022-08-01 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT, increased scope due to surface condition | Waiting for approval of budgets | Prioritize work based on requirements
| Installation of High Mast Lights at Lusaka | Install Apollo lights | Capital |  | 700000 | Y | N | MIG | 700000 |  |  |  | 2022-08-01 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT, increased scope due to surface condition | Waiting for approval of budgets | Prioritize work based on requirements
| Installation of High Mast Lights at Sethone | Install Apollo lights | Capital |  | 700000 | Y | N | MIG | 700000 |  |  |  | 2022-08-01 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT, increased scope due to surface condition | Waiting for approval of budgets | Prioritize work based on requirements
| Electrification of Tarentaalrand | Electrification | Operational |  | 1000000 | Y | N | INEP | 1000000 |  |  |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Electrification of Nkomanini | Electrification | Operational |  | 4300000 | Y | N | INEP | 4300000 |  |  |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Electrification of Mokgwathi | Electrification | Operational |  | 2400000 | Y | N | INEP | 2400000 |  |  |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Electrification of Ramotshinyadi | Electrification | Operational |  | 2640000 | Y | N | INEP | 2640000 |  |  |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Electrification of Maribathema | Electrification | Operational |  | 800000 | Y | N | INEP | 800000 |  |  |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Electrification of Mugwazeni | Electrification | Operational |  | 2860000 | Y | N | INEP | 2860000 |  |  |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Vegetation Control | Clearing of Vegetation underneath O/Head Powerr lines | Operational |  | 2000000 | N | Y | OWN | 2000000 |  |  |  | 2022-08-01 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Identifying lines to be cleared | Prioritize work based on requirements
| New Electricity Connections (Consumer Contribution) | New Electricity Connections (Consumer Contribution) | Capital |  | 30000000 | N | Y | OWN | 10000000 | 10000000 | 10000000 |  | 2022-07-01 | 2023-06-30 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Electrical Master Plan | Electrical Master Plan | Operational |  | 1250000 | N | Y | OWN | 750000 | 500000 |  |  | 2022-07-01 | 2023-07-30 | 2022-09-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Urban distribution networks | Miniature substation Urban distribution networks in phases | Capital |  | 1000000 | N | Y | OWN |  |  | 1000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| 11kv cables Tzaneen CBD in phases (Tzaneen Main - SS1) | Replacing 11kv cables due to required increase in capacity | Capital |  | 7000000 | N | Y | OWN | 5000000 | 2000000 |  |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| 11 kV and 33 kV Auto reclosers per annum X4 (La_Cotte x 2, California x 1, | Replace 11 kV and 33 kV Auto reclosers per annum | Capital |  | 3000000 | N | Y | OWN | 1500000 |  | 1500000 |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Monitoring system on GTM electrical network | Install scada monitoring system on GTM electrical network | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| 11kv Feeder from Western sub to Industrial area | New 11kv Feeder from Western sub to Indyustrial area | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuild 66 kV wooden line from Tarentaalrand Main to Tzaneen (20km) in Phases | Rebuild 66 kV wooden line from Tzaneen to Tarentaalrand | Capital |  | 9000000 | N | Y | OWN | 3000000 | 3000000 | 3000000 |  | 2022-07-15 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Building of new 4 MVA, 33/11 kV Substation at Agatha (Meyers Rus T off Phase 1) | Building of new substation | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Skirving and Peace Streets replacement of old switchgear with safe technologies | Installation of new 11kv switchgear | Capital |  | 8000000 | N | Y | OWN |  | 8000000 |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| SS3 retrofitting old panels with safe technologies | Installation of new 11kv switchgear | Capital |  | 2000000 | N | Y | OWN |  | 2000000 |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Tzaneen Main retrofitting old panels with safe technologies | Installation of new 11kv switchgear | Capital |  | 2000000 | N | Y | OWN |  |  | 2000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Procurement of Network planning software | Procurement of Network planning software | Operational |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Renewal Repairs and maintenance of Bulk meters and Replace current transformers & meter panel Tarentaalrand, | Renewal Repairs and maintenance of Bulk meters | Capital |  | 2500000 | N | Y | OWN | 1500000 |  | 1000000 |  | 2022-08-15 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Install Bulk current transformers & meter panel Gravelotte | Renewal Repairs and maintenance of Bulk meters | Capital |  | 500000 | N | Y | OWN | 500000 |  |  |  | 2022-08-15 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Installation of STATS meters Tzaneen Main, Letsitele Main, Western Sub, Rubbervale & 33/11kV Substation in Phases | Installing statistical metering system | Operational |  | 500000 | N | Y | OWN | 500000 |  |  |  | 2022-08-15 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Installing of Quality of Supply recorders (Tarentaal Rand, Tzaneen Main, Letsitele Main, Henley, Waterbok, Middlekop, Politsi, Blacknoll, Letsitele Valley | Installing of Quality of Supply recorders | Operational |  | 500000 | N | Y | OWN | 500000 |  |  |  | 2022-08-15 | 2022-10-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Refurbishment of protection systems and panels in Tarentaal rand | Refurbishment of protection systems and panels in Main subs in phases | Capital |  | 6000000 | N | Y | OWN |  | 3000000 | 3000000 |  | 2022-09-15 | 2022-11-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Refurbishment of protection systems and panels in Tzaneen Main | Refurbishment of protection systems and panels in Main subs in phases | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Refurbishment of protection systems and panels in Letsitele Main | Refurbishment of obsolete protection systems and panels in Main subs in phases | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Refurbishment of protection systems and panels at Rubbervale | Refurbishment of obsolete protection systems and panels in Main subs in phases | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replacement of Box Breakers at Letsitele Main Substation in Phases | Replacement of Box type 33kV Breakers in Main Substations in phases | Capital |  | 3000000 | N | Y | OWN |  | 1500000 | 1500000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replacement of Box Breakers in Main Substations at Tzaneen Main in phases | Replacement of Box type 33kV Breakers in Main Substations in phases | Capital |  | 1500000 | N | Y | OWN |  |  | 1500000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replacement of 132Kv & 66Kv Breakers at Tarentaal Main Substations in phases | Replace oil type breakers with latest technology | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replacement of 66Kv Current Transformers at Letsitele Main Substations in phases | Replacement of old dilapidated current Transformers | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replacement of 66Kv Isolators at Letsitele Main Substations in phases | Replacement of old knife type Isolators | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replacement of 66Kv Breakers at Letsitele Main Substations in phases | Replace oil type breakers with latest technology | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Duiwelskloof 33 kV line (5 km) | Rebuilding of 33kV lines | Capital |  | 3000000 | N | Y | OWN | 3000000 |  |  |  | 2022-09-15 | 2022-11-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Grysappel 11 kV line (2.5 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN |  | 1000000 |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Pusela 11 kV line (4.5 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN |  |  | 1000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of New Orleans 11 kV line (2 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN | 1000000 |  |  |  | 2022-09-15 | 2022-11-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Letsitele Valley / Benzulani 11 kV line (5 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN |  |  | 1000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Manorvlei / Broederstroomdrift (5 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN |  |  | 1000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Hotel / Stanford Lake College 11 kV line (5 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN |  | 1000000 |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Tarentaal California 11 kV line (5 km) | Rebuilding of 11kV lines | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Tarentaal / Deerpark 11 kV line (5 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN |  |  | 1000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Henley 11 kV line (2 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN | 1000000 |  |  |  | 2022-09-15 | 2022-11-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of Waterbok / Prieska 11 kV line (5 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN |  |  | 1000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Rebuilding of La Cotte 11 kV line (5 km) | Rebuilding of 11kV lines | Capital |  | 1000000 | N | Y | OWN |  | 1000000 |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replace, Refurbish & Upgrading of underground LV cables, metering kiosks (Tzaneen Town) | Replace, Refurbish & Upgrading of LV cables due to low voltage, metering kiosks and in phases | Capital |  | 2000000 | N | Y | OWN |  | 1000000 | 1000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replace, Refurbish & Upgrading of underground LV cables, metering kiosks (Haenerstburg Town) | Replace, Refurbish & Upgrading of underground LV cables, metering kiosks in phases | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replace, Refurbish & Upgrading of underground LV cables, metering kiosks (Letsitele Town) | Replace, Refurbish & Upgrading of underground LV cables, metering kiosks in phases | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Replacement of old metering boxes and meters | Replacement of old metering boxes for SPU & LPU as per NRS 057 | Operational |  | 500000 | N | Y | OWN | 500000 |  |  |  | 2022-07-01 | 2022-08-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Customer Management and Interrogation system | Customer Management system | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Maintenance Management tools & system | Maintenance management software | Operational |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Reduction Electricity losses analysis | Develop distribution Electricity losses reduction strategy | Operational |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Revenue Protection | Implementationn of a Revenue Protection Program | Operational |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Traffic Lights | Replacement of old halogen traffic lights heads, replacement of vissors and pole painting | Capital |  | 500000 | N | Y | OWN | 500000 |  |  |  | 2022-07-01 | 2022-08-15 | 2022-11-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| R71 Streetlights Cnr Voortrekker to Deerpak Intersection | New, Replace streetlights with the latest technology type | Capital |  | 3500000 | N | Y | OWN | 1000000 |  | 2500000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Computerise Task order management system | Computerise Task order management system | Operational |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Installing of Power Factor Capacitors Blacknol, Tarentaal T-off, The Pleins Henely, LaCotte, Waterbok | Installing of Power Factor Capacitors | Capital |  | 3000000 | N | Y | OWN |  | 1000000 | 1000000 | 1000000 | N/A | N/A | N/A | N/A | N/A | Prioritize work based on requirements
| Building of new 10 MVA, 66/11 kV Substation at Blackhills, Includes construction of 66kV line | Build a New 66/11kV Substation with a 10MVA Trfr, includes a 66kV line | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Upgrading of LA-Cotte Substation to 5MVA | Install a 5MVA transformer to increase capacity | Capital |  | 2000000 | N | Y | OWN |  |  | 2000000 |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Upgrading of Politsi Substation to 5MVA | Install a 5MVA transformer to increase capacity | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Upgrading of Middlekop Substation from 2MVA to 4MVA | Install a 2MVA transformer to increase capacity | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Install New 5MVA 66/11kV Transformer Letsitele Valley | Install a new 5MVA transformer | Capital |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Conduct Electrical network Harmonics Studies | Simulation of electrical network to determine harmonic levels | Operational |  |  | N | Y | OWN |  |  |  |  | N/A | N/A | N/A | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| Installation of Air conditioner Municipal Buildings | Install Air conditioners | Capital |  | 500000 | N | Y | OWN | 500000 |  |  |  | 2022-07-01 | 2022-09-15 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements
| TID rollover Pre-paid | TID Rollover Pre-Paid meters | Operational |  | 1000000 | N | Y | OWN | 500000 | 500000 |  |  | 2022-08-01 | 2022-10-01 | 2023-06-21 | Insufficient funds, Stoppage on Procurement by NT | Waiting for approval of budgets | Prioritize work based on requirements

## CIVIL ENGINEERING SERVICES
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MHANGWANA D
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2022/2023 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022' | 2022/2023' | 2023/2024' | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Contract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
CIVIL ENGINEERING SERVICES
1. | Paving of Mulati Access road | Upgrading of Road from Gravel to Concrete Paving | Capital |  | 33428457.64 | 33428457.64 | 0 | MIG | 26928457.64 | 6500000 | 0 |  |  | 09/12/2020 | 30/08/2022 | None | Construction
2. | Paving of Zangoma to Mariveni Road | Upgrading of Road from Gravel to Concrete Paving | Capital |  | 27000000 | 27000000 | 0 | MIG | 0 | 7000000 | 20000000 |  |  | N/A | TBC | None | Planning
3. | Upgrading of Marirone to Motupa Street from gravel to paving | Upgrading of Road from Gravel to Concrete Paving | Capital |  | 25916024 | 25916024 | 0 | MIG | 0 | 7000000 | 18916024 |  |  | N/A | TBC | None | Planning
4. | Paving of Moseanoka to Cell C Pharare Internal Streets | Upgrading of Road from Gravel to Concrete Paving | Capital |  | 56638679.3 | 56638679.3 | 0 | MIG | 25438679.3 | 31200000 | 0 |  |  | 09/11/2020 | 09/02/2023 | None | Construction
5. | Paving of Risaba, Mnisi, Shando, to Driving school Internal Street | Upgrading of Road from Gravel to Concrete Paving | Capital |  | 42079741.27 | 42079741.27 | 0 | MIG | 25979741.27 | 16100000 | 0 |  |  | 25/11/2020 | 19/08/2022 | None | Construction
6. | Paving of Main road from Ndhuna Mandlakazi, Efrika, Zangoma,Mpenyisi to Jamba Cross Internal Street (in Ward 13, Mandlakazi) | Upgrading of Road from Gravel to Concrete Paving | Capital |  | 40863260.82 | 40863260.82 | 0 | MIG | 27463260.82 | 13400000 | 0 |  |  | 23/11/2020 | 07/09/2022 | None | Construction
7. | Paving of N’wamitwa Bridge via Nhlengeleti School to Taxi Rank,Clinic via Lwandlamuni School to N’wamitwa/Mandlakazi Road from gravel to paving | Upgrading of Road from Gravel to Concrete Paving | Capital |  | 34663260.82 | 34663260.82 | 0 | MIG | 27463260.82 | 7200000 | 0 |  |  | 26/11/2020 | 07/09/2022 | None | Construction
8. | Dan Access road from R36 (Scrapyard) to D5011 (TEBA) | Rehabilitation of Road | Capital |  | 30000000 | 30000000 | 0 | MIG | 0 | 7000000 | 23000000 |  |  | N/A | TBC | None | Planning
9. | Installation of High lights at Xihoko, Mandlakazi, Nkowankowa, Mariveni, Lusaka and Sethone | Installation of High Mast Lights | Capital |  | 8400000 | 8400000 | 0 | MIG | 0 | 4200000 | 4200000 |  |  | N/A | TBC | None | Planning
10. | Leretjeni Sports Complex | Construction of the Sports Compex | Capital |  | 11000000 | 11000000 | 0 | MIG | 0 | 11000000 | 0 |  |  | N/A | TBC | None | Design
11. | Bulamahlo Community Hall | Construction of a new Community Hall | Capital |  | 13300000 | 13300000 | 0 | MIG | 0 | 3100000 | 10200000 |  |  | N/A | TBC | None | Planning
12. | Runnymede Sport Facility Phase 2 | Upgrading of the Sports Facility | Capital |  | 18600000 | 18600000 | 0 | MIG | 0 | 0 | 18600000 |  |  | N/A | TBC | None | Planning
13. | 1 X Power Generator for Letsitele water treatment plant | Purchase of a Power Generator for Letsitele water treatment plant | Capital |  | 300000 | 0 | 300000 | Own | 0 | 300000 | 0 | 18/07/2022 | 31/08/2022 | TBC | TBC | None | Planning
14 | Haenertsburg Cemetery road | Rehabilitation Haenertsburg Cemetery road | Capital |  | 4000000 | 0 | 4000000 |  | 0 | 4000000 | 0 | 15/08/2022 | 09/09/2022 | TBC | TBC | None | Planning
15 | Nkowakowa Internal streets (Bankuna, Tambo to Maxakeni Road) | Rehabilitation of Nkowakowa Internal streets (Bankuna, Tambo to Maxakeni Road) | Capital |  | 4000000 | 0 | 4000000 |  | 0 | 4000000 | 0 | 22/08/2022 | 12/09/2022 | TBC | TBC | None | Planning
16 | Lenyenye Internal Streets (Main street to Industrial Area, Stadium, Ithuseng to Main street via Police Station) | Rehabilitation of Lenyenye Internal Streets (Main street to Industrial Area, Stadium, Ithuseng to Main street via Police Station) | Capital |  | 3200000 | 0 | 3200000 |  | 0 | 3200000 | 0 | 22/08/2022 | 12/09/2022 | TBC | TBC | None | Planning
17 | Tar cutting machines and small compactors | Purchasing of tar cutting machines and small compactors | Capital |  | 60000 | 0 | 60000 |  | 0 | 60000 | 0 | 11/07/2022 | 23/08/2022 | TBC | TBC | None | Planning
18 | Walk-behind Roller X 2 | Purchase of Walk-behind Roller X 2 | Capital |  | 500000 | 0 | 500000 |  |  | 500000 | 0 |  |  | TBC | TBC | None | Planning
19 | Fleet Management System | Purchase of Fleet Management System | Capital |  | 1000000 | 0 | 1000000 | Own | 0 | 1000000 | 0 | 11/07/2022 | 27/08/2022 | TBC | TBC | None | Planning
20 | New Guardroom at Civic Centre | New Guardroom at Civic Centre | Capital |  | 40000 | 0 | 40000 | Own | 0 | 40000 | 0 | 31/08/2022 | 24/09/2022 | TBC | TBC | None | Planning
21 | Construction machinery: TLB, Grader | Purchase of 4X TLB, 2X Grader G140 | Capital |  | 3000000 | 0 | 3000000 | Own | 0 | 3000000 | 0 | 11/07/2022 | 27/08/2022 | TBC | TBC | None | Planning
22 | Installation of smoke detectors in municipal buildings | Installation of smoke detectors in municipal buildings and Sub-stations | Capital |  | 500000 | 0 | 500000 | Own | 0 | 500000 | 0 | 12/07/2022 | 03/09/2022 | TBC | TBC | None | Planning
23 | Diagnostic machine and replacement of hydraulic jack and toolbox | Purchase of diagnostic machine and replacement of hydraulic jack and toolbox for the workshop | Capital |  | 100000 | 0 | 100000 | Own | 0 | 100000 | 0 | 12/07/2022 | 03/09/2022 | TBC | TBC | None | Planning
24 | Nkowakowa offices (Old Home Affairs building) | Renovations of Nkowakowa offices (Old Home Affairs building) | Capital |  | 800000 | 0 | 800000 | Own | 0 | 800000 | 0 | 31/08/2022 | 24/09/2022 | TBC | TBC | None | Planning

## CORPORATE SERVICES
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MHANGWANA D
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2022/2023 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022' | 2022/2023' | 2023/2024' | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
CORPORATE SERVICES
7
8
9
10

## COMMUNITY SERVICES
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MHANGWANA D
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2022/2023 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2020/2021 | 2021/2022 | 2022/2023 | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
COMMUNITY SERVICES
| Landfill access control system | Electronic system which records the vehicle registration and license of vehicles entering the landfill site. | Operational |  | R50,000.00 |  | R50,000.00 | Own | 2022-08-01 | 2022-08-22 | Once off | 2022-08-31
| External auditing of landfill site | Auditing of landfill site by a Suitably qualified consulting firm to comply with the TOR of our landfill permit. | Operational |  | R800,000.00 |  | R800,000.00 | Own | 2023-02-06 | 2023-03-09 | Once off | 2023-04-01
| Security Measures for GTM Substations | Protection and Monitirng of Critical Infrastrure | Operational |  | 10280000 | N/A | Yes | Own | TBC | TBC | TBC | 2025 | Moratorium on new Tenders |  | Applying Exemption from National Treasury

## PED
Name of Municipality or Municipal Entity -GREATER TZANEEN MUNICIPALITY
Name of Accounting Officer/Delegated Officer -MHANGWANA D
Signature of Accounting Officer / Delegated Official
Telephone Number and e-mail address-015 307 8002
2022/2023 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project Description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | 2021/2022 | 2022/2023 | 2023/2024 | Preparation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
PED
| LED STRATEGY | REVIEW OF LED STRATEGY |  |  |  |  | R500.000
| SMME STRATEGY | DEVELOPMENT OF SMME STRATEGY |  |  |  |  | R500.000
| TOURISM | DEVELOPMENT OF TOURISM PLAN |  |  |  |  | R500.000
| AGRI EXPO | IMPLEMENTATING OF AGRI EXPO |  |  |  |  | R500.000
| SMME | SUPPORT OF SMME |  |  |  |  | R300.000

## GTEDA
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Project Name | Project description | Type | Contract Number | Estimated Cost (R)/ Budgeted Amount |  |  | Source of Funding | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges | Status | Corrective measures
|  |  | Capital or Operational | (To be provided by SCMU) | Total | Grant | Own funds | (Own/MIG/INEP/DBSA)
GTEDA

## Compatibility Report
Compatibility Report for PROCUREMENT PLAN FOR 2021 2022.xls
Run on 2021/03/25 11:16
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 18 | Excel 97-2003