## Audit Action Plan
Financial Year: 2023/2024
Annexure: Matters Affecting Audit Report
Audit Action Plan Status: All
Line Item | Finding | Detailed finding | Root causes provided identified by AGSA | Insert/enhance the detailed root cause | Proposed action to address detailed root cause |  | Progress | Expected POE | No. of Years Repeated | Responsible Person | Due Date | Management Approval Comments | Choene Maeta Approval Comments | IA Assurance Comments | AC Approval Comments | Council Approved Date | Council Resolution No. | Action Plan Status | Implementation Progress % | Implementation Status | Completed Date | IA Review Date | IA Review Comments | NT/PT Recommendation Considered
| 1. PPE - Incorrect value of land | During the audit of land, it was noted that the recorded values of certain land parcels varied significantly from what would be expected based on the size of the land. Although land is carried at cost, the cost recorded in the asset register did not correlate with the size of the land as such reliance cannot be placed on the values as disclosed in the financial statements. This discrepancy raises concerns about the accuracy of land valuations, which are critical for financial reporting purposes in accordance with GRAP 17 | Management had different methodology and approach of accounting the aforementioned land | Management had different methodology and approach of accounting the aforementioned land | The entire Land and Investment property was revisited for re-evaluating the values through use of the valuer's methodology. The matter was resolved during adjustment and finalisation of the audit. |  | This was resovled and by the nature of this asset class the re=evaluation is done once in three to five years.. | Re-evaluation report to support the updated FAR | 0 | Manager Assets |  | Audit Action Plan Approved | Audit Action Plan Reviewed and Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2023. | Developed (Council Approved) | 100% | Started-Bids are now advertised with minimum threshold in line with SCM reg 22 | 2024-03-01 |  |  | N/A
| 2. Investment property: Overstatement of Investment property | During the audit of Land Investment property we identified land accounted for in the municipal records as part of investment property, however, as per the deeds office the land is registered in the name of private individual and in other instances the land has no registered owner | Investment property must be accounted for in line with GRAP and municipality only account for land that is owned by the municipality | Administrative error on investment property for including land registered in the name of individual | Management will liaise with legal and PED on regular basis to verify property transfer report to identify and correct any properties that might have changed ownership. Continuos meetings will also be held with PED to identify any other new private properties that might have been transfered during the financial year. |  | Monthly transfer reports for the months of July 2024 to November 2024 have already been obtained by the asset division. | Monthly transfer reports | 0 | Manager Assets & PED |  | Audit Action Plan Approved | Audit Action Plan Reviewed and Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Started-Bids are now advertised with minimum threshold in line with SCM reg 22 | 2024-03-01 |  |  | N/A
| 3. PPE : Illegal occupation of municipal land | During the audit of community assets (Park) it was noted that the municipality has land registered in its name, however the land has been illegally occupied as there were physical structures constructed by private individual on the municipal land. | Management didn't ensure that land is accounted for in line with GRAP requirements as the municipality has lost control over the land | Administrative error, Impairment assessment on illegally occupied properties was not adequately conducted | The physical verification of the entire asset register for land and investment property will be conducted and impairement journal will be processed for the illegally occupied land. |  | To enhance communictaion with PED and assets management division on identification of illegally occupied land and the identification of illegally occupied land will be verified during normal assets verification process. | Asset verification report Report from PED on illegally occupied land | 0 | Manager Assets |  | Audit Action Plan Approved | Audit Action Plan Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Started- the draft procedure / criteria has been developed and is circulating for inputs | 2024-03-01 |  |  | N/A
| 4. PPE: Stolen assets not written off | During the audit of PPE, internal memos and reports where stolen assets are reported were requested. These stolen assets were traced back to the asset register to confirm whether they have been written off. Assets were reported as stolen in the internal audit report but were not written off in the asset register therefore resulting in the overstatement of PPE at year end. | To ensure that all stolen assets are reported to Asset department and written off | Administrative error and inadequate review during finalization of stolen assets in the asset register | The communication will be made with the user departmentans to report the stolen asssets timeously, Adequate reconciliation of reported stolen assets vs list of assets to be processed to council for write-off |  | User departments report stolen assets to the asset division and listing is reconciled with reported cases for completeness | Reconciliation report on stolen assets | 0 | Manager Assets |  | Audit Action Plan Approved | Audit Action Plan Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Not Yet Started |  |  |  | N/A
| 5. Revenue – Incorrect interest rate used | The interest charged on outstanding balances for property rates was incorrect, the municipality calculated interest using an incorrect interest rate of 9.25%, being the 8.25% plus the 1%. The prime rate as at 1 July 2023 is 11.75%, as such the correct interest rate to be applied was supposed to be 12.75%, being prime of 11.75 plus 1 as per approved tariffs Interest was understated by 3.5% and the difference noted results in a projected understatement of Revenue property fines and penalties is R 2 133 836 | Tariff update was not done adequately on the module to update interest rate for the year | Tariff update was not done adequately on the module to update interest rateon property rates for the year | Reconciliation for update of tariffs and inetrest rates will be performed in the beginning of the year to determine the accury of uploaded tariffs/ interest to ensure that relevant prime rate is used to account for the interest rate charged. |  | The interest rate for 2024/25 has since been updated on the billing system and the interest is charged adequately The matter has been resolved | Extract of interest charges from billing system | 0 | Manager Revenue |  | Audit Action Plan Approved | Action Plan Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Started-Bids are now advertised with minimum threshold in line with SCM reg 22 |  |  |  | N/A
| 6. Misstatement of Contingent liabilities | The description of the case below suggests that the municipality is actively seeking to recover the land or the value of such land from the developer, being Phadima Phadima Group There is a possible inflow rather than an outflow of resources and the obligation for the inflow rests with Phadima Phadima Group and the matter is to be determined through a legal process, as such, the case should be disclosed as a contingent asset and not contingent liability | Incorrect classification | Incorrect classification | The matter was resolved during adjustment of AFS and finalisation of the audit to ensure that contingent liabilities and contingent assets are properly disclosed on the AFS. |  | The matter was resolved and all contingent liability and assets are disclossed adequately | Disclosure note of contigent liability and assets | 0 | Manager Legal & CFO |  | Audit Action Plan Approved | Audit Action Plan Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Not Yet Started |  |  |  | N/A
| 7. Legal fees – Maria Malatji and Bernard Tongue | • The Municipality was a defendant in two legal matters launched by Maria Malatji and Bernard Tongue for the following cases o Maria Malatji – Maria Malatji filed a lawsuit against the municipality for R1 000 000 in damages sustained by her property. This was attributed to the construction activities conducted by the municipality in her vicinity. A settlement was reached the Municipality paid a settlement fee of R100 000 o Bernard Tongue - It was noted that Bernado Tongue filed a lawsuit against the municipality for R1 000 000 in damages sustained by his property. This was attributed to the construction activities conducted by the municipality in her vicinity A settlement was reached the Municipality paid a settlement fee of R100 000 • Both matters were heard and finalised by the high court on 19-July-2023 • The attorney handling the cases have billed the municipality twice for the same work done on the same day, for example, consultation with the municipality was billed twice, travelling on the same day to court was billed twice, appearing in court for 8 hours was billed twice, research on the case was billed twice The double charge or billing results in the incurrence of fruitless expenditure as there are no additional benefits that were derived by the municipality from the payments made | Management didn't exercise an oversight responsibility regarding the prevention of incurrence of fruitless expenditure. | Inadequate clarification on the invoices that the matters were handled by two different senior attorneys. Inadequate review of submitted supporting documents to substintiate invoices | 1.Issue out supplementary instructions or communication to panel attorneys instructing them that invoices should indicate the full name and surname of the attorney(s) handling the case. 2. Where one or more attorneys or advocates are are handling the same case, the statement of account (invoice) should clearly indicate the attorney or advocate who rendered a specific item. 3. Where an attorney or advocate travelled in execution of the mandate, the details of the motor vehicle used should be attached to the invoice. 4. Charges for court appearances should be supported by a copy of court appearnce record for the specific date. 5. An invoice which does not comply with the above requirements will not be processed for payment until the requirements are fulfilled. 6.The fruitless expenditure will be recovered from the future claims of T.J Machete Attorneys as they are currently handling other cases for the Municipality. T.J Machete Attorneys will be formally informed of the recovery of the fruitless expenditure. |  | The invoices are now processed with details of attorneys handling the matter and copy of court appearance Draft letter of recovery has been prepared to notify the attorney on deduction of duplicate payment | Letter issued to the attorney Proof of recovery supporting documents of invoices | 1 | Manager Legal |  | Audit Action Plan Reviewed and Approved | Audit Action Plan Reviewed and Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Started- CSD report is generated to identify providers in the service of state institutions the service provider sign the MBD 4 Cllrs declared interest |  |  |  | N/A
| 8. Consulting costs – Payment for consulting services (Asset management) | Contrary to the above the following was noted: • The municipality has placed over-reliance on the use of consultants and has not reduced the costs of assets consultants in the current financial year. • The cost of asset management consultants has increased by 24.5% from prior year to current year, whereas the entity has received an unqualified audit option and was expected to reduce the costs of consultants • The Municipality incurred consulting costs amounting to R5 886 690 in relation to the 2022/23 financial year as follows: | There was no reduction of the over-reliance on consultants and vacancies were not filled. | Reliance on the use of consultants The municipality developed a Consultancy Reduction Plan during the 2023/2024 Financial Year, which clearly entails the steps to be taken by management to reduce reliance on consultants. As per the GAP analysis performed by the management prior to the appointment of consultants, management indicated that the Division is understaffed. During the 2024/2025 Budget engagements two senior positions were budgeted to enhance capacity with asset management unit. The posts have since been advertised. Cost of asset management consultants The calculation of average cost for remaining period of the contract is not necessarily accurate, the cost for remaining months is lower due insignificant work as compared to work undertaken during compilation of asset register. The projected project cost will be curbed at R6.5 million, this implies that the expenditure will not exceed R6.5million. Based on the Auditors calculation for prior year of R5 886 690 and envisaged current year expenditure of R6500 0000, the increase on use of consultant is 10%. In 2022/23, the municipality appointed consultants late and adopted risk based approach while in 2023/24 the consultants were appointed early and adopted comprehensive asset verification and valuations. Furthermore, the value of assets increased significantly. The use of consultants was as a result of inadequate capacity within asset management | To capacitate the asset management unit in order to reduce over-reliance on consultants. Appointment of additional persornel This will reduce cost on use of consultants, some of work will be performed internally |  | Two post have been advertised to supplement current human capital and some of work will be performed internally | Reduced cost of consultants Proof of enhanced capacity within assets | 0 | Chief Financial Officer |  | Audit Action Plan Reviewed and Approved | Audit Action Plan Reviewed and Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Not Yet Started |  |  |  | N/A
| 9. Expenditure Management - Fleet management | The municipality has a contract with ABSA for fleet management, the municipality will provide a list to ABSA, and the bank will issue a petrol card with the vehicle registration which gives the vehicle access to refuel using the card. Monthly the municipality will receive a transaction level report for filling and to support the monthly debit order. For the year under review we reviewed the transaction level report and verified the vehicles, it was therefore noted that the municipality has paid for fuel consumption and monthly administration fee on vehicles that were not operational. As a result, the municipality has incurred financial loss and fruitless expenditure. | Management didn't ensure that vehicles that are written off and no longer operation are removed from the ABSA fleet management register | Management didn't ensure that vehicles that are written off and no longer operation are removed from the ABSA fleet management register | fleet management register will be upated on monthly basis. |  | Fleet management reconciliation is compiled to ensure stationary and written off vehicles are verified and registered. | Email correspondences with user departments and ABSA Fleet Management Division; and Asset Write off Report | 0 | Manager Expenditure & Fleet |  | The Audit Action Plan is reviewed and approved | The audit action plan is reviewed and approved | Adit finding action plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Not Yet Started |  |  |  | N/A
| 10. Expenditure management – Invalid indigents subsidised through free basic electricity (FBE) | during the audit of indigent consumers who receive free basic electricity through the indigent programme, it was noted that there are many indigent consumers who do not meet the criteria to be regarded indigents and other provided invalid information. As a result the municipality incurred fruitless expenditure on the Free Basic Electricity (FBE) expenditure which also amounts to a material financial loss, the accumulated amount over two years is R1 817 007.93 The amount is even higher when considering the prior financial years due to the extent or numbers to indigent consumers who do not qualify for Free Basic Electricity | Adequate controls weren't ensure implemented to only valid beneficiaries of the indigent subsidy qualify for the subsidy, and to ensure that the free basic electricity is allocated in terms of the indigent policy | Inadequate vetting of indigents in the past and year under review | The municipality has taken a proactive steps in 2024/25 by vetting new applications and existing indigent register to detect deacesed indigents and income level. Subsequent to issuance of the finding, management reviewed indigent register and removed indigent flagged by AGSA |  | Reconciliation of indigent register against vetting results and indigents flagged by AGSA has been performed, and the indigent register is up to date | Reconcilation report Updated indigent register | 0 | Manager Revenue |  | Audit Action Plan is Reviewed and approved | Audit Action Plan is Reviewed and approved | Audit finding action plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Not Yet Started |  |  |  | N/A
| 11. Overtime – Excessive overtime: Overtime in excess of basic salaries | During the year under review the municipality incurred overtime amounting to R30 639 916, this was an increase of R 1 724 478 when compared to prior year amount of R28 915 438 Employees of the municipality have earned excessive overtime and in most months the overtime payment exceeded the basic salary There is inadequate control measures implemented by the municipality to manage overtime; 10 employees earned overtime totalling R5 710 405,97 | Management didn't ensure that employees comply with the overtime policy | Community Services : The excessive overtime is caused by schedules for saturday and sunday to conduct litter picking and cleaning of council facilities for puplic use . > Electrical Engineering : The excessive overtime was caused by loadshedding for 10 employees whom the overtime led to the monitory valeue of R5m per annum and emergency work due to natual cuases. >Engineering Services : excisive overtime is caused by water shedding schedules and aging infurustcture for water and sewere. And supply of water through tankers in the villages. | Engineering , Electrcial and Community Services :Introduction of 6 day work system and shift system. Electrical : Appoointment of additional electricans. |  | "Community Services : The department has reduced overtime from 8 hours to 6 hours on Saturday and Sunday. Electrcial Engineering : Reduction of hours ,monitoring and rotation of electricians. And there is improvement in the network perfromance. Engineering Services : Prioritisation of emergecy work only and adequate monitoring of overtime Other support departments( finance, corporate services and MM's office)- adequate implementation and monitoring of overtime tool | Schedule of workplan Monthly consolidated overtime report to detect reduction in overtime | 0 | Directors of service Departments |  | Audit Action Plan Reviewed and Approved | Audit Action Plan Reviewed and Approved | Audit finding action plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Not Yet Started |  |  |  | N/A
| 12. Employees were paid overtime, while outside the overtime salary threshold | During the audit of overtime, it was noted that the employees were compensated for overtime worked by monetary payment even though their basic salary is above the threshold R224 080-48, and they should have been compensated by means of time off in accordance with the overtime policy. | Management didn't ensure that municipal employees comply with the overtime policy and gazzeted salary threshold determinations. | The policy made a provision to work overtime in excess of the threshold as most of employees are above the prescribed threshold and such restriction will have significant impact on service delivery and overall performance of the institution | An advise was sought from the Department of Labour, that should the municipality wish to pay in excess of the aforementioned threshold such should be stated in the policy. Refer to the attached correspondence |  | The advise will be included and enhanced on the reviewed policy during the 2025/26 FY | Reviewed Policy and Minutes of the LLF. | 2 | Director Electrical |  | Approved | [5 empty] | Developed (Management Approved) | 10% | Started- Development of procedures for transfer and regsitering of properties in progress. Amendments of SLA with service providers on the panel is in progress | 20-Dec-2023 |  |  | N/A
| 13. Overtime hours worked not pre-approved. | All employees selected for audit were found to have had the overtime authorization documents approved after the actual overtime was worked in contravention of the overtime policy as stated above. | Management didn't ensure that proper overtime control measures are implemented. | The departmental Administrator collates approved Timesheets, pre- approval forms and memos for Electrical Department with the consolidated long list constituting Overtime and Standby claims (as supporting document to Timesheets) to Salaries Unit for processing. However detailed record is kept by the User Department. | Management will ensure that approved pre-approvals/memo are attached to timesheets for overtime claim. |  | Payroll officials verified that approved pre-approval, Long List from Electrical Department and Memo are attached to timesheets for overtime claim. | Approved pre-approval, Long List from Electrical Department and Memo | 2 | Manager Expenditure & Manager O&M Electrical |  | According to the first signed Agreement the disposal was done in terms of SCM process.(see the attached copy of the signed). | Audit Action Plan Approved | Action to address finding is not clear | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 30% | In Progress |  |  |  | N/A
| 14. Overtime - Excessive hours per month | it was noted that overtime has been excessively worked and claimed by emergency employees against the guidelines of the municipality | Management didn't ensure that employees comply with the overtime policy | Load Shedding is Implemented National as Emergency this accumulate high hours together with the normal emergency overtime | Implementation of overtime reduction plans by respective service departments |  | "Community Services : The department has reduced overtime from 8 hours to 6 hours on Saturday and Sunday. Electrcial Engineering : Reduction of hours ,monitoring and rotation of electricians. And there is improvement in the network perfromance. Engineering Services : Prioritisation of emergecy work only and adequate monitoring of overtime |  | 2 | Directors of service Departments |  | Action Plan Approved | Action Plan Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 100% | Completed and resolved during the audit |  |  |  | N/A
| 15. Leave encashment- Calculations not in line with the Basic condition of employment act. | During the audit of leave encashment, it was noted that the calculation for leave encashment included overtime as part of the total basis salary. In terms of the BCEA, overtime should not be included as part the leave encashment calculation, as such, there has been a material overpayment of leave encashment. Not all employees receive overtime payment, in this regard those with overtime will always receive an overstated amount of leave encashment | Calculation of employee's remuneration in terms of Section 35(5) of Basic Conditions of Employment Act, 1997 Accrued Staff Leave calculation is based on Total Earnings /divided by 21.67, multiply by No of Leave Days Available Leave encashment constitutes taxable remuneration irrespective of the fact that not all employees are entitled or approved to receive the same benefits or allowances. Hence is it regarded (classified) as earnings. | Historic system calculation error, and the error stemmed from an improperly configured calculation within our legacy system, which inadvertently led to fruitless expenditure in the current year and correction in prior year | The leave pay linked formula on PAY DAY has been revised by removing the average overtime line item from total earnings. |  | Accrued Staff Leave formula for leave encashment calculation has been revised by removing the following non fixed cash items The matter has been resolved | Leave encashment calculation/reconciliation | 2 | Manager Expenditure |  | Approved | Audit Action Plan Approved | Action plan audit finding is sufficient. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Started - the MPAC is curretly conducting investigations |  |  |  | N/A
| 16. CAATs interest family | During the year under review, the municipality did business with people whom their family members are employed by the state and no declaration of interest was made on the MBD 4 | The municipality rely on CSD and does not have access to CAATs to detect family members | The municipality rely on CSD and does not have access to CAATs to detect family members | The relevant officials and Cllrs were engaged including the service providers for adequate declaration Notice will be issued to all staff and cllrs on adequate declaration of interest Adequate completion will be emphasised during briefing sessions to ensure that suppliers understand MBD4 |  | Draft memorandums have been developed to notify staff and cllrs on adequate declaration Identfied official and cllr have completed declaration form Suppliers were notified to declare on MBD4 should they wish to bid in the municipality | Issued memos Declaration forms of the identfied cllrs and officials communication with the suppliers | 0 | Manager SCM |  | Audit Action Plan reviewed and approved. | Audit Action Plan Approved. | The control indicated on the action plan is not clear to avoid recurrence of the finding. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 0% | Not Yet Started | 22-Jan-2024 |  |  | N/A
| 17. Traffic fines - Traffic fines withdrawn without appropriate approval | Traffic fine tickets that were withdrawn without being authorized by the relevant authority. This results in a misstatement of receivables for the 2023/2024 financial year | Management oversight for not signing off invalid/inaccurate tickets upon withdrawal | Tickets are withdrawn in scenarios where incorrect/inadequate information is captured on the tickets. The tickets in question are not recoverable due to incorrect/inadequate information to enforce recovery or follow-up; however, management acknowledges administrative errors of not signing-off invalid tickets for recovery Management oversight for not signing off invalid/inaccurate tickets upon withdrawal | The unit has since verified all the tickets to ensure that invalid tickets are signed Perform monthly verification to determine that all tickets are adequately signed and filled adequately |  | Verification of are performed to ensure tickets are signed before filling | Signed invalid tickets | 0 | Manager Traffic & Licencing |  | Audit Action Plan Reviewed and Approved | Audit Action Plan Reviewed and Approved | Audit finding action plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Started- draft consultancy reduction plan has been develped, which encapsulate gap anayisis |  |  |  | N/A
| 18. Traffic fines reduction processed without approval from the Chief traffic officer | traffic fine reduction applications were processed and included in the balance of receivables even though the reduction applications were not approved by the chief traffic officer. This results in a misstatement of traffic fine receivables | Management oversight on the completeness of office use processes. | Traffic fines paid promptly (early bird) are subject to a discount to encourage offenders to pay traffic fines, where customers would have paid and deemed the tickets as finalized. However, the municipality made an administrative error by not completing the final stage of office use. The offender met the requirements for reduction and paid the ticket accordingly Management oversight on the completeness of office use processes. | The unit will verified all the reduced tickets are signed by Chief traffic officer before filling and processed Perform monthly verification to determine that all tickets are adequately signed and filled adequately |  | Verification of are performed to ensure tickets are approved before are being processed | approved reduced tickets | 0 | Manager Traffic & Licencing |  | The ICT steering committee charter to be reviewed. | Audit Action Plan Approved | The control indicated in the action plan is not clear to avoid recurrence of the finding. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Not Yet Started |  |  |  | N/A
| 19. Traffic fine - Traffic fine withdrawn without a valid reason | During the audit of traffic fines, we noted that there was an instance of a traffic fine ticket that was withdrawn without a valid reason. | Oversight by management for indicating an error on the ticket and without providing handwritten reasons. | the reason for the withdrawal of the ticket stated above was due to the incorrect name being displayed; however, this was marked/circled as an indication of error. The circled area sought to indicate an error, which serves as a basis for withdrawal. Management acknowledges that there should have been further indication or handwritten reasons. | The unit will provide explanation of withdrwal of tickes and verify that explanation is provided before filling Perform monthly verification to determine that all tickets have adequate explanation for withdrawal |  | Verification of are performed to ensure tickets have adequate explanation | withdrawal tickets with necessary explanation | 0 | Manager Traffic & Licencing |  | N/A | [5 empty] | Developed (Management Approved) | 100% | Completed | 22-Jan-2024 |  |  | N/A
| 20. Prepayments – Payments not set-off against customer accounts | During the audit of prepayments, we noted that there are payments that are made by customers for what has been billed to them for the different service charges. These payments have been allocated to incorrect accounts which are inactive and not being billed, as such the payments made by the customer were incorrectly classified as prepayments | Unknown deposits were allocated to one debtor account no 16 to be able to identify the monetary value of those payments that we were not able to allocate to an identified debtor. Payments non-identification has escalated as the debtor will indicate account number on beneficiary transfer but when we receive it on our bank statement the reference will not show, only our bank account reference will show which make it impossible to allocate if the debtor does not give us the proof of payment. | Unknown deposits were allocated to one debtor account no 16 to be able to identify the monetary value of those payments that we were not able to allocate to an identified debtor. Payments non-identification has escalated as the debtor will indicate account number on beneficiary transfer but when we receive it on our bank statement the reference will not show, only our bank account reference will show which make it impossible to allocate if the debtor does not give us the proof of payment. | Reconciliation of credits to acc 16 for identification and allocation to debtors accounts and/or vote receipts Absa bank need to resolve the issue of no reference on the bankstatement and consumers urged to send proof of payments to cash control at payments@tzaneen.gov.za. | The accounting officer should ensure that amounts received are recorded into the correct accounts as this will assist reducing the high balance of receivables, ensure that correct interest is charged on outstanding consumer balances and that the impairment is correctly calculated and customers who pay their accounts are excluded from the impairment. Where amounts are received from unknown sources this should be correctly classified as unknown deposits under payables. | Perform reconciliation of credits to acc 16 for identification and allocation to debtors accounts and/or vote receipts Trace unallocated deposits and allocate to relevant accounts, notice to public has been issued to inform customers that their deposits has not been allocated to engage the municipality Regular engagements with Absa to correct their implementation of role(programming) to have reference number of clients to appear on municipal statements | Decrease/ clearing amount allocated to acc 16 and identification of paymets made. | 0 | Manager Revenue |  | Audit Action Plan Reviewed and approved | Audit Action Plan Reviewed and approved. | Audit action plan does not address the audit finding. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 16% | In Progress- the process has commenced with the identification of disputed accounts on intergovernmental debt | 18-Dec-2023 |  |  | N/A
| 21. Bad debt written off differs to approved council write - off | During the audit of receivables it was noted that the municipality wrote off bad debt amounting to R46 410 149.65. However, through inspection of the council resolutions, we noted that council only approved bad debt write-off amounting to R45 940 978. This results in a difference of R469 170.77. | Management considered the following month balance given past experience of delay in approval of council items | During the process of preparing the w/off report to Council, management used the current balance on the debtors system for the purpose of the report on the premise that should the approval and write-off not being within the same month that we present the report the balances accumulate interest and when we do the actual write-off the balances at that stage will be regarded for write-off and it does practically happen that the presented balance is less than the write-off actual amount. | Write-off report need to be approved by Council in the month we present to enable write-off amounts to correspond with approved write-off amount or alternatively when we do write-off report all interest charges should be stop on accounts presented to prevent accumulation of amounts on these accounts if the write-off is not done timeously. | Ensuring that irrecoverable debt written off is the same amount as what has been approved by council prior to being included in the final AFS | Only applicable when new write-off reports are compiled. The matter was resolved with AGSA | N/a | 0 | Manager Revenue |  | Audit action plan reviewed and approved | Audit Action Plan Reviewed and Approved | Audit finding action plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 20% | In Progress- payment advance reports have been reviewed and reconcilied | 18-Dec-2023 |  |  | N/A
| 22. Distribution losses | The distribution loss disclosed in the financial statements indicates a substantial electricity loss for the year under review. In the current financial year electricity amounting to R67 724 198 (11%) was lost through distribution loss. During finalisation of the audit, an arithmetical error was identified and the losses increased to 17%, which is above the tolarable range of 5%-12% | Management didn't ensure that proper controls were in place to manage and curb the distribution losses during the year. | Technical losses, illegal connection and possible losses through estimates consumption Inadequate implementation of internal controls to curb or reduce distribution losses | 1.Revenue should ensure that all electrical meters are billed with actual readings every third month and closely monitor estimates accounts 2.Reviewing of the system used to estimate consumption for meters not read. 3.Establishment of a revenue and electrical department war room to meet bi weekly and tackle electricity meters challenges timeously. 4.Revenue need to come up with a strategy to reduce the high number of estimates and journals being pass through the billing system, as the infuence the number of units sold in a month. 5.Estimates calculated by the EMS system must be review as they contribute to the number of units sold in a particular month, either positive of in a negative way. 6. Meter verification/audit to detect illegal connection 7.Investigation of prepaid meters with no recharge for longer period or low consumption for anticipated high usage meters 8. Data purification on billing system |  | war room meeting between Revenue and Electrical to take place on the 04 February 2025 Revenue enhancement steering committee has been resucitated, the meeting was held on the 17 January 2025, the task include among others reduction of distribution losses and revenue protection Monthly calculation of distribution losses verification of possible illegal connection is undertaken during meter readings | Reduction in electricity losses by end of the 3rd Quarter. Reduction in the number estimates older than 2 months. Report on the number of meters requiring electrical engineering department to attend them Revenue collection reports Monthly distribution losses report | 0 | Director Electrical |  | Audit Action Plan Reviewed and Approved | Audit Action Plan Reviewed and Approved | Addition on detailed audit finding. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 100% | Completed | 18-Dec-2023 |  |  | N/A
| 23. Lack of regular meetings by the ICT steering committee | During the audit of IT management we noted that during the 2023/2024 financial year, the IT steering committee of Greater Tzaneen municipality only met once (1), which is in contravention of the ICT steering committee charter | The ICT Steering Committee charter was approved in July 2022, and the municipality had challenges of convening the meetings due to non-appointment of the chairperson. | The ICT Steering Committee charter was approved in July 2022, and the municipality had challenges of convening the meetings due to non-appointment of the chairperson | The ICT steering committee has been establish and the meeting are held on quaterly basis | The ICT steering committee has been establish and the meeting are held on quaterly basis | The ICT steering committee has been establish and the meeting are held on quaterly basis The matter is resolved | Minutes and attendance register of the steering committee | 1 | Manager IT |  | Audit Action Plan Reviewe and approved | Audit Action plan reviewed and approved | Audit finding action plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 100% | Completed | 18-Dec-2023 |  |  | N/A
| 24. Water tanker services | The water tanker service requisitions were issued to the different service providers after the service had already been rendered or in the process of being rendered. Furthermore, we noted that the different orders were issued close to the invoice date or on the invoice date. | Essential Services delivery to community which cannot be halted. | • The service of water tankers in most instances is a result of emergency (pipe burst/vandalized pumpstations/stolen cables and transformer) and planned outage or maintenance. • As a result, the municipality is obliged to act swiftly due to demand of an essential service in the community. To restore the pump stations or repair pipe burst it may take amount of time, at times the municipality activate the service providers from the panel who are paid on rates and rotation basis. The consequence of waiting for formalities, approval of memorandums and issuing of orders because some incidents happen on weekend or after hours may result in community unrest/ protest. • In some instances, the municipality is obliged to activate additional water tanker than planned due to high demand and pressure from the community. It should be understood that the municipality has no control over this but to act swiftly and in spirit of humanity and service delivery under circumstances. • The municipality experienced issues of community protest in the past, hence opted to act swiftly on the provision of water as essential service. • The order for such rendered service was later issued, the number of days are aligned to the issued purchase order. The service is not provided on quotation but rate basis. Though, the formalities were activated during the process of rendering the service it meets the objective of section 217 of the constitution, which advocate the principle of fairness, equitable and transparency, during award or issuing of orders. Service providers are selected on rotation basis using accepted/standard rate, the purchase order serve as a formalization of allocated work. • It should be noted that the municipality appointed the service providers to render the service as and when required; however, there is an element of emergency where order are issued immediately during the activation of the service. Paperwork leading to the release of purchase orders are prepared during the week and at times it may be impractical to have purchase order for incident that occurred on weekend or at night because the municipality should release water tankers the next morning or immediately. • In terms of alignment of figures as per agreed rates and number of allocated dates, the municipality is compliant and acknowledge the deficiency of service being activated while waiting for formalities because the circumstances of pipe burst/vandalism among others is not within our control but bound to act swiftly and assist community and minimize protest | The municipality has ceased the procurement of water tankering services since December 2023, the function is performed by Mopani District Municipality. The matter is resolved | The municipality has ceased the procurement of water tankering services since December 2023, the function is performed by Mopani District Municipality. The matter is resolved | The municipality has ceased the procurement of water tankering services since December 2023, the function is performed by Mopani District Municipality. The matter is resolved | Extract from GL to substintiate that the municipality is no longer paying water tankering services | 1 | Manager Water Services |  | network upgrade and line refurbishment projects. | Audit Action Plan Approved | Audit plan for audit finding is sufficient. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 29% | In Progress |  |  |  | N/A
| 25. Dilapidated municipal property and loss of public resources | • On 21 October 2022 AGSA issued a finding on the condition of the municipal property that was dilapidated. • The property has been neglected by the municipality resulting in its extreme dilapidation. • To date there has not been any action on the restoration or possible use of the property, as such the municipality has misused a public resource | Dilapidated structure, management didn't ensure that Investment properties are maintained in a good condition and are held for capital appreciation or to earn rental income | Process are under way to demolish the structure given that is no the structure is no longer in good state for occupation and it may cost the municipality high cost to resuscitate the building. | The structure has since been demolish due to poor state of condition and occupation and it may cost the municipality high cost to resuscitate the building. | Process are under way to demolish the structure given that is no the structure is no longer in good state for occupation and it may cost the municipality high cost to resuscitate the building. | The matter would now be resolved | Inspection / Pictures to ensure that the structure is demolished | 0 | Director Engineering and PED |  | Action Plan Approved | Action Plan Approved | Audit Finding Action Plan verified and validated. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) |  | Started- draft consultancy reduction plan has been develped, which encapsulate gap anayisis |  |  |  | N/A
[12 empty] | Approved | [5 empty] | Developed (Management Approved) |  | Not Yet Started |  |  |  | N/A
[12 empty] | implemented | Audit Action Plan Approved | Action plan for audit finding is sufficient. | Audit committee noted the action plan with inputs on the 23rd January 2024. | 01-Feb-2024 | Council approved Audit Action Plan on the 25th January 2024. | Developed (Council Approved) | 62% | In Progress | 21-Jan-2024 |  |  | N/A