## STRATEGIC RISKS 2023 2024 FY
No | Link to objective |  | Link Objectives | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | Rating | Current controls | Perceived control effectiveness | Rating | Residual risk | RRR | Risk owner | Actions to improve management of the risk | Means of verification | Action owner | QRT 1 | QRT 2 | QRT 3 | QRT 4 | Budget
|  | 1 | Efficient and effective administration | Good governance | Agency not established in line with MFMA Sec 84 as a municipal entity subsection 1 (a) and (b) | 1. The mandate of the entity is not transferred which poses a threat to the entity’s going concern.. 2. No collaboration between the entity and LED-PED 3. Registration of Tax liabilities( removed) | Duplications of functions between PED (LED) and Gteda (municipal entity) | Critical | 5 | Common | 5 | High | 25 | SLA betweeen GTM and GTEDA Draft report on the legal status of the agency | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1&2.Continue to advice the municipal council ro comply in terms of MFMA Section 84 subsec 1(a) and (b) 2. Appoint CEO ( removed) 3. Request Treasury to advise on the step by step process of regularising the municipal entity( removed) 3.The parent municipality must write the letter to the entity to agree on the tax liabilities.( removed) 4. The entity to apply for tax exemption from SARS upon receipt of the letter from the parent municipality.( removed) | 1. Minutes of meeting between GTM and GTEDA 2. Appointment letter of CEO( removed) 3. Feedback from treasury( removed) 4. Letter fom municipality to entity costituting the municipal stand-point with regard to tax liability( removed) 5. Approval from SARS partaining to tax exemption( removed) | Director PED and CEO GTEDA | 1&2 Feedback From COGHSTA(Report) |  |  |  | R0.00
1 | Efficient and Effective administration | 2 | Efficient and effective administration | Good governance | 1. Excessive Overtime hours | 1.Excessive payments done beyond what is indicated in the overtime policy as approved by Council. 2.Non implementation of overtime ministerial threshold (R241 110.59 - 1 March 2023) ( removed) 3.Non-compliance with the overtime guiding tool.( removed) | Audit findings, Health of the affected officials due to possible fatigue Abuse of overtime Litigation Possible financial Loss Negative impact on service delivery | Critical | 5 | Common | 5 | High | 25 | Approved overtime policy, Overtime guiding tool Basic Conditions of Employment Act, Internal Circular on Pre -Approvals of overtime Gazzette about the ministerial threshold | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Monitoring of overtime trends in respective departments. 1b.Ensure departments limit overtime hours and align them to what has been prescibed as per the overtime policy 2.Seek clarity from department of labour to assist with the clarification of law on the interpretation of law of the overtime threshold( removed) 2.Ensure the implementation of overtime Ministerial threshhold by monitoring pre approval of overtime( proposal) 3.Reviewal of the overtime policy and send it to council for approval and amend the overtime guiding tool ( removed) | Council resolution, Management minutes on Reviewed overtime tool, Quarterly Council Resolution for approval of overtime above threshold. Letter and response from the Department of Labour for clarity seeking. | Directors | 1.Quarterly overtime monitoring report 1b.Overtime monitoring Report 2. Letter to the Department of Labour for clarity seeking. ( removed) | 1.Quarterly overtime monitoring report 1b. Pre-Approvals , Emergency Memorandums. 3.Management minutes on Reviewed overtime tool( removed) | 1.Quarterly overtime monitoring report 1b.Pre-Approvals , Emergency Memorandums | 1.Quarterly overtime monitoring report 1b.Pre-Approvals , Emergency Memorandums | R0.00
|  | 3 | Optimise and sustain infrastructure investment and services | Service Delivery | Aging infrastructure | 1.Inadequate implementation of maintenance plans and (outdated)Master Plans 2. Insufficient mantainance budget | Poor delivery of services Public protest High costs of maintenance & replacements | Critical | 5 | Common | 5 | High | 25 | Infrastucture Maintenance plan Electrical Master Plans Monthly Inspection report Outage and Mantainance Report | Weak | 0.8 | High | 20 | Accounting Officer | 1.Ensure the implentation of the maintenance plans and Master Plans and perform reactive maintenance as and when required. 1b. Advocate for the appointment of a service provider to review the Master plans. 2.Advocate for Budget increase at the end of the financial year | Quarterly inspections report | 1&2.Directors: Electrical Services. Director Engineering Services | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports | 1.Monthly Mantainance reports and Approved master plans 1b. Internal Memo(budget increase) 2. Approved IDP | R0.00
2 | Optimize and sustain infrastructure investment and services | 4 | Improve access to sustainable and affordable services | Service Delivery | Non adherence of the service level agreement between Water Service Authority ( Mopani District Municipality) and Water Service Provider (Greater Tzaneen Municipality) | 1.Lepele is invoicing GTM for bulk purchases of which is the responsibility of the WSA according to the agreement.( bill not being paid) | Financial loss, GTM incurring the costs of maintenance of infrastructure on behalf of the MDM cash flow constraints Poor service delivery Community Protests | Critical | 5 | Common | 5 | High | 25 | IGR meetings about the SLA between MDM & GTM (Water service authority & Water service provider) Continuos meetings between GTM and MDM, service level agreement | weak | 0.8 | High | 20 | Accounting Officer | Conduct meetings with Lepele, MDM and GTM(Bill settlent). | Progress reports on the implementation of the SLA, | Director: Civil Engineering Services | attendance register and minutes | attendance register and minutes | attendance register and minutes | attendance register and minutes | R0.00
4 | Efficient and Effective administration | 5 | Efficient and effective administration | Good governance | Fraud and corruption - (abuse of municipal vehicles, abuse of fuel, abuse of overtime) | 1.Weak systems of control, 2.manipulation of internal controls, 3.unethical behaviour, | Audit findings; Financial loss, Reputational damage, | Critical | 5 | Common | 5 | High | 25 | awareness to all staff and municipal stakeholders, Approved policies: anti-fraud and corruption, Whistle blowing, fraud prevention plan Anti-corruption hotline Fraud risk register has been developed, Anti-corruption strategy | saisfactory | 0.65 | High | 16.25 | MM | 1-3. Continue to conduct/ raise Awareness on fraud , ethics and corruption. | Investigation report (if any), attendance regsiter for attendance of the workshop, request send to Communications and Marketing about the anti-corruption messages) | CRO | 1-3. Attendance register/communique sent on awareness |  | 1-3. Attendance register/communique sent on awareness |  | R0.00
5 | Efficient and Effective administration | 6 | Efficient and effective administration | Good governance | Non adherence with the reporting format in the Electronic Performance management System. | 1.Inaccurate performance management reporting(Actuals reported and PoEs submmitted/ attached not addressing KPIs (not aligned with reported information) | Audit findings, Lack of credible reports Misalignment of information | Critical | 5 | Common | 5 | High | 25 | Quarterly performance report, APR, SDBIP, Internal Audit reports on performance of information Refresher trainings/workshops | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Continue to conduct refresher trainings/workshops as and well required. | Quarterly SDBIP report | Directors | 1. Attendance register( confirm Quarterly POE) | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | Quarterly Internal Audit performance of information reports and quarterly SDBIP report | R0.00
To be reviewed by the Risk Office |  | 7 | Efficient and effective administration | Good governance | 1% of personnel budget not fully allocated as per the requirements of Skills Development Act [SDA] | 1.Insufficient training budget on all functions of compliance | Low staff morale, incompetences, Fines & penalties, | Critical | 5 | Common | 5 | High | 25 | WSP, Training plans, | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Accept the risk | Signed Budget Council Resolution. | CFO Director Corporate Services | Continuos training | Continuos training | Continuos training | 1. Approved budget by Council.( confirm POE) | R0.00
6 | Improve access to affordable basic services | 8 | Improve access to sustainable and affordable services | service delivery | Increasing theft and loss of infrastructure | 1.Social issues in the country (unemployment, loadshedding) 2.Absence of security at certain areas. 3.Non-adherence with asset management policy 4.Negligence and lack of safeguarding of municipal assets(loss through theft) | Financial loss, Loss of critical information/data, audit findings, Inconsistent security checks, | Critical | 5 | Common | 5 | High | 25 | security guards, cameras, security technology penalties imposed equivalent to the cost of the item, community policing forums | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Ensure establishment of community policing forums . 1b.Conduct awareness workshops to address social crimes with the comminities 2.Identify and list all Municipal assests to be safeguarged. 3.Inform council about the stolen and replaced assests. 4..Conduct awareness workshops to address negligence and lack of safeguarding of municipal assets | Number of SAPS cases partaning reported cases | Director Comminity Services. | 1. Quartely Report | 1. Quartely Report 1b.Invitation and Attendance Registers 2.Report(Municipal Assets and Municipal Assets location) 4.Invitation and Attendance Registers | 1. Quartely Report | 1. Quartely Report 1b.Invitation and Attendance Registers 3. Council Resolution 4.Invitation and Attendance Registers | R0.00
7 | Efficient and Effective administration | 9 | Efficient and effective administration | Good governance | Non-compliance with SCM policy and regulations. | 1. Lack of forward planning 2. Non-adherence to SCM policy and regulations | Increasing irregular expenditures law suits, unjustified deviations audit findings | Critical | 5 | Common | 5 | High | 25 | Deviation register, Approved memo for deviation SCM policy and regulations MFMA circulars | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Ensure adherence to proper forward planning procedures by relevant stakeholders. 2.Training of the bid committee members and SCM officials, 2b. Ensure that the approved written deviations are inline with the SCM Policy. | Training plan, attendance register of the bid committee training, approved written quotations | CFO | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report | 1& 2b.Quartely Progress Report 2. Agenda and attendance Registers. | R0.00
|  | 10 | Increase Financial Viability | Revenue Collection | Low collection of revenue collection at the municipal townships (Nkowankowa, Lenyenye) | 1. Credit control of Business properties in the townships on water availability. Restriction of water availability to residential properties. 2. Non provision of services in particular roads, sidewalk library etc. non complaince to national building regulations.(To be removed) | Financial loss | Critical | 5 | Common | 5 | High | 25 | Credit control policy, Debt collection policy, revenue enhancement strategy, Indigent register maintained annually Approved building Plans. National Building Regulations. | weak | 0.8 | High | 20 | Accounting Officer | 1.Implement credit control and debt collection policies. 1b.Improved communication with the communities. 2. Ensure visibility of building inspectors..(To be removed) | Means of communications to the communities, Quarterly reports on the implementation of credit control and debt collection. | 1.CFO 1b. Director Corporate Services. 2. Director Engineering | 1.Quarterly reports on the implementation of credit control and debt collection actions 1b.Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | 1.Quarterly reports on the implementation of credit control and debt collection actions Quarterly report on the improved communication with clients 2.Quarterly Inspection Reports(To be removed) | R0.00
3 | To promote corporate governance excellence | Good governance | Non-compliance with MSA (individual performance management not cascaded to all officials) | Ineffective implementation of performance management system | Audit findings, Poor performance management | [6 empty] | Approved disaster Relief policy; Disaster Management Plan District risk assessment
Note on U2: C Stanley: Consider Linking Actions to improve management of risk with Root Causes
Note on W2: C Stanley: Consider mapping Action owners with Action Plans
Note on X2: C Stanley: Are these quarterly milestones, how should we treat them on the system? There is also need to map the milestones with the action plans

## STRATEGIC RISKS 2024 205FY
DRAFT STRATEGIC RISKS FOR 2024/2025 FINANCIAL YEAR
NO | Link Objectives | Risk category | Risk description | Background to the risk/Risk Root Cause | Risk Consequence | Impact | Rating | Likelihood | Rating | Inherent risk | Rating | Current controls | Perceived control effectiveness | Rating | Residual risk | RRR | Risk owner | Actions to improve management of the risk | Means of verification | Action owner
1 | Efficient and effective administration | Good governance | Agency not established in line with MFMA Sec 84 as a municipal entity subsection 1 (a) and (b) | 1. The mandate of the entity is not transferred which poses a threat to the entity’s going concern.. 2. No collaboration between the entity and LED-PED | Duplications of functions between PED (LED) and Gteda (municipal entity) | Critical | 5 | Common | 5 | High | 25 | SLA betweeen GTM and GTEDA Legal opinion | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | To advice the municipal council to comply in terms of MFMA Section 84 (1) (a) and (b) | Minutes of meeting between GTM and GTEDA | Director PED
2 | Efficient and effective administration | Good governance | Excessive hours of overtime worked and hours and non compliance to the Ministerial threshold (Overtime paid to employees outside the remuneration scale) | 1.Excessive payments done beyond what is indicated in the overtime policy as approved by Council. 2.Non implementation of overtime ministerial threshold | Audit findings, Health of the affected officials due to possible fatigue Abuse of overtime Litigation Possible financial Loss Negative impact on service delivery | Critical | 5 | Common | 5 | High | 25 | Approved overtime policy, Overtime guiding tool Management overtime strategies per municipal directorates Basic Conditions of Employment Act, Internal Circular on Pre -Approvals of overtime Gazzette about the ministerial threshold | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Monitoring of overtime trends in respective departments. 1b.Ensure departments limit overtime hours and align them to what has been prescibed as per the overtime policy 2.Seek clarity from department of labour to assist with the clarification of law on the interpretation of law of the overtime threshold. 2.Ensure the implementation of overtime Ministerial threshhold by monitoring pre approval of overtime( proposal) | Council resolution, Management minutes on Reviewed overtime tool, Quarterly Council Resolution for approval of overtime above threshold. Letter and response from the Department of Labour for clarity seeking.
3 | Optimise and sustain infrastructure investment and services | Service Delivery | Aging infrastructure (Roads, Buildings, Solid Waste) | 1.Inadequate implementation of maintenance plans and (outdated)Master Plans 2. Insufficient mantainance budget | Poor delivery of services Public protest High costs of maintenance & replacements | Critical | 5 | Common | 5 | High | 25 | Infrastucture Maintenance plan Electrical Master Plans Monthly Inspection report Outage and Mantainance Report | Weak | 0.65 | High | 16.25 | Accounting Officer | 1.Ensure the implentation of the maintenance plans and Master Plans and perform reactive maintenance as and when required. 1b. Advocate for the appointment of a service provider to review the Master plans. 2.Advocate for Budget increase at the end of the financial year | Quarterly inspections report
4 | Improve access to sustainable and affordable services | Service Delivery | Non compliance with Water Service Authority ( Mopani District Municipality) and Water Service Provider (Greater Tzaneen Municipality) agreement. | Lepele is invoicing GTM for bulk purchases of which is the responsibility of the WSA according to the agreement.( bill not being paid) | Financial loss, GTM incurring the costs of maintenance of infrastructure on behalf of the MDM cash flow constraints Poor service delivery Community Protests | Critical | 5 | Common | 5 | High | 25 | IGR meetings about the SLA between MDM & GTM (Water service authority & Water service provider) Continuos meetings between GTM and MDM, service level agreement | weak | 0.65 | High | 16.25 | Accounting Officer | Conduct meetings with Lepele, MDM and GTM(Bill settlent). | Progress reports on the implementation of the SLA,
5 | Efficient and effective administration | Good governance | Fraud and corruption occuring at the municipality | 1.Weak systems of control, 2.manipulation of internal controls, 3.unethical behaviour, | Audit findings; Financial loss, Reputational damage, | Critical | 5 | Common | 5 | High | 25 | awareness to all staff and municipal stakeholders, Approved policies: anti-fraud and corruption, Whistle blowing, fraud prevention plan Anti-corruption hotline Fraud risk register has been developed, Anti-corruption strategy | saisfactory | 0.65 | High | 16.25 | Accounting Officer | Conduct awareness on fraud , ethics and corruption. | Investigation report (if any), attendance regsiter for attendance of the workshop, request send to Communications and Marketing about the anti-corruption messages)
6 | Efficient and effective administration | Good governance | Non adherence to the reporting time frames. | 1.Inaccurate performance management reporting(Actuals reported and PoEs submmitted/ attached not addressing KPIs (not aligned with reported information) | Audit findings, Lack of credible reports Misalignment of information | Critical | 5 | Common | 5 | High | 25 | Quarterly performance report, APR, SDBIP, Internal Audit reports on performance of information Refresher trainings/workshops | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Continue to conduct refresher trainings/workshops as and well required. | Quarterly SDBIP report
7 | Improve access to sustainable and affordable services | service delivery | Increasing theft of infrastructure | 1.Social issues in the country (unemployment, loadshedding) 2.Absence of security at certain areas. 3.Non-adherence with asset management policy 4.Negligence and lack of safeguarding of municipal assets(loss through theft) | Financial loss, Loss of critical information/data, audit findings, Inconsistent security checks, | Critical | 5 | Common | 5 | High | 25 | security guards, cameras, security technology penalties imposed equivalent to the cost of the item, community policing forums | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Ensure establishment of community policing forums . 1b.Conduct awareness workshops to address social crimes with the comminities 2.Identify and list all Municipal assests to be safeguarged. 3.Inform council about the stolen and replaced assests. 4..Conduct awareness workshops to address negligence and lack of safeguarding of municipal assets | Number of SAPS cases partaning reported cases
8 | Efficient and effective administration | Good governance | Non-compliance with SCM policy and regulations. | 1. Lack of forward planning 2. Non-adherence to SCM policy and regulations | Increasing irregular expenditures litigations/law suits, unjustified deviations audit findings | Critical | 5 | Common | 5 | High | 25 | Deviation register, Approved memo for deviation SCM policy and regulations MFMA circulars | satisfactory | 0.65 | High | 16.25 | Accounting Officer | 1. Ensure adherence to proper forward planning procedures by relevant stakeholders. 2.Training of the bid committee members and SCM officials, 2b. Ensure that the approved written deviations are inline with the SCM Policy. | Training plan, attendance register of the bid committee training, approved written quotations
9 | Increase Financial Viability | Revenue Collection | Low collection of revenue collection at the municipal townships (Nkowankowa, Lenyenye) | Credit control of Business properties in the townships on water availability. Restriction of water availability to residential properties. | Financial loss | Critical | 5 | Common | 5 | High | 25 | Credit control policy, Debt collection policy, revenue enhancement strategy, Indigent register maintained annually Approved building Plans. National Building Regulations. | weak | 0.65 | High | 16.25 | Accounting Officer | 1.Implement credit control and debt collection policies. 1b.Improved communication with the communities. | Means of communications to the communities, Quarterly reports on the implementation of credit control and debt collection.
10 | Effective and efficient administration | Information Technology | ICT steering committee not in place | poor governance | Financial loss | Critical | 5 | Common | 5 | High | 25 | None |  | 0.65 | High | 16.25 | Accounting Officer | Appointment letter | Minutes and attendance letter
11 | Effective and efficient administration | SCM | Suppliers in the services of the state | poor governance | Financial loss | Critical | 5 | Common | 5 | High | 25 | MBD4 | Satisfactory | 0.65 | High | 16.25 | Accounting Officer | To acquire the system to detect the | Quarterly report
Note on S3: C Stanley: Consider Linking Actions to improve management of risk with Root Causes