## COVER
GREATER TZANEEN MUNICIPALITY
ADJUSTED SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP) 2022/2023 FINANCIAL YEAR
Approved by

## TABLE OF CONTENT
Table of contents: |  | Page
| List of Acronyms | 3
1 | Introduction | 4
2 | GTM Strategy Map for 2021/22 | 6
3 | Monthly Revenue Projections by source | 8
4 | Monthly Expenditure by vote | 9
5 | Capital Funding by source & Expenditure by Source & Vote | 10
6 | Capital Works Plan - 3 Year MTREF | 11
7 | Service Delivery Targets per Department
7.1 | Key Performance Indicators per Department | 32
7.2 | Project milestones per Department | 43
8 | Reporting Procedures | 44

## ACRONYMS
List of Acronyms
# | Number | MTREF | Medium Term Revenue and Expenditure Framework
% | Percentage | OtS | Office of the Speaker
CFO | Chief Financial Officer | PED | Planning and Economic Development Department
CORP | Corporate Services Department | PMS | Performance Management System
CSD | Community Services Department | SDBIP | Service Delivery and Budget Implementation Plan
EED | Electrical Engineering Department | SMME | Small, Medium and Micro Enterprises
EPWP | Expanded Public Works Programme | ToW | Transporter of Waste
ESD | Engineering Services Department | WSA | Waste Service Area
GTEDA | Greater Tzaneen Economic Development Agency
GG | Good Governance
GTM | Greater Tzaneen Municipality
HR | Human Resource
IDP | Integrated Development Plan
IT | Information Technology
KPA | Key Performance Area
KPI | Key Performance Indicator
kWh | Kilo Watt Hour
LED | Local Economic Development
MFMA | Municipal Finance Management Act
MFVM | Municipal Financial Viability and Management
MIG | Municipal Infrastructure Grant
MM | Municipal Manager
MTOD | Municipal Transformation and Organisational Development

## INTRODUCTION
1. INTRODUCTION
The Service Delivery and Budget Implementation Plan is drafted in accordance with the Municipal Finance Management Act (Act. 56 of 2003). Section 53 (1) (c ) (ii) of the MFMA specifies that the SDBIP must be approved by the Mayor within 28 days of approving the Budget. The SDBIP must include:
(a) projectsions for each month of (i) revenue to be collected, by source (ii) operational and capital expenditure, by vote;
(b) service delivery targets and performance indicators for each quarter;
MFMA Circular 13, issued by the National Treasury, further adds that the SDBIP must further include a detailed capital works plan, per ward, covering a three year period.
The SDBIP is one element of a continuous planning, implementation and reporting cycle. The aim of this process is to ensure that the vision of Council is achieved by implementing the activities planned in support of the strategic objectives contained in the Integrated Development Plan. The success of this cycle is dependant on the integration between the Budget, IDP and SDBIP and the process is presented below:
KPI Baselines: Year-end data for KPIs are not yet available for all measures since the 20/19/20 financial year has not yet ended by the time the 20/21 SDBIP was concluded. These will be updated during the mid-year review process. (Refer to 7.1 of this plan)
Project planning: Quarterly Milestones for projects are allocated a percentage weighting in terms of the proportion of the work to be done for that quarter. These percentages then accumulates towards the 100% expected at year-end for a specific project. Note that in the case of multi-year projects the expected result at financial year-end may be only a portion of the physical progress of the total project. In these instances the Capital Works Plan should be consulted as this will give an indication as to when the project will be completed.

## Strategy Map
2. GTM Strategy Map for 2022/23
Municipal KPA alignment to National KPAs |  | Strategic Objective Codes:
National KPA | Municipal KPA | LED 1: | Increased Investment in the GTM Economy
Municipal Transformation and Organisational Development | Good Governance (GG) | LED 2: | Create a stable and an enabling environment by attracting suitable investors
Good Governance and Public participation | Good Governance (GG) | LED 3: | Enhanced Integrated Developmental Planning
Municipal Financial Viability and Management | Good Governance (GG) | LED 4: | Develop a high performance culture for a changed, diverse, efficient and effective local government
Basic Service Delivery | Service Delivery (SD) | SD 1: | Improve access to sustainable and affordable basic services
Local Economic Development | Economic Growth (LED) | SD 2: | Optimise and sustain infrastructure investment and services
Spatial Rational | Economic Growth (LED) | SD 3: | Enhanced sustainable environmental management and social development
|  | SD 4: | Develop and build a skilled and knowledgeable workforce
|  | GG 1: | Improve stakeholder satisfaction
|  | GG 2: | Increased Financial viability
|  | GG 3: | Effective and Efficient Administration
|  | GG 4: | Attract and retain best human capital to become employer of choice

## Revenue & Expenditure
Revenue By Source | Total
Property rates | 134837829
Service charges - electricity revenue | 700000000
Service charges - water revenue | 0
Service charges - sanitation revenue | 0
Service charges - refuse revenue | 37893774
Rental of facilities and equipment | 800000
Interest earned - external investments | 4500000
Interest earned - outstanding debtors | 41701132
Dividends received | 0
Fines, penalties and forfeits | 12008000
Licences and permits | 817000
Agency services | 14664291
Transfers and subsidies | 516330000
Other revenue | 10651748
Gains | 0
Total Revenue | 1474203774
Expenditure By Type | Total
Employee related costs | 367029275
Remuneration of councillors | 28445008
Debt impairment | 49600000
Depreciation & asset impairment | 121847579
Finance charges | 14057048
Bulk purchases - electricity | 465421255
Inventory consumed | 77568118
Contracted services | 77920401
Transfers and subsidies | 45801506
Other expenditure | 152591041
Losses | 0
Total Expenditure | 1400281231

## Capex
Vote | Total
Vote 1 - Executive & Council | 0
Vote 2 - Planning and Economic Development | 2000000
Vote 3 - Budget and Treasury | 400000
Vote 4 - Corporate Services | 0
Vote 5 - Engineering Services | 134468840
Vote 6 - Community Services | 0
Vote 7 - Electrical Engineering | 27500000
Vote 8 - Office of the Speaker | 0
Total Capital expenditure | 164368840

## 3.LEGISLATION
SERVICE DELIVERY AND IMPLEMENTATION PLAN 2022-23
1. INTRODUCTION
The Service Delivery and Budget Implementation Plan (SDBIP) seeks to promote municipal accountability and transparency and is an important instrument for service delivery and budgetary monitoring and evaluation. The SDBIP is a partnership contract between the administration, council and community which expresses the goals and objectives, set by the council as quantifiable outcomes that can be implemented by the administration over the next 12 months.
Diagram 1
SDBIP “contract”
Council Administration
IDP
Budget
Monthly reports Mid-year performance assessment Annual Report
Employee Contracts and annual Performance agreements for the municipal manager & Senior managers
2. LEGISLATION
Section 1 of the MFMA defines the SDBIP as : A detailed plan approved by the mayor of the municipality in terms of section 53 (1) (c)(ii) for implementing the municipality’s delivery of services and the execution of its annual budget and which must include (as part of the top-layer) the following:
(a) Projections for each month of:
· Revenue to be collected, by source, and
· Operational and capital expenditure, by vote;
(b) Service delivery targets and performance indicators for each quarter.
In terms of National Treasury Circular No. 13 the SDBIP must provide a picture of service delivery areas, budget allocations and enable monitoring and evaluation. It specifically requires the SDBIP to include;
· Monthly projections of revenue to be collected for each source;
· Monthly projections of expenditure (operating and capital) and revenue for each vote
· Quarterly projections of service delivery targets and performance indicators for each vote;
· Information for expenditure and delivery; and
· Detailed capital works plan
In terms of Sections 69 (3) (a) and (b) of the MFMA the accounting officer of a municipality must submit to the Mayor within 14 days after the approval an annual budget, a draft SDBIP for the budget year and drafts of the annual performance plans as required in terms of Section 57 (1) (b) of the Municipal Systems Act (MSA) for the municipal manager and all senior managers. Furthermore, according to Section 53 (1) (c) (ii) and (iii) of the MFMA, the Mayor is expected to approve the SDBIP within 28 days after the approval of the budget.
The Greater Tzaneen Municipality’s 2021/22 Medium- term Budget and Integrated Development Plan (IDP) have been approved by Council on 27 May 2021 in terms of the MFMA and the MSA respectively. The process leading to the draft Budget, IDP and business plans, which have an important bearing on the finalizations of the SDBIP, includes the following elements:
Departmental business plans/departmental SDBIPs. These departmental SDBIPs provide the details plans and targets according to which the department’s performance will be monitored.
The departmental SDBIPs contain performance plans of senior managers. The performance plans were formulated in terms of the IDP sector plans and the operational mandates relevant to each department. The performance plans forms the basis for the signing of the annual performance agreements of the Municipal Manager and Senior Managers. The SDBIP represents the key performance targets as captured across core departments.
SDBIP
Service delivery targets (by Top Manager and by Ward)
Performance indicators
Revenue and Expenditure by Vote

## 4.METHODOLOGY
Methodology and Content
The development of the SDBIP was influenced by the Priorities, Strategic Objectives, Programme Objectives and Strategies contained in the IDP
ensuring progress towards the achievement thereof. The SDBIP of Greater Tzaneen Municipality (GTM) is aligned to the Key Performance Areas (KPAs)
Spatial Rationale as another KPA to be focused upon.
The methodology followed by GTM in the development of the SDBIP is line with National Treasury Framework contained in the Framework for Managing
Programme Performance Information.

## 8.ORGANISATIONAL KPI (2)
Performance Indicators and Targets for the following Key Performance Areas
1. Spatial Rationale, 2. Basic Service Delivery, 3. Local Economic Development, 4. Financial Viability, 5. Good Governance and Public Participation, 6. Municipal Transformation
Organisational Scorecard
Vote No | Measurable Objective | Programme | KPI | Baseline / Status | Budget | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 4th Quarter Target | Programme Owner | Evidence Required | Adjustments Notes
KPA 1: SPATIAL RATIONALE
IDP Strategic: facilitate integrated human settlements and agrarian reform
| Enhanced Integrated Planning | Housing consumer | Number Housing consumer education initiatives | 4 | 0 | 4 | 1 | 1 | 1 | 1 | PED | Attendance Register,Minutes/report | No adjustment
| Enhanced Integrated Planning | SPLUMA | Number of SPLUMA Tribunals sittings | 6 | 0 | 4 | 1 | 1 | 1 | 1 | PED | Notice of the Meeting,Attendance Register,Minutes | No adjustment
| Enhanced Integrated l Planning | LUMS | % of proclaimed Land Use Scheme | 0 | 0 | 100% | 5% Advervement of the appointment of the services provider | 10% Appointment of the services provider | No target this quarter | 100% adopted land use scheme status core | PED | Advertisement, letter of appointment of servise provider and council resolution for the draft adopted status core report) | No adjustment
400 | Enhanced Integrated Planning | GIS | Number of Geographical Information Systems purchased | 0 | 2800000 | 1 | 1 GIS procured | No target this quarter | No target this quarter | No target this quarter | PED | Delivery note of GIS equipment | No adjustment
BASIC SERVICE DELIVERY KEY PERFORMNACE INDICATORS
IDP Strategic Objective: Improve access to affordable and sustainable services,Optimise and sustain infrastructure servicesOptimise and sustain infrastructure services
Vote No | Measurable Objective | Programme | KPI | Baseline / Status | Budget R | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 4th Quarter Target | Programme Owner | Evidence Required
2.1 Free Basic Electricity
500 | Improve access to affordable and sustainable services | Free Basic Electricity (NKPI) | Number of indigents households with access to free basic electricity (NKPI) | 26981 | 1,500,000 | 26141 | 26141 | 26141 | 26141 | 26141 | Budget Treasury | indigents Register | No adjustment
2.3 Roads, bridges and stormwater management
| Improved access to affordable and sustainable basic services | Marirone to Motupa Street | % of planning, designs of Marirone to Motupa Street | 0 | 9500000 | 100% | Approval of project scoping report (25%) | Approval of detailed design report (50%) | Advertise for construction (75%) | Site establishment (100%) | Engineering Services Department | Scoping report. Detailed design report approval. Tender advert. | Budget adjusted from R7 000 000 to R9 500 000
| Improved access to affordable and sustainable basic services | Dan Access road from R36 (Scrapyard) to D5011 (TEBA) | % of planning, designs of Dan Access Road | Damaged Tar | 2500000 | 100% | No target for this quarter | Approval of project scoping report (25%) | Approval of detailed design report (50%) | Advertise for construction (100%) | Engineering Services Department | Scoping report. Detailed design report approval. Tender advert. | Budget adjusted from R7 000 000 to R2 500 000
| Improved access to affordable and sustainable basic services | Haenertsburg Cemetery road | % of Haenertsburg Cemetery Road upgraded | Damaged Tar | 3000000 | 100%(0.7km) | Complete detailed designs (25%) | Advertisement for constuction (50%) | No target for this quarter | 100% (0,7km Project completed ) | Engineering Services Department |  | KPI adjusted from Number of km upgraded of the Haenertsburg Cemetery Road to % of Haenertsburg Cemetery Road upgraded Budget adjusted from R4 000 000 to R3 000 000
| Improved access to affordable and sustainable basic services | Nkowakowa Internal streets (Bankuna, Tambo to Maxakeni Road) | % of Nkowakowa Internal streets (Bankuna, Tambo to Maxakeni Road) rehabilitated | Damaged Tar | 6000000 | 100% (3,3km) | Complete specifications (25%) | Advertisement for constuction (50%) | No target for this quarter | 100% Project completed (3,3km) | Engineering Services Department | Design report approval. Tender advert. Minutes of handover meeting. Completion Certificate | KPI adjusted from Number of km rehabilitated of the Nkowakowa Internal streets (Bankuna, Tambo to Maxakeni Road) to % of Nkowakowa Internal streets (Bankuna, Tambo to Maxakeni Road) rehabilitated Budge adjusted from R4 000 000 to R6 000 000
| Improved access to affordable and sustainable basic services | Nkowankowa A Condesa to Hani Street | Number of km of Nkowankowa A Codesa and Hani Street paved | 1,7km | 518000 | 1,7km | No target for this quarter | No target for this quarter | No target for this quarter | 1,7km (Project Completed) | Engineering Services Department | Monthly Project Progress Reports, Project Completion Certificate | Additional Project
| Improved access to affordable and sustainable basic services | Zangoma to Marivei road | % of planning, designs of Zangoma to Mariveni Road paved | New | 10713644 | 100% | No target for this quarter | No target for this quarter | Approval of detailed design report (50%) | Site establishment (100%) | Engineering Services Department | Scoping report. Detailed design report approval. | Additional project
| Improved access to affordable and sustainable basic services | Lenyenye Internal streets (Main Street) | Number of km rehabilitated of the Lenyenye Internal streets | Damaged Tar | 3200000 | 1.2km | No target for this quarter | No target for this quarter | No target for this quarter | 1,2km Project completed | Engineering Services Department | Appointment Letter, Minutes of handover meeting. Completion Certificate | Additional project
| Improved access to affordable and sustainable basic services | Mulati Access road | Number of km of Mulati Access road upgraded from gravel to Paving | 2.9 km | 12340300 | 5,7km | 5,7km (Project completed | No target for this quarter | 5,7km (Project completed | No target for this quarter | Engineering Services Department | Completion Certificates | Budget adjusted from R6 500 000 to R12 340 300 (R8 840300 MIG and R3 500 000 Own Funding) target adjusted from 1st quarter 5,7km oad paved to 3rd quarter 5,7km road paved
| Improved access to affordable and sustainable basic services | Moseanoka to Cell C Pharare Streets | Number of km of Moseanoka to Cell C Pharare Streets upgraded from gravel to Paving | 3.3km | 32738100 | 8,8km | 4,4km of road paved | 8,8km (Project completed) | No target for this quarter | 8,8km (Project completed) | Engineering Services Department | Progress report. Completion Certificates | Budget adjusted from R31 200 000 to R32 738 100 (R31 238 100 MIG and R1 500 000 Own Funding),4th quarter adjusted from no target for this quarter to 8,8km project completed)
| Improved access to affordable and sustainable basic services | Risaba, Mnisi, Shando to Driving School Internal Street | Number of km of Risaba, Mnisi, Shando to Driving School Internal Street upgraded from gravel to paving | 1.9 | 19120110 | 6,1km | 4km of road paved | 6,1km (Project completed) | No target for this quarter | 6,1km (Project compled) | Engineering Services Department | Progress report. Completion Certificates | Budget adjusted from R16 100 000 to R19 120 110 (R18 141 600 MIG and R978 510 Own Funding), target adjusted from no traget for this quarter to 6,1km in Quarter 4(Project completed)
| Improved access to affordable and sustainable basic services | Main road from Ndhuna Mandlakazi, Efrika, Zangoma, Mpenyisi to Jamba Cross Internal Street (in Ward 13, Mandlakazi) and Nwamitwa Bridge via Nhlengeleti School to Taxi Rank, Clinic via Lwandlamoni School to Nwamitwa/Mandlakazi Road | Number of km of Main road from Ndhuna Mandlakazi, Efrika, Zangoma, Mpenyisi to Jamba Cross Internal Street (in Ward 13, Mandlakazi) and Nwamitwa Bridge via Nhlengeleti School to Taxi Rank, Clinic via Lwandlamoni School to Nwamitwa/Mandlakazi Road upgraded from gravel to paving | 4.8 | 12116180 | 5,6km | 4km of road paved | 5,6km (Project completed) | No target for this quarter | 5,6km (Project completed) | Engineering Services Department | Progress report. Completion Certificates | Budget adjusted from R13 400 000 to R12 116 180, annual target adjusted from 4,9km to 5,6km, 4th quarter adjusted from no target for this quarter to 5,6km(Project completed)
| Improved access to affordable and sustainable basic services | Nwamitwa Bridge via Nhlengeleti School to Taxi Rank, Clinic via Lwandlamoni School to Nwamitwa/Mandlakazi Road upgraded from gravel to paving | Number of km of Nwamitwa Bridge via Nhlengeleti School to Taxi Rank, Clinic via Lwandlamoni School to Nwamitwa/Mandlakazi Road upgraded from gravel to paving | 2.1 | 12000000 | 4,9km | 4km of sub-base layer completed | 4,9km Project completed | No target for this quarter | 4,9km (project completed) | Engineering Services Department | Progress report. Completion Certificates | Budget adjusted from R7 200 000 to R12 000 000, annual targt adjusted from 5,9km to 4,9km, 4tth quarter adjusted from no target for this quarter to 4,9km (Project completed)
| Improved access to affordable and sustainable basic services | Walk-behind Roller | Number of Purchase of Walk-behind Roller | New | 500000 | 2 | No target for this quarter | No target for this quarter | 2 x walk behind rollers procured and delivered | No target for this quarter | Engineering Services Department | Delivery note. | No adjustment
| Improved access to affordable and sustainable basic services | Tar cutting machines | Number Purchasing of tar cutting machines | New | 40000 | 2 | No target for this quarter | No target for this quarter | 2 x tar cutting machines procured and delivered | No target for this quarter | Engineering Services Department | Delivery note. | Budget adjusted from R60 000 to R40 000
| Improved access to affordable and sustainable basic services | Speed Humps | Number of speed humps constructed | New | 800000 | 20 | No target for this quarter | No target for this quarter | No target for this quarter | 20 | Engineering Services Department | Completion Certificates | Additional project
| Improved access to affordable and sustainable basic services | Waste Removal Truck | Number of waste removal truck purchased | New | 2500000 | 1 | No target for this quarter | No target for this quarter | No target for this quarter | 1 | Engineering Services Department | Delivery Note | Additional project
| Improved access to affordable and sustainable basic services | Mayors Vehicle | Number of Mayor's vehicle purchased | New | 750000 | 1 | No target for this quarter | No target for this quarter | No target for this quarter | 1 | Engineering Services Department | Delivery Note | Additional project
| Improved access to affordable and sustainable basic services | Speakers Vehicle | Number of Speaker's Vehicle purchased | New | 750000 | 1 | No target for this quarter | No target for this quarter | No target for this quarter | 1 | Engineering Services Department | Delivery Note | Additional project
| Improved access to affordable and sustainable basic services | Civic Centre Building Roof | % of Revamping of Civic Centre Building Roof | Damaged roof | 2800000 | 100% | No target for this quarter | No target for this quarter | Project completed (100%) | No target for this quarter | Engineering Services Department | Appointment Letter, Minutes of handover meeting. Completion Certificate | Additional project
| Improved access to affordable and sustainable basic services | Grader G140 and Vehicles | Number of Purchasing of Machinery and Fleet | New | 4600000 | 3(1 x grader G140, 2x Vehicles) | No target for this quarter | No target for this quarter | 1 x grader G140 | Purchase of 2x electrical vehicles this quarter | Engineering Services Department | Delivery note. | Budget adjusted from R3 000 000 to R4 600 000, Indicator adjusted from Number of Purchasing of 1 x TLB, 1 x graders G140 to Purchasing of Machinery and Fleet, annual target adjusted from 1 x grader G140 to 1x grader and 4th quarter adjusted from no target for this quarter to purchase of 2x electrical vehicles
Electrification Projects
| Improve access to sustainable and affordable basic services | Electricity provision | Number of households electrified in current financial year | 589 | 14000000 | 1721 | No target for this Quarter | No target for this Quarter | No target for this Quarter | 1721 | EED | Com+pletion Certificates | Target adjusted from 700 to 1721
| Optimise and sustain infrastructure investment and services | Electricity network maintenance and refurbishment | R-value spent on maintenance of the electricity infrastructure |  | 19661733 | 19661733 | No target for this Quarter | No target for this Quarter | 9830867 | 19661733 | EED | Financial Report | No Adjustment
Electrification Projects | Increased Financial viability | Cost Recovery | % of Electricity Loss | 10% | 0 | 15% | No target for this Quarter | No target for this Quarter | No target for this Quarter | 15% | EED | Distribution loss Report | No Adjustment
| Optimise and sustain infrastructure and services | Electricity Connection | % of the new Electricity Connections (Consumer (Contribution)Funds received as services contributions spent on new connections and procurement of transformers) | 100% | 10000000 | 100% | 25% | 50% | 75% | 100% | EED | New Connection register, Job cards | No Adjustment
| Optimise and sustain infrastructure and services | Electricity Network upgrade and Refurbishment | Number of Replace 11 kV and 33 kV Auto reclosers per annum | New | 1500000 | 4 | No target for this Quarter | No target for this Quarter | 2 (Auto Reclosers installed) | Project completed (4 Auto Reclosers installed) | EED | Progress Report, Completion Certificate | Budget adjusted from R100 000 000 to R1 500 000
| Optimise and sustain infrastructure and services | Electricity Network upgrade and Refurbishment | % of designs of Rebuild 66 kV wooden line from Tzaneen to Tarentaalrand in Phase 1 of 5 | New | 4000000 | 100% | 5% Appointment of consultant | No target for this Quarter | No target for this Quarter | Approval of final designs 100% | EED | Appointment of consultant , Approval of Designs | Budget adjusted from R3 000 000 to R4 000 000, 3rd quarter Target changed from appointment of contractor to no target for the quarter and 4th quarter target Physical construction 100% (Structures Installed only)to Approval of designs 100% KPI adjusted from % of Rebuild 66 kV wooden line from Tzaneen to Tarentaalrand in Phase 1 of 5 to % of designs of Rebuild 66 kV wooden line from Tzaneen to Tarentaalrand in Phase 1 of 5
| Optimise and sustain infrastructure and services | Electricity Network upgrade and Refurbishment | % of Renewal Repairs and maintenance of Bulk meters and Replace current transformers & meter panel Tarentaalrand, Phase 1 of 3 | New | 1500000 | 100% | No target for this Quarter | 10% (Appointment of contractor) | No target for this Quarter | Project completed 100% | EED | Appointment of contractor, Progress reports, Completion Certificate | No Adjustment
| Improve access to sustainable and affordable basic services | Electricity Network upgrade and Refurbishment | % of Install bulk metering panel Letsitele main | New | 500000 | 100% | No target for this Quarter | 10% (Appointment of contractor) | No target for this Quarter | Project completed 100% | EED | Appointment of contractor, Progress reports, Completion Certificate | Indicator adjusted from % of Install Bulk current transformers & meter panel Gravelotte changed to % of Install bulk metering panel Letsitele main
| Optimise and sustain infrastructure and services | Electricity Network upgrade and Refurbishment | % of Rebuilding of Duiwelskloof 33 kV line (5 km) | New | 3000000 | 100% | Appointment of consultant (5%) | Appointment of contractor (10%) | Project progress (25%) | Project completed 100% | EED | Appointment of contractor, Progress Reports, Completion Certificate | No Adjustments
| Optimise and sustain infrastructure and services | Electricity Network upgrade and Refurbishment | % of Rebuilding of New Orleans 11 kV line (2,5 km) | New | 1000000 | 100%(2,5km ) | Appointment of consultant (5%) | Appointment of contractor (10%) | Project progress (25%) | Project completed (2,5km)100% | EED | Appointment of contractor, Progress Reports, Completion Certificate | Target changed from 2km to 2,5km
| Optimise and sustain infrastructure and services | Electricity Network upgrade and Refurbishment | % of Rebuilding of Henley 11 kV line (2,5 km) | New | 1000000 | 100%(2,5km ) | Appointment of consultant (5%) | Appointment of contractor (10%) | Project progress (25%) | Project completed (2,5km)100% | EED | Appointment of contractor, Progress Reports, Completion Certificate | Target changed from 2km to 2,5km
| Optimise and sustain infrastructure and services | Electricity Network upgrade and Refurbishment | % of Replacement of traffic lights control boxes on intersections in town | New | 500000 | 100% | No target for this Quarter | No target for this Quarter | Appointment of contractor (10%) | Replacement of traffic lights control boxes (100%) | EED | Appointment of contractor, Progress reports. | No Adjustment
| Optimise and sustain infrastructure and services | Installation of Air conditioner | % of Installation of Air conditioner Municipal Buildings | New | 500000 | 100% | No target for this Quarter | No target for this Quarter | Appointment of contractor (10%) | Installation of Air conditioner 100% | EED | Appointment of contractor, Progress reports. | No Adjustment
| Optimise and sustain infrastructure and services | SCADA Monitoring System | % of SCADA engineering system design | Addititional project | 4000000 | 100% | No target for this quarter | No target for this quarter | No target for this quarter | Approved engineering system design (100%) | EED | Engineering system design preport | Additional Project
| Optimise and sustain infrastructure and services | Ebenezer 33kV Feeder Line | % of Rebuilding of the Ebenezer 33kV feeder line phase 4(2km) | Addititional project | 6133517 | 100%(2km) | No target for this Quarter | No target for this Quarter | No target for this Quarter | Project completed 100% (2km) | EED | Progress Report, Completion Certificate | Additional project
| Optimise and sustain infrastructure and services | Pre-Paid meters | % of Tocket Identification D Rollover Pre-Paid meters | New | 500000 | 100% | 25% | 50% | 75% | 100% | EED | Progress Report, Completion Certificate | No Adjustment
| Improve access to affordable and sustainable services | Electrification of Tarentalrand | % of Electrification of Tarentalrand (50 units) | New | 952000 | 100% | Appointment of consultant (5%) | No target for this Quarter | Appointment of contractor (10%) | Project completed 50 units 100% | EED | Appointment of consultant , Appointment of contractor, Progress Quarterly reports & Completion certificate | budget adjusted from R1 000 000 to R952 000
| Improve access to affordable and sustainable services | Electrification of Nkomanini | % of Electrification of Nkomanini (258 units) | New | 4797115 | 100% | Appointment of consultant (5%) | No target for this Quarter | Appointment of contractor (10%) | Project completed 258 units 100% | EED | Appointment of consultant,Appointment of contractor, Progress Quarterly reports & Completion certificate | adjustmentTarget changed from 215 to 258 and budget adjusted from R4 300 000 to R4 797 115
| Improve access to affordable and sustainable services | Electrification of Mokgwathi | % of Electrification of Mokgwathi (120 units) | New | 2508662 | 100% | Appointment of consultant (5%) | No target for this Quarter | Appointment of contractor (10%) | Project completed 120 units 100% | EED | Appointment of consultant, Appointment of contractor, Progress Quarterly reports & Completion certificate | Budget changed from R2 400 000 to R 2 508 662
| Improve access to affordable and sustainable services | Electrification of Ramotshinaydi | % of Electrification of Ramotshinaydi (132 units) | New | 2726316 | 100% | Appointment of consultant (5%) | No target for this Quarter | Appointment of contractor (10%) | Project completed 132 units 100% | EED | Appointment of consultant, Appointment of contractor, Progress Quarterly reports & Completion certificate | Budget changed from R2 640 000 to R 2 726 316
| Improve access to affordable and sustainable services | Electrification of Maribethema | % of Electrification of Maribethema (40 units) | New | 741200 | 100% | Appointment of consultant (5%) | No target for this Quarter | Appointment of contractor (10%) | Project completed 40units 100% | EED | Appointment of consultant, Appointment of contractor, Progress Quarterly reports & Completion certificate | Budget changed from R800 00 to R741 200
| Improve access to affordable and sustainable services | Electrification of Mugwazeni | % of Electrification of Mugwazeni(100 units) | New | 2274706 | 100% | Appointment of consultant (5%) | No target for this Quarter | Appointment of contractor (10%) | Project completed 100 units 100% | EED | Appointment of consultant, Appointment of contractor, Progress Quarterly reports & Completion certificate | Budget changed from R2 860 000 to R2 274 706 and Target changed from 143 to 100
| Optimise and sustain infrastructure and services | Overhead electricity | Number of Kilometers of overhead electricity lines rebuilt | 19,2 km |  | 12km | No target for this quarter | No target for this quarter | No target for this quarter | 12km | EED | Completion Certificates | Target Changed from 9km to 12km
| Optimise and sustain infrastructure and services | Electricity network maintenance and refurbishment | R- Value of energy effecincy demand site management | New | 5000000 | 5000000 | No target for this quarter | No target for this quarter | 1500000 | 12km | EED | Payment Certificates | Budget changed from R800 00 to R741 200
| Optimise and sustain infrastructure and services | Supply and Installation of High Mast lights | Number of High Mast lights erected at Nkowankowa, Mariveni, Lusaka, Sethong, Xihoko and Mandlakazi | New | 3600000 | 6 | No target for this quarter | No target for this quarter | 6x highmast erected | 6x Project completed(100%) | Engineering Services Department | Progress report Completion certificate | Budget adjusted from R4 200 000 to R3 600 000
| Improve access to affordable and sustainable services | Electrification of Mavele Phase5 | % of Electrification of Mavele Phase5 (213 Units) | 95.5% | 0 | 100% | No target for this quarter | No target for this quarter | Project completed 213 (100%) | No Target for this Quarter | EED | Completion Certificate | 100% (4,5% to be added to the baseline of 95,5% of which will add to the 100%)
| Improve access to affordable and sustainable services | Electrification of New Phepene | % of Electrification of New Phepene (75 Units) | 5% | 1400000 | 100% | No target for this quarter | No target for this quarter | No target for this quarter | Project completed 75 (100%) | EED | Progree Report Completion certificate | Rollover
| Improve access to affordable and sustainable services | Electrification of New Rita | % of Electrification of New Rita (30 Units) | 5% | 692000 | 100% | No target for this quarter | No target for this quarter | No target for this quarter | Project Completed 30 100%) | EED | Progress Report, Completion Certificate | Rollover
| Improve access to affordable and sustainable services | Electrification of Winny Mandela | % of Electrification of Winny Mandela (678 Units) | 95.9% | 1100000 | 100% | No target for this quarter | No target for this quarter | No target for this quarter | Project Completed 678 (100%) | EED | Progress Report, Completion Certificate | Rollover
| Improve access to affordable and sustainable services | Electrification of Senakwe | % of Electrification of Senakwe (35 Units) | 32.64% | 682000 | 100% | No target for this quarter | No target for this quarter | No target for this quarter | Project Completed 35 (100%) | EED | Progress Report, Completion Certificate | Rollover
2.4 Solid Waste management
| Enhanced Sustainable environmental Management and social development | Refuse removal from households to the landfill site | Number of households with access to weekly kerbside solid waste collection(5 formal Towns) | 9052 |  | 8695 | 8695 | 8695 | 8695 | 8695 | Community Services | ●EPWP Beneficiaries Payment-advices ●1 x approved Timesheet & Checklist signed off | No Adjustment
|  |  | # of Rural Waste Service Areas serviced (Level 2 waste management) | 40 |  | 40 | 40 | 40 | 40 | 40 | Community Services | ●EPWP Beneficiaries Payment-advices ●1 x approved Timesheet & Checklist signed off by Ward Committee & Traditional Authority | No Adjustment
2.4 Solid Waste management |  |  | Number of commercial,institutional and industrial centres with access to solid waste removal services | 938 |  | 407 | 407 | 407 | 407 | 407 | Community Services | ●EPWP Beneficiaries Payment-advices ●1 x approved Timesheet & Checklist signed off | No Adjustment
600 |  |  | Amount of Cubic meters of waste disposed at the landfilled side | 7270 |  | 934m3 | 934m3 | 934m3 | 934m3 | 934m3 | Community Services | Quarterly reports | No Adjustment
2.5 Recreational facilities
| Optimise and sustain infrastructure investment and services | Sports complex | % of Constructionn of Leretjeni Sports complex at Leretjene village | Vandalised facility | 11000000 | 100% | Approval of designs (25%) | Advertisement for constuction (50%) | Appointment of Contrator and site handover (75%) | Project completed (100%) | Engineering Services Department | Design report approval. Tender advert. Appointment Letter. Minutes of site handover meeting. Completion Certificate | No Adjustment
2.5 Recreational facilities | Optimise and sustain infrastructure investment and services | Bulamahlo Community Hall | % of planning and designs of Bulamahlo Community Hall | New | 2500000 | 100% | No target this quarter | Approval of project scoping report (25%) | Approval of detailed design report (50%) | Advertise for construction (100%) | Engineering Services Department | Approval of scoping report, design report and tender advert. | Budget adjusted from R3 100 000 to R2 500 000
2.6 maintenance and repairs
| Improve access to affordable and sustainable services | Testing of water samples | % of water samples(at GTM water purification plants)complying with SANS 241 | 100% | 0 | 100% | 100% | 100% | 100% | 100% | Engineering Services Department | Testing of water samples Report | No Adjustment
| optimise and sustain infrastructure services | Maintenance of Buildings | Number of maintaince activities on municipal buildings and properties | 96 | 0 | 96 | 24 | 24 | 24 | 24 | Engineering Services Department | Maintenance reports | No Adjustment
2.6 maintenance and repairs | optimise and sustain infrastructure services | Maintenance of Vehicles | Number of municipal fleet maintained | 264 | 0 | 264 | 66 | 66 | 66 | 66 | Engineering Services Department | Maintenance reports | No Adjustment
| optimise and sustain infrastructure services | Maintenance of roads | Number of square meter of tarred municipal roads patched | 12000 | 0 | 12000 | 3000 | 3000 | 3000 | 3000 | Engineering Services Department | Job cards, Completion certificates | No Adjustment
| optimise and sustain infrastructure services | Maintenance of roads | Number Kilometers of municipal roads graded | 2400 | 0 | 2400 | 600 | 600 | 600 | 600 | Engineering Services Department | Reports, Happy letters | No Adjustment
| optimise and sustain infrastructure services | Parks & gardens | Number of municipal parks and gardens maintained | New | 0 | 18 | 18 | 18 | 18 | 18 | CSD | Weekly Maintenance plan and checklist | No Adjustment
| optimise and sustain infrastructure services | Maintenance of machines | Number of municipal machines maintained | 3 | 1300000 | 3 | 1 | 1 | 1 | No target for this quarter | Engineering Services Department | Maintenance reports | No Adjustment
2.7 Library Facility
| Enhanced Sustainable environmental Management and social development | Outreach and marketing | Number of Outreach and marketing strategy | New | 0 | 1 | 1 | No target for this quarter | No target for this quarter | No target for this quarter | CSD | Library outreach & marketing strategy adopted, Council Resolution | No Adjustment
| Enhanced Sustainable environmental Management and social development | Library Services | Number of Library users | 24000 | 0 | 48000 | 12000 | 12000 | 12000 | 12000 | CSD | Tattletape statistics (5 libraries) Monthly Reports (5 libraries) | No Adjustment
Library Facility | 2.8 Building Control
| Improve municipal internal control systems | Contravention notices | # of contravention notices issued to decrease non-compliance to building regulation | 48 | 0 | 48 | 12 | 12 | 12 | 12 | Engineering Services Department | Notices of contravention | No adjustment
| Improved access to affordable and sustainable basic services | New Guardroom | % of new Guardroom at Tzaneen Civic Centre | New | 150000 | 100% | Development of specifications(10%) | Appointment of service provider (20%) | Specification and tender advert(75%) | Project completed (100%) | Engineering Services Department | Specifications. Appointment letter. Completion certificate. | Budget adjusted from R40 000 to R150 000, 3rd quarter adjusted from project completed (100%)to Specification and tender advert(75%) and 4th quartre adjusted from no target this quarter to project completed 100%)
2.6 Building Control | Improved access to affordable and sustainable basic services | Purchase of Diagnosis Mechanical and replacement of Hydraulic jack tools for the workshop | % of Purchase of Diagnosis Mechanical and replacement of Hydraulic jack tools for the workshop | New | 96000 | 100% | Development of specifications(10%) | Appointment of service provider (20%) | Diagnosis machine and Hydraulic Jack Delivered (100%) | No target for this quarter | Engineering Services Department | Specifications. Appointment letter. Delivery note. | Budget adjusted from R100 000 to R96 000
| Improved access to affordable and sustainable basic services | Renovation of Nkowakowa offices (Old Home Affairs building) | % of Renovation of Nkowakowa offices (Old Home Affairs building) | Existing building | 800000 | 100% | Development of specifications(10%) | Appointment of service provider (20%) | Brickwork completed(30%) | Project completed (100%) | Engineering Services Department | Specifications. Appointment letter. Progress report. Completion certificate. | No adjustment
| Improved access to affordable and sustainable basic services | Installation of smoke detectors in Civic Centre and sub-offices | % of Installation of smoke detectors in Civic Centre and sub-offices | New | 500000 | 100% | No target for this quarter | Development of specifications(10%) | Appointment of service provider (20%) | Installation completed (100%) | Engineering Services Department | Specifications. Appointment letter. Installation certificate. | No adjustment
2.9 Other Assets
| Effective and Efficient Administration | Fleet management system | % of fleet management systems procured | New | 1500000 | 100% | No target for this quarter | Appoint service provider (20%) | Fleet management system installed on vehicles (50%) | Fleet management system operational (100%) | Engineering Services Department | Progress Report. Appointment letter. Installation certificate. | Budget adjustment from R1 000 000 to R1 500 000
| Effective and Efficient Administration | Power Generator for Letsitele Water Treatment Plant | Number of Power Generator installed at Letsitele Water Treatment Plant | New | 300000 | 1 | Specification developed (50%) | No target for this quarter | 1 Installation completed (100%) | No target for this quarter | Engineering Services Department | Specifications and commissioning certificate | No adjustment
2.7 Other Assets | Effective and Efficient Administration | Office furniture | Number Office furniture purchased |  | 400000 | 20 | No target for this quarter | 10* office chairs purchased | No target this | 10* Ofiice chairs and 10 office tables purchased | Budget and Treasury | Delivery note. | No adjustment
KPA 3:LOCAL ECONOMIC DEVELOPMENT
IDP Strategic Objective:Promote local economic growth
500 | Measurable Objective | Programme | KPI | Baseline / Status | Budget | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 4th Quarter Target | Programme Owner | Evidence Required
KPA 3:LOCAL ECONOMIC DEVELOPMENT | Increased Investment in the GTM Economy | LED | # of jobs created through municipal LED initiatives and capital projects | 100 | 0 | 100 | 25 | 50 | 75 | 100 | PED | Quarterly reports on number of jobs created | No Adjustment
IDP Strategic Objective:Promote local economic growth | Ensure that the SMME's are capacitated | SMME | # of SMME's supportted | 100 | 0 | 100 | 25 | 50 | 75 | 100 | PED | Attendance register,Report | No Adjustment
Vote No | Ensure the creation of jobs through Community Works Programme | CWP | # of Local reference committee meetings held (CWP) | 4 | 0 | 4 | 1 | 1 | 1 | 1 | PED | Attendance register,Minutes/report | No Adjustment
400 | Increased Investment in the GTM Economy | LIBRA | # of LIBRA education meeting held | 4 | 0 | 4 | 1 | 1 | 1 | 1 | PED | Notices, attendance register and the minutes) | No Adjustment
| Increased Investment in the GTM Economy | Agriculture Expo | # Agricultural EXPO | 1 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 | PED | Council Resolution and reports | No Adjustment
| Ensure the creation of jobs through Expanded Public Works Programme | EPWP | Number active of jobs creared through municipal EPWP projects (NKPI)(Full time equivalent) | 684 | 8065000 | 807 | 241 | 202 | 202 | 162 | ESD | EFT Calculation Sheet | No Adjustment
| Increase Investment in GTM Economy | Investment attraction | Number of committed investors attracted through GTEDA | 1 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 | GTEDA | Signed agreements and commitment letters | No Adjustment
| Increase Investment in GTM Economy | Networking Seminars | Number of Information sharing and networking seminars convened | 2 | 462831 | 2 | 1 | No target this quarter | No target this quarter | 1 | GTEDA | Seminar report. Signed attendance register. | No Adjustment
| Increase Investment in GTM Economy | Agricultural Business Incubator | Number of LED projects implemented through,agricultural Business Incubator | 5 | 200000 | 10 | No target this quarter | No target this quarter | No target this quarter | 10(Training, business development) | GTEDA | Quarterly Report | No Adjustment
| Increase Investment in GTM Economy | Workplace Skills Development Plan | Number of Workplace Skills Development Plan (WSP) submitted to LG Seta by 30 April | 1 | 251834 | 1 | No target this quarter | No target this quarter | No target this Quarter | 1 | GTEDA | WSP, Proof of submission | No Adjustment
| Increase Investment in GTM Economy | Annual Report | Number of Annual Report submitted to the municipality by 15 January | 1 | 0 | 1 | No target this quarter | No target this quarter | 1 | No target this quarter | GTEDA | Annual Report, Proof of submission | No Adjustment
| Increase Investment in GTM Economy | GTEDA business plan | Number of Submission of the GTEDA business plan to GTM by 31st March | 1 | 0 | 1 | No target this quarter | No target this quarter | 1 | No target this quarter | GTEDA | Business Plan, Proof of submission | No Adjustment
| Increase Investment in GTM Economy | Strategic Risk mitigated | Number of Strategic Risk mitigated | 5 | 0 | 2 | No target this quarter | No target this quarter | No target this quarter | 2 | GTEDA | Risk Monitoring Report | No Adjustment
| Increase Investment in GTM Economy | Audited Financial Statement | Numner of Audited Financial Statement submitted to AGSA by 31 August | 1 | 443978 | 1 | 1 | No target this quarter | No target this quarter | No target this quarter | GTEDA | AFS submitted to AGSA, Proof of submitted | No Adjustment
| Increase Investment in GTM Economy | Annual Budget | Number of Annual Budget Approved by 31st May by Council | 1 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 | GTEDA | Annual Budget Approved, Council Resolution | No Adjustment
| Increase Investment in GTM Economy | Waste Management for SMME | Number of SMMEs LED project implemented for Waste Management | 4 | 100000 | 5 | 1 | 1 | 1 | 2 | GTEDA | SMMEs Report | No Adjustment
| Increase Investment in GTM Economy | Budget Spent | % Budget Spent | 100% | 9857217 | 100% | 25% | 50% | 75% | 100% | GTEDA | Financial Reports | No Adjustment
| Increase Investment in GTM Economy | SMME's assisted with registration | Number of SMME's assisted with registration | 40 | 0 | 40 | 10 | 10 | 10 | 40 | GTEDA | CIPC registration reports | No Adjustment
| Increase Investment in GTM Economy | Internal Audits Conducted | Numberof Internal Audits Conducted | 4 | 225450 | 4 | 1 | 1 | 1 | 1 | GTEDA | Internal Audit Report | No Adjustment
| Increase Investment in GTM Economy | Tzaneen Farmer Supported | Number of SMMEs LED project implemented for Farmer Support Facility | 40 | 160000 | 40(training farmers on governance and compliance, technical training on production and financial management) | No target this quarter | No target this quarter | No target this quarter | 40(training farmers on governance and compliance, technical training on production and financial management) | GTEDA | SMMEs Report | No Adjustment
KPA 4:FINANCIAL VIABILITY
IDP Strategic Objective: Sound Financial Management
| Measurable Objective | Programme | KPI | Baseline / Status | Budget | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 4th Quarter Target | Programme Owner | Evidence Required
KPA 4:FINANCIAL VIABILITY | Increase Financial viability | Revenue enhancement strategy | Number of revenue enhancement strategy reviewed | 1 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 | Budget and Treasury | 2023/24 Enhancement Revenue Strategy | No Adjustment
IDP Strategic Objective: Sound Financial Management | Increase Financial viability | Annual Budget | Number Annual Budget submitted to Council by 31 May | 1 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 | Budget and Treasury | Council Resolution | No Adjustment
Vote No | Increase Financial viability | Asset and invetory management | Number of assets update schedules | 12 | 0 | 12 | 3 Updated schedule of assets changes | 3 Updated schedule of assets changes | 3 Updated schedule of assets changes | 2 Updated schedule of assets changes and 1 final assets register | Budget and Treasury | Schedule of assests changes reports | No Adjustment
| Increase Financial viability | Annual Assets Verification | Number of Annual Asset Verification report concluded by 31 Aug | 1 | 0 | 1 | 1 | No target this quarter | No target this quarter | No target this quarter | Budget and Treasury | Assests verification report | No Adjustment
|  | Adjudicated bids | % Of adjudicated bids over closed bids that has been advertised | 100% | 0 | 100% | 100% | 100% | 100% | 100% | Budget and Treasury | Adjudication report | No Adjustment
|  |  | Number of compliant in-year SCM reports submitted to Council | 12 | 0 | 12 | 3 SCM reports | 3 SCM reports | 3 SCM reports | 3 SCM reports | Budget and Treasury | SCM Quarterly reports | KPI Adjusted Number of compliant in-year SCM reports submitted on time to Council and Treasury to Number of compliant in-year SCM reports submitted on time to Council
| Increase Financial viability | Cost coverage | Number of times that current interest payment can be covered with available operating income excluding depreciation and impairement | 1.6 | 0 | 1.6 | 1.6 | 1.6 | 1.6 | 1.6 | Budget and Treasury | Financial reports | No Adjustment
| Increase Financial viability | Revenue collection | % of revenue collected (revenue billed over revenue collected) | 80% | 0 | 80% | 80% | 80% | 80% | 80% | Budget and Treasury | Financial reports | No Adjustment
| Increase Financial viability | Debt coverage | % of debt coverage ratio(operating income divided by debts service owing | 0% | 0 | 0% | 0% | 0% | 0% | 0% | Budget and Treasury | Financial reports | No Adjustment
| Increase Financial viability | MFMA reports | Number of S71 reports submitted to the mayor and provincial treasury within 10 working days of start of the month | 12 | 0 | 12 | 3 | 3 | 3 | 3 | Budget and Treasury | S71 monthly report | No Adjustment
|  |  | Number of S52 reports submitted to Council within 30 days of the end of each quarter | 4 | 0 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury | S52 Quarterly reports | No Adjustment
|  |  | Number of S72 reports submitted to Council and provincial treasury after assessment by the accounting officer by 25 january | 1 | 0 | 1 | No target this quarter | No target this quarter | 1( S72 reports submitted to Council and provincial treasury after assessment by the accounting officer by 25 january) | No target this quarter | Municipal Manager | Mid-year report,prove of submission to Council and provincial treasury | No Adjustment
|  |  | Number of Adjustment Budget reports submitted to Council in terms of S28 | 1 | 0 | 1 | No target this quarter | No target this quarter | 1 (Budget Adjustment Report) | No target this quarter | Budget and Treasury | Council Resolution
No Adjustment
| Increase Financial viability | Annual financial statements | Number of annual financial statements submitted to the A-G within the prescribed timeframes | 1 | 0 | 1 | 1(Unaudited AFS submitted to A-G 31 August 2022) | No target this quarter | No target this quarter | No target this quarter | Budget and Treasury | AFS,Delivery note,coghsta, NT, PT | No Adjustment
| Increase Financial viability | Draft Annual Performance report | Number of Draft Annual Performance report submitted within regulated time | 1 | 0 | 1 | 1(Unaudited Annual Performance Report submitted to A-G 31 August 2022) | No target this quarter | No target this quarter | No target this quarter | Municipal Manager | APR,Delivery note,coghsta, NT, PT | No Adjustment
| Increase Financial viability | Personnel Expenditure | % of personnel budget spent | 100% | 0 | 100% | 25% | 50% | 75% | 100% | Budget and Treasury | Financial report | No Adjustment
| Increase Financial viability | MIG Expenditure | % of MIG Expenditure | 100% | 99741000 | 100% | 25% | 50% | 75% | 100% | Engineering Services Department | Grant Expenditure Reports | No Adjustment
| Increase Financial viability | Maintenance Expenditure | % of maintenance budget spent | 100% | 0 | 100% | 25% | 50% | 75% | 100% | Engineering Services Department | Monthly financial report | No Adjustment
| Increase Financial viability | Capital Expenditure | % of capital budget spent | 100% | 0 | 100% | 25% | 50% | 75% | 100% | Engineering Services Department | Financial report | No Adjustment
KPA 5:GOOD GOVERNANCE AND PUBLIC PARTICIPATION
IDP Strategic Objective: Build capable institution and administration
| Measurable Objective | Programme | KPI | Baseline / Status | Budget | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 4th Quarter Target | Programme Owner | Evidence Required
KPA 5:GOOD GOVERNANCE AND PUBLIC PARTICIPATION
IDP Strategic Objective: Build capable institution and administration | Effective and Efficient Administration | External Auditing | Number of Improved audit opinion obtained from AG | 1(Unqualified audit opinion) | 0 | 1(Unqualified audit opinion) | No target this quarter | 1(Unqualified audit opinion) | No target this quarter | No target this quarter | Municipal Manager | A-G Audit report | No Adjustment
Vote No | Effective and Efficient Administration | Internal Audit | Number of AG Action Plan submitted to Council by 31 Jannuary | 1 | 0 | Submit AG Action Plan to Council by 31 Jannuary | No target this quarter | No target this quarter | 1(Submit AG Action Plan to Council by 31 January) | No target this quarter | Municipal Manager | A-G Auditing Action Plan and council resolution
5.1 Auditing and Risk Management | [12 empty] | No Adjustment
200 |  |  | Number of audit findings from the Auditor General | 42 | 0 | 40 | No target this quarter | 40 | No target this quarter | No target this quarter | Municipal Manager | A-G Report | No Adjustment
200 |  |  | % of A-G quieries resolved | 58% | 0 | 100% | No target this quarter | No target this quarter | 25% | 100% | Municipal Manager | AGSA Action Plan | No Adjustment
| Effective and Efficient Administration |  | Number of senior managers complying with the minimum competency levels (Municipal Finance Management Programme) | 7 | 0 | 7 | 7 | No target this quarter | No target this quarter | No target this quarter | Corporate Services | Competency report | No Adjustment
| Effective and Efficient Administration |  | Number of Risk Based Internal Audit Plan approved | 1 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 | Municipal Manager | Council Resolution | No Adjustment
|  |  | Number of PMS report submitted to council | 4 | 0 | 4 | 1 | 1 | 1 | 1 | Municipal Manager | Council Resolution | No Adjustment
| Effective and Efficient Administration | Audit Committee | Number of audit committee meetings held | 6 | 0 | 4 | 1 | 1 | 1 | 1 | Municipal Manager | Agenda Minutes Attendance register | No Adjustment
| Effective and Efficient Administration | Risk Assessment | Number of risk assessments conducted | 1 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 (Risk Assessment) | Municipal Manager | Quarterly reports, Risk Monitoring Reports | No Adjustment
| Effective and Efficient Administration | Board Meeting | Number of board meetings held | 4 | 559510 | 4 | 1 | 1 | 1 | 1 | GTEDA | Quarterly Reports(invitation, attendance register and minutes) | No Adjustment
200 | Effective and Efficient Administration | Strategic Risk Mitigated | Number of Strategic Risk mitigated | 4 | 0 | 4 | 1 | 1 | 1 | 1 | Municipal Manager | Risk Monitoring Report | No Adjustment
200 | Effective and Efficient Administration | Risk and compliance Committee | Number of Risk and compliance Committee meetings held | 4 | 0 | 4 | 1 | 1 | 1 | 1 | Municipal Manager | Quarterly reports and Compliance committee reports | No Adjustment
5.1 Safety and Security Management
| Effective and Efficient Administration | Safety and Security | % of cases of theft reported and resolved | 100% | 0 | 100% | 100% | 100% | 100% | 100% | Community Services | Security reports | KPI Adjusted from % of cases of theft of council items report to % of cases of theft reported and resolved
5.2 Council and Oversight Structures (Putting people first)
Safety and Security Management | Effective and Efficient Administration | MPAC | Number of MPAC report submitted to council | 5 | 0 | 4 | 1 | 1 | 1 | 1 | Municipal Manager | Notice, Minutes & Attendance register | No Adjustment
|  |  | Number of MPAC meetings held | 12 | 0 | 12 | 3 | 3 | 3 | 3 | Corporate Services | MPAC Reports,Council Resoution | No Adjustment
5.2 Council and Oversight Structures (Putting people first) | Effective and Efficient Administration | Council function and support | Number of council sitting held | 7 | 0 | 4 | 1 | 1 | 1 | 1 | Corporate Services | Notice, Minutes & Attendance register | No Adjustment
200 |  |  | % of GTM council resolutions implemented | 100% | 0 | 100% | 100% | 100% | 100% | 100% | Municipal Manager | Council Resolution register | No Adjustment
|  |  | Number of schedule Executive committee meetings held | 12 | 0 | 12 | 3 | 3 | 3 | 3 | Corporate Services | Notice, Minutes & Attendance register | No Adjustment
10 | 5.3Public Participation
| Effective and Efficient Administration | Public Participation | Number of public participation meetings (imbizos) held | 35 | 0 | 4 | 1 | 1 | 1 | 1 | Municipal Manager | Imbizo Report, Attendance Register | No Adjustment
|  |  | Number of community feedback meetings held | 70 | 0 | 140 | 35 | 35 | 35 | 35 | Corporate Services | Community feedback reports, Attendance register | No Adjustment
5.4 Public Participation | Effective and Efficient Administration | Compliants Management | % of compliants referred to departments and resolved | 100% | 0 | 100% | 100% | 100% | 100% | 100% | Municipal Manager | Compliants Management Register | No Adjustment
200 | Effective and Efficient Administration | Ward committees support | Number of functional ward committees | 35 | 0 | 35 | 35 | 35 | 35 | 35 | Corporate Services | functional ward committees Report | No Adjustment
| Effective and Efficient Administration | Ward committees support | Number of monthly ward committees reports submitted | 210 | 0 | 420 | 105 | 105 | 105 | 105 | Corporate Services | Monthly ward committees report | No Adjustment
200 | Effective and Efficient Administration | Communication | Number of Communication strategy reviewed and implemented annually | 1 | 0 | 1 | 1(Implementation of the Strategy) | 1(Implementation of the Strategy) | 1(Implementation of the Strategy) | 1(Communication strategy reviewed) | Corporate Services | Council Resolution & quartely reports | No Adjustment
10 | Effective and Efficient Administration | Licensing and lawenforcement | Number of monthly compliance assessments conducted on Licensing services (as set out in the SLA with Dpt of Transport) | 36 | 0 | 36 | 9 | 9 | 9 | 9 | Community Services | SLA Monthly Licensing Compliance Checklists | No Adjustment
10 | Effective and Efficient Administration | IT Strategy | Number of IT strategy reviewed annually | 1 | 0 | 1 | No target for this quarter | No target for this quarter | No target for this quarter | 1 | Corporate Services | Reviewed IT Strategy, Council Resolution | No Adjustment
200 | Effective and Efficient Administration | Disaster Recovery Plan | Number of Disaster Recovery Plan reviewed | 1 | 0 | 1 | No target for this quarter | No target for this quarter | No target for this quarter | 1 | Corporate Services | Reviewed Disaster Recovery plan, Council Resolution | No Adjustment
| Effective and Efficient Administration | Road traffic regulation | Number of roadblocks conducted | 12 | 0 | 12 | 3 | 3 | 3 | 3 | Community Services | Monthly roadblock report | No Adjustment
| Effective and Efficient Administration | Disaster Management | % of disaster incidences responded to within 72 hours | 100% | 0 | 100% | 100% | 100% | 100% | 100% | Municipal Manager | Quarterly reports, Disaster Incident Register | No Adjustment
| Effective and Efficient Administration | Disaster Risk Management awareness campaigns | Number of disaster risks management awareness campaigns held | 5 |  | 15 | 3 | 3 | 5 | 4 | Municipal Manager | Quarterly reports, Attendance Register, Invitation, Agenda | No Adjustment
KPA 6:MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
| Measurable Objective | Programme | KPI | Baseline / Status | Budget | Annual Target | 1st Quarter Target | 2nd Quarter Target | 3rd Quarter Target | 4th Quarter Target | Programme Owner | Evidence Required
200 | IDP Strategic Objective: Build capable institution and administration
KPA 6:MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT | 6.1 IDP
Vote No | Develop a high Skilled and Knowledgeable workforce | IDP Review | Number of IDP/Budget adopted by Council by May | 1 | 0 | 1 | No target for this quarter | No target for this quarter | No target for this quarter | 1(Final IDP /Budget) | Municipal Manager | Council resolution | No Adjustment
IDP Strategic Objective: Build capable institution and administration | Develop a high Skilled and Knowledgeable workforce | IDP Represenatative Forum | Number of IDP Representative Forum meetings held | 4 | 0 | 5 | 1(Process plan) | 1(Analysis Phase) | 2(Stategy and draft projests | 1(Final Projects) | Municipal Manager | Minutes,Attendance register | No Adjustment
6.1 IDP | Develop a high Skilled and Knowledgeable workforce | IDP/PMS strategic planning session | Number of strategic planning session held | 1 | 0 | 1 | No target this quarter | 1 strategic planning Session | No target this quarter | No target this quarter | Municipal Manager | Invitations & attendance register | No Adjustment
200 | Develop a high Skilled and Knowledgeable workforce | IDP Assessments | Number of IDP Assessment report for Special programmes mainstreaming conducted | New | 0 | 2 | 1 | 1 | No target this quarter | No target this quarter | Municipal Manager | IDP Assessment report, Annual Report Assessment report | No Adjustment
6.2 PERFORMANCE MANAGEMENT
200 | Develop a high Skilled and Knowledgeable workforce | PMS | Number of senior managers ( section 54 and S56) with signed performance agreements within prescribed timeframe | 7 | 0 | 7 | 7 | No target this quarter | No target this quarter | No target this quarter | Municipal Manager | Signed Performance Agreements | No Adjustment
IDP Strategic Objective: Build capable institution and administration | Develop a high Skilled and Knowledgeable workforce |  | Number of formal assessements conducted (S54 & 56) | 2 | 0 | 2 | No target this quarter | No target this quarter | 1 (mid-year for 2022/23) | 1 (annual assessment for 2021/22) | Municipal Manager | Assessment reports | No Adjustment
6.2 PERFORMANCE MANAGEMENT | Develop a high Skilled and Knowledgeable workforce |  | Number of other officials other than S 56 managers with Performance Plans | 30 | 0 | 50 | 20(Development of Performance Plans) | 50(Development of Performance Plans) | No target this quarter | No target this quarter | Corporate Services | Performance Plans | No Adjustment
200 | Develop a high Skilled and Knowledgeable workforce |  | Number of in-year performance management reports submitted to Council | 4 | 0 | 4 | 1 | 1 | 1 | 1 | Municipal Manager | Council Resolution | No Adjustment
200 | Develop a high Skilled and Knowledgeable workforce |  | Number of Draft Annual Performance Report submitted to the AG, Audit Committee and Mayor by 31 August | 1 | 0 | 1 | 1(Draft Annual Performance Report submitted to the AG, Audit Committee and Mayor by 31 August) | No target this quarter | No target this quarter | No target this quarter | Municipal Manager | Delivery note Coghsta, | No Adjustment
| Develop a high Skilled and Knowledgeable workforce |  | Number of Draft Annual Report | 1 | 0 | 1 | No target this quarter | No target this quarter | 1(Draft Annual Report ) | No target this quarter | Municipal Manager | Delivery note Coghsta, | No Adjustment
200 | Develop a high Skilled and Knowledgeable workforce |  | Number of Final Annual and oversight reports adopted within stipulated timeframes | 1 | 0 | 1 | No target for this quarter | No target for this quarter | 1(Oversight report on the Annual report approved by Council by March) | No target this quarter | Corporate Services | Council Resolution | No Adjustment
6.3 Skils Development and Employment Equity
200 | Develop a high Skilled and Knowledgeable workforce | Skills Development | Number of employees and councillors capacitated in terms of Workplace Skills plan | 174 | 0 | 369 | 92 | 92 | 93 | 92 | Corporate Services | Training reports | No Adjustment
IDP Strategic Objective: Build capable institution and administration | Develop a high Skilled and Knowledgeable workforce | Workplace skills plan (Technical skills) | Number of municipal personnel with technical skills/capacity (engineer & technicians (EED & ESD) | 58 | 0 | 26 | 26 | 26 | 26 | 26 | Corporate Services | Skills development reports | No Adjustment
6.3 Skils Development and Employment Equity | Develop a high Skilled and Knowledgeable workforce | Workplace Skills Development Plan | Number Workplace Skills Development Plan (WSP) submitted to LG Seta by 30 April | 1 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 | Corporate Services | Quarterly Report ("WSP Proof of submission" Registration) | No Adjustment
10 | Develop a high Skilled and Knowledgeable workforce | Employment Equity Plan (NKPI) | Number of people from employment equity target group employed in the three highest levels of the municipality (National indicator) | 30 | 0 | 32 | 35 | 35 | 32 | 32 | Corporate Services | Employment Equity reports | Target adjusted from 35 to 32, Annual Target adjusted form 35 to 32
10 | 6.4. Human Resource Management, Legal Services & Occupational Health and Safety
10 | Develop a high Skilled and Knowledgeable workforce | Workplace skillsplan | Amount actual spent( 1 % of the salary budget of municipality) on implementing workplace skills plan (National Indicator) | 1568710 | 2000000 | 500000 | 500000 | 500000 | 500000 | 500000 | Corporate Services | Financial report | No Adjustment
IDP Strategic Objective: Build capable institution and administration | Develop a high Skilled and Knowledgeable workforce | Labour Forum | Number of Local Labour Forum Meetings held | 5 | 0 | 4 | 1 | 1 | 1 | 1 | Corporate Services | Attendance Register, Agenda Quarterly reports | No Adjustment
6.4. Human Resource Management, Legal Services & Occupational Health and Safety | Develop a high Skilled and Knowledgeable workforce | OHS Inspection Report | Number of workstations inspected for OHS contraventions | 54 | 0 | 48 | 12 | 12 | 12 | 12 | Corporate Services | Inspection reports | No Adjustment
10 | Develop a high Skilled and Knowledgeable workforce | OHS Compliance Report | Number of in-year compliance reports on OHS generated | 4 | 0 | 4 | 1 | 1 | 1 | 1 | Corporate Services | Compliance Report | No Adjustment
10 | 6.5 Policies and By-laws
10 | Develop a high Skilled and Knowledgeable workforce | Policy workshop | Number of policy workshops held | 0 | 0 | 1 | No target this quarter | No target this quarter | No target this quarter | 1 | Corporate Services | Invitations & attendance register | No Adjustment
IDP Strategic Objective: Build capable institution and administration | Develop a high Skilled and Knowledgeable workforce | Policies | Number of policies developed/reviewed | 24 | 0 | 57 | No target this quarter | No target this quarter | No target this quarter | 57 | Corporate Services | Policy register | No Adjustment
6.5 Policies and By-laws
,,
3

## TID
Performance Indicators and Targets for the following Key Performance Areas
1. Spatial Rationale, 2. Basic Service Delivery, 3. Local Economic Development, 4. Financial Viability, 5. Good Governance and Public Participation, 6. Municipal Transformation
Organisational Scorecard
Vote No | Indicator title | Short defination | Purpose/importance | Source/collection of data | Method of calculation | Data limitations | Type of indicator | Calculation type | Reporting cycle | New indicator | Desired performance | indicator responsibility
KPA 1: SPATIAL RATIONALE
IDP Strategic: facilitate integrated human settlements and agrarian reform
| # Housing consumer education initiatives | Housing consumers in the entire residential property market understands role in the housing provision | Providing support to housing consumer education initiative and awareness creation | SDBIP Quarterly Reports | Counting number of reports on the housing consumer eduction initiatives | None | Output | Cumulative | Quarterly | No | Improved educational awreess on housing provision | PED
| # of SPLUMA Tribunals sittings | Monitor the implementation of municipal SDF strategy with SPLUMA | Strengthen the implementation of municipal land development | SDBIP Quarterly Reports | Counting number of reports on the implementation of SDF | None compliance by traditional leaders with SPLUMA | Output | Cumulative | Quarterly | No | Improved proper planning on municipal land development | PED
| % of proclaimed Land Use Scheme | Land use management is a system that ensures that the right things get built, in the right place, at the right time. The system consists of legal requirements and regulations that ensure that land is developed in a desirable and sustainable way | The general purpose of a Scheme is to create coordinated, harmonious and sustainable development of a municipal area in such a way that it efficiently promotes health, safety, order, amenity, convenience and general welfare, as well as efficiency and economy in the process of development | SDBIP Quarterly Reports | Milestone achieved as per each activity |  | Output | Cumulative | Quarterly | Yes | Single LUS for the whole of Greater Tzaneen Municipality | PED
400 | % of Geographical Information Systems purchased | A Geographic Information System (GIS) is a computer system that analyzes and displays geographically referenced information. It uses data that is attached to a unique location | Geographic Information Systems are powerful decision-making tools for any business or industry since it allows the analyzation of environmental, demographic, and topographic data. | SDBIP Quarterly Reports | Purchased and delivered equipments | Lack of quality data | Output | Cumulative | Quarterly | No | Implementation of the approved GTM Corporate GIS model | PED
BASIC SERVICE DELIVERY KEY PERFORMNACE INDICATORS
IDP Strategic Objective: Improve community well-being through accelerated service delivery
Vote No | Indicator title | Short defination | Purpose/importance | Source/collection of data | Method of calculation | Data limitations | Type of indicator | Calculation type | Reporting cycle | New indicator | Desired performance | indicator responsibility
2.1 Free Basic Electricity
2.3 Roads, bridges and stormwater management
| Number of km of Nkowankowa A Codesa and Hani Street paved | Upgrading of municipal road from gravel to paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | % of kilometers of the road upgraded | None | Output | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| % of planning, designs and site handover | Develop designs for Marirone to Motupa road | Perform preliminary investigation, scoping and design documentation | Approval of design report | % of design work completed | Delays in implementation of the project | Acticity | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number of km of Mulati Access road upgraded from gravel to Paving | Upgrading of municipal road from gravel to paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | % of kilometers of the road upgraded | None | Output | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number of km of Matapa to Leseka Access road from gravel to tar | Upgrading of municipal road from gravel to paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | % of kilometers of the road upgraded | None | Output | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number of km of Moseanoka to Cell C Pharare Internal streetsupgraded from gravel to paving | Upgrading of municipal road from gravel to paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | % of kilometers of the road upgraded | None | Output | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number of km of Risaba, Mnisi, Shando to Driving School Internal Street upgraded from gravel to paving | Upgrading of municipal road from gravel to paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | % of kilometers of the road upgraded | None | Output | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number of km of Main road from Ndhuna Mandlakazi, Efrika, Zangoma, Mpenyisi to Jamba Cross Internal Street (in Ward 13, Mandlakazi) and Nwamitwa Bridge via Nhlengeleti School to Taxi Rank, Clinic via Lwandlamoni School to Nwamitwa/Mandlakazi Road upgraded from gravel to paving | Upgrading of municipal road from gravel to paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | % of kilometers of the road upgraded | None | Output | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number of km of Nwamitwa Bridge via Nhlengeleti School to Taxi Rank, Clinic via Lwandlamoni School to Nwamitwa/Mandlakazi Road upgraded from gravel to paving | Upgrading of municipal road from gravel to paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | % of kilometers of the road upgraded | None | Output | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| % of planning and designs for the upgrading of Nkowakowa B Streets (Hope of Christ Street, Bombelani School Street, Giyani Soshangani Street and Xirhombarhomba Street) | Upgrading of municipal road from gravel to paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | % of kilometers of the road upgraded | None | Output | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| % of Planning and designs for the upgrading of Topanama Access Road | Develop designs for upgrading of Topanama Access Road | Perform preliminary investigation, scoping and design documentation | Approval of design report | % of design work completed | Delays in implementation of the project | Acticity | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| % of planning and designs for the upgrading of Thapane Street | Develop designs for upgrading of Thapane Street d | Perform preliminary investigation, scoping and design documentation | Approval of design report | % of design work completed | Delays in implementation of the project | Acticity | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number of km for the construction of Tickyline to Makhwibuding storm water drainage systems. | Construction of Tickeyline to Makhwibidung Stormwater Drainage System | To make the road accessible during adverse rainy condition | Completion certificate | Measuring number of kilometers of drainage system | Delays in implementation of the project | Activity | Carry Over | Quarterly | Yes | Improved roads accessibility for motorists and pedestrians | ESD
| % of planning and designs for the upgrading of Lenyenye Streets | Develop designs for upgrading of Lenyenye Streets | Perform preliminary investigation, scoping and design documentation | Approval of design report | % of design work completed | Delays in implementation of the project | Acticity | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| % of planning and designs for the upgrading of Zangoma to Mariveni Road | Develop designs for upgrading of Zangoma to Mariveni Road | Perform preliminary investigation, scoping and design documentation | Approval of design report | % of design work completed | Delays in implementation of the project | Acticity | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| % of planning and designs for the upgrading of Nkowakowa Section D Streets (Tommy Spaza Shop via Bridge, Mashaba via Vodacom and Raymond Makelana Streets) | Develop designs for upgrading of Nkowakowa Section D Streets (Tommy Spaza Shop via Bridge, Mashaba via Vodacom and Raymond Makelana Streets) | Perform preliminary investigation, scoping and design documentation | Approval of design report | % of design work completed | Delays in implementation of the project | Acticity | Carry Over | Quarterly | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number of speed humps constructed | Appointment of sevice provider to develop designs, appointment of a contractor & low level bridges constructed | Construct low level bridges to improve access by road users | SDBIP Quarterly Reports | Counting number of bridges constructed | None compliance Procurement plan | Output | Cumulative | Quarterly | No | Improved road infrastructure in the municipality | ESD
| Number of walk-behind rollers purchased | Purchase of 2 x walk-behind compaction rollers | Compaction of roads during pothole repairs | Delivery note | Counting number of rollers purchased and delivered | Non-compliance with procurement plan | Output | Carry Over | Quarterly | Yes | Improved road infrastructure in the municipality | ESD
| Number of TLBs and Graders purchased | Purchase of 1 x TLB and 1 x Grader and | TLB for excavations and grader for roads maintenance | Delivery notes | Counting number of TLBs and Grader purchased and delivered | Non-compliance with procurement plan | Output | Carry Over | Quarterly | Yes | Improved road infrastructure in the municipality | ESD
Electrification Projects
| # of households electrified in current financial year | Identify villages to be electrified as per backlog list, confirm capacity availability of capacity with Eskom, apply for funding, appoint consultant, surveyed stands, verify surveyed stands, consultant designs & specification, present to Eskom TEF& approve by Eskom, Appoint contractor, project handed over , contractor construct electrical network, Book outage with Eskom, Energized & Hand over to Eskom | Access to Basic service Electricity netowork | SDBIP Quarterly Reports | Average % of milestone achieved | Planned number of connection not equivalent to surveyd stands/ Difficult in getting approval by Eskom/Prices not market related | Output | Cumulative | Quarterly | No | Improve lighting in crime hotpot areas | EED
| R-value spent on maintenance of the electricity infrastructure | Operational budget spent on maintennce of electrical infrastructure guided by approved maintenance plan | Perform maintenance of the electrical netowk | SDBIP Quarterly Reports | Budget spent on maintenance | Data from EMS for funds spent on maintenance. Insufficient manaintenance performed | Output | Cumulative | Quarterly | No | Prolong the lifespan of the electrical network | EED
| % of Electricity Loss | Measure of Electricity network technical and non-technical losses.Electricity purchased from Eskom over Electricity sales | Reduction financial losses caused by Electricity, ensure that Municipality remains financially viable from the sales of electricity | SDBIP Quarterly Reports | Average % of milestone achieved | Lack of sales of electricity data to enable the calculation of losses | Output | Cumulative | Annual | No | Reduce losses on electricity network/Improve reveue collection from Electricity sales | EED
| % of Electrification of Mavele Phase5 | Identify villages to be electrified as per backlog list, confirm capacity availability of capacity with Eskom, apply for funding, appoint consultant, surveyed stands, verify surveyed stands, consultant designs & specification, present to Eskom TEF& approve by Eskom, Appoint contractor, project handed over , contractor construct electrical network, Book outage with Eskom, Energized & Hand over to Eskom | Access to Basic service Electricity netowork | SDBIP Quarterly Reports | Average % of milestone achieved | Planned number of connection not equivalent to surveyd stands/ Difficult in getting approval by Eskom/Prices not market related | Output | Cumulative | Quarterly | No | Improve lighting in crime hotpot areas | EED
| % of Electrification of New Phepene | Identify villages to be electrified as per backlog list, confirm capacity availability of capacity with Eskom, apply for funding, appoint consultant, surveyed stands, verify surveyed stands, consultant designs & specification, present to Eskom TEF& approve by Eskom, Appoint contractor, project handed over , contractor construct electrical network, Book outage with Eskom, Energized & Hand over to Eskom | Access to Basic service Electricity netowork | SDBIP Quarterly Reports | Average % of milestone achieved | Planned number of connection not equivalent to surveyd stands/ Difficult in getting approval by Eskom/Prices not market related | Output | Cumulative | Quarterly | Yes | Improve lighting in crime hotpot areas | EED
| % of Electrification of New Rita | Identify villages to be electrified as per backlog list, confirm capacity availability of capacity with Eskom, apply for funding, appoint consultant, surveyed stands, verify surveyed stands, consultant designs & specification, present to Eskom TEF& approve by Eskom, Appoint contractor, project handed over , contractor construct electrical network, Book outage with Eskom, Energized & Hand over to Eskom | Access to Basic service Electricity netowork | SDBIP Quarterly Reports | Average % of milestone achieved | Planned number of connection not equivalent to surveyd stands/ Difficult in getting approval by Eskom/Prices not market related | Output | Cumulative | Quarterly | Yes | Improve lighting in crime hotpot areas | EED
| % of Electrification of Winny Mandela | Identify villages to be electrified as per backlog list, confirm capacity availability of capacity with Eskom, apply for funding, appoint consultant, surveyed stands, verify surveyed stands, consultant designs & specification, present to Eskom TEF& approve by Eskom, Appoint contractor, project handed over , contractor construct electrical network, Book outage with Eskom, Energized & Hand over to Eskom | Access to Basic service Electricity netowork | SDBIP Quarterly Reports | Average % of milestone achieved | Planned number of connection not equivalent to surveyd stands/ Difficult in getting approval by Eskom/Prices not market related | Output | Cumulative | Quarterly | Yes | Improve lighting in crime hotpot areas | EED
2.4 Solid Waste management
600 | Number of households with access to weekly kerbside solid waste collection(5 formal Towns) | Development of refuse removal program, placement of skip bins at strategic points, weekly collections at the urban households and business establishments | Provide basic refuse removal services to rural households | SDBIP Quarterly Reports | Counting number of households were refuse is collected | None compliance Procurement plan | Output | Cumulative | Quarterly | No | Increased number of households and business establishment with access to basic refuse removal | Director Technical Services
| # of Rural Waste Service Areas serviced (Level 2 waste management) | Development of refuse removal program, placement of skip bins at strategic points, weekly collections at the urban households , rural and business establishments | Provide basic refuse removal services to rural households | SDBIP Quarterly Reports | Counting number of households were refuse is collected | None compliance Procurement plan | Output | Cumulative | Quarterly | No | Increased number of households and business establishment with access to basic refuse removal | Director Technical Services
| Number of commercial,institutional and industrial centres with access to solid waste removal services | Development of refuse removal program, placement of skip bins at strategic points, weekly collections at the urban households and business establishments | Provide basic refuse removal services to rural households | SDBIP Quarterly Reports | Counting number of households were refuse is collected | None compliance Procurement plan | Output | Cumulative | Quarterly | No | Increased number of households and business establishment with access to basic refuse removal | Director Technical Services
| Amount of Cubic meters of waste disposed at the landfilled side | Weighing of refuse disposed at the landfill site and report monthly on the SANWIS protal. | Provide accurate statistics on waste to DEFF. | SDBIP Quarterly Reports | Weighing amoount of refuse to be disposed at the landfill site. | malfunctioning of the weigh bridge due to power cuts and an outdated system. | Activity | Cumulative | Quarterly | Yes | Improved Solid Waste management systems. | Director Community Services
2.5 Recreational facilities
| Meter of Fence erected at Nkowankowa cemetery extension | Concrete palisade fencing of Nkowankowa cemeteries | Improve security at cemeteries | Project report | % of the number of cemeteries fenced | None | Output | Carry Over | Quarterly | No | Improved cemetries with security features | ESD
| Meters of Fence erected at Lenyenye cemetery | Concrete palisade fencing of Lenyenye cemeteries | Improve security at cemeteries | Project report | % of the number of cemeteries fenced | None | Output | Carry Over | Quarterly | No | Improved cemetries with security features | ESD
2.6 maintenance and repairs
| % of water samples(at GTM water purification plants)compying wit SANS 241 | Water samples collected from water purification for testing to ensure compliance SANS 241 standards | To promote safe livelihood of consumers and enforce quality control | Water test results from the laboratory | % of water samples compliant with minimum requirements | None | Outcome | Stand-alone | Monthly | No | Health and safety of water consumers in the municipality | ESD
| Number of maintaince activities on municipal buildings and properties | Regular inspections of municipal buildings, development of maintenance plan & regular maintenance of municipal buildings | To ensure that municipal buildings are regularly maintained | SDBIP Quarterly Reports | Counting the number of buildings maintained | None compliance Procurement plan | Output |  | Quarterly | No | Increased life span of assets | ESD
| Number of municipal fleet maintened | List of municipal vehicles that are operational in a month under reporting versus the total available municipal fleet | Ensure that employees have access to municipal fleet at all times | Monthly fleet report | % of operational municipal (number of operational fleet over the total number of municipal fleet) | Fleet that is redundant or obsolete requiring auction | Outcome | Stand-alone | Monthly | No | Availability of vehicles as tools of trade | ESD
| Number of square meter of tarred municipal roads patched | Upgrading of municipal roads from gravel to tar and paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | Consolidate total number of kilometers of the roads upgraded | None | Output | Last Value | Annual | No | Improved roads accessibility for motorists and pedestrians | ESD
| Number Kilometers of municipal roads graded | Upgrading of municipal roads from gravel to tar and paving with concrete blocks | Ensure access to communities and public amenities during all weather conditions | MIG projects report | Consolidate total number of kilometers of the roads upgraded | None | Output | Last Value | Annual | No | Improved roads accessibility for motorists and pedestrians | ESD
500 | Number of municipal parks and gardens maintained | Development of maintenace plan, conduct daily routine maintenance of parks and gardens | To ensure that parks and gardens are maintained to serve as recreational facilities | SDBIP Quarterly Reports | Counting the number parks and gardens maintained | None compliance Procurement plan | Output | Cumulative | Quarterly | No | Sustainable service delivery provision | CSD
500 | Number of municipal machines maintained | Regular inpections of machines, evaluate mechanical faults on machines and send out report for repair to service provider. Ensure that machines are not out service for longer than 3 days | To ensure that machines are well maintained so that service delivery is not interrupted | SDBIP Quarterly Reports | Counting number of machines maintained | None compliance Procurement plan | Output | Cumulative | Quarterly | No | Sustainable service delivery provision | ESD
| Replacement of traffic lights control boxes | [10 empty] | EED
| R-value spent on maintenance of the electricity infrastructure | Operational budget spent on maintennce of electrical infrastructure guided by approved maintenance plan | Perform maintenance of the electrical netowk | SDBIP Quarterly Reports | Budget spent on maintenance | Data from EMS for funds spent on maintenance. Insufficient manaintenance performed | Output | Cumulative | Quarterly | Yes | Prolong the lifespan of the electrical network | EED
Library Facility
| # of Library users | Monitoring the number of people using the GTM libraries | The number of people using the GTM libraries indicate the effectivess of the library services. | The electronic security system at the library entrances count the numbers of people entering/leaving the libraries. | The number recorded at the beginning of each month is subtracted from the number recorded at the end of the month. The total is further divided according to the type of entrance gates at the libraries. | The electronic security system does not work during power outages. When the power is down, the number of users are counted manually. | Output | Cumulative | Monthly | No | Increased number of library users | CSD
2.6 Building Control
| # of contravention notices issued to decrease non-compliance to building regulation | Notices of contravention issued for non-compliance with the National Building Regulations | To enforce compliance with the National Building Regulations | Notices of contravention | Counting number of notices of contravention issued | Months in which there are no contraventions | Outcome | Cumulative | Monthly | No | Decreased rate of contraventions | ESD
| % of ablution block, offices and storage facilities constructed | Construction of office block with ablution and storage facilities at Tzaneen Testing Ground | To create more office space with conducive working environment | Completion certificate | % of office, ablution block and storage facility constructed | Non-compliance with procurement plan | Output | Carry Over | Quarterly | Yes | Conducive working Environment | ESD
| % of roof revamped at Civic Centre | Refurbishment of existing roof at Tzaneen Civic Centre | To create healthy and safe work environment during all weather conditions | Completion certificate | % of roof revamped | Non-compliance with procurement plan | Output | Carry Over | Quarterly | No | Conducive working Environment | ESD
2.7 Other Assets
| Number of High Mast lights erected at Nkowankowa, Petanenge, Zangoma/Mariveni, Moime/Shikwambana, Lusaka, Sethong and Moleketla | Erection of highmast light at Nkowankowa, Petanenge, Zangoma/Mariveni, Moime/Shikwambana, Lusaka, Sethong and Moleketla | To reduce criminal activities by increase streetlighting during night | Projects report | Counting number of highmast lights erected | Non-compliance with procurement plan | Output | Carry Over | Quarterly | Yes | Reduced criminal activities | ESD
| % of power generators supplied and installed for Aqua Park Booster Pump Station | Installation of diesel power generator at Aqua Park pumpstation | To ensure power supply during electricity outages / cut-off | Commissioning certificate | % of power generators installed | Non-compliance with procurement plan | Output | Carry Over | Quarterly | Yes | Uninterrupted power supply | ESD
| % of fleet management systems procured | Installation of fleet management system on municipal assets | To monitor the usage of municipal fleet and fuel consumption | Installation certificate | % of fleet management system installed and functional | Non-compliance with procurement plan | Output | Carry Over | Quarterly | Yes | Reduced number of offences and reduced fuel consumption | ESD
| Number of Waste Removal Trucks procured | Purchase of 1 x waste removal truck | To improve waste collection in towns and townships | Delivery note | Counting number of waste removal trucks purchased and delivered | Non-compliance with procurement plan | Output | Carry Over | Quarterly | Yes |  | ESD
| Number of Trailers for Traffic Officers Procured | Conduct needs analysis,develop specifications, advertise and procurement of trailers for traffic officers | To impve service delivery | SDBIP Quarterly Reports | Counting number of trailers for traffic officers are purchased | None compliance to Procurement plan | Output | Cumulative | Quarterly | No | Sustainable service delivery provision | ESD
| Number of Vehicles Procured | Conduct needs analysis,develop specifications, advertise and procurement of a vehicle | To improve service delivery | SDBIP Quarterly Reports | Counting number of vehicles are purchased | None compliance to Procurement plan | Output | Cumulative | Quarterly | No | Sustainable service delivery provision | ESD
| Number of Vehicles Procured | Conduct needs analysis,develop specifications, advertise and procurement of a vehicle | To improve service delivery | SDBIP Quarterly Reports | Counting number of vehicles are purchased | None compliance to Procurement plan | Output | Cumulative | Quarterly | No | Sustainable service delivery provision | ESD
| Number of IT equipments purchased | Conduct needs analysis,develop specifications, quatations and procurement of IT equipments | To improve the IT network system | SDBIP Quarterly Reports | Counting number of IT equipments purchased | None compliance to Procurement plan | Output | Cumulative | Quarterly | No | Effective communication IT systems | CORP
500 | Number Office furniture purchased | Develop specifications, quotations and procurement of office furniture | To provision of furniture to staff for effective service delivery | SDBIP Quarterly Reports | Counting the number of furniture purchased | None compliance to Procurement plan | Output | Cumulative | Quarterly | No | Conducive working Environment | CFO
KPA 3:LOCAL ECONOMIC DEVELOPMENT
IDP Strategic Objective:Promote local economic growth
Vote No | Indicator title | Short defination | Purpose/importance | Source/collection of data | Method of calculation | Data limitations | Type of indicator | Calculation type | Reporting cycle | New indicator | Desired performance | indicator responsibility
400 | # of jobs created through municipal LED initiatives and capital projects | Establishment of a forum for engagement n order to promote economic growth | To provide support for local economic development | SDBIP Quarterly Reports | Counting number of LED Forums held | None | Output | Cumulative | Quarterly | No | Job creation in order to improve quality of life of the people of the municipality | PED
| # of SMME's supportted | Support SMMEs with business registration, provide business training and capacity | Strengthen local economic development | SDBIP Quarterly Reports | Counting number of SMME | Poor attendance by SMMEs | Output | Cumulative | Quarterly | No | Empower SMMEs | PED
| # of Local reference committee meetings held (CWP) | Area based programme,intended to be ongoing, this allows it to target the poorset area where market -based jobs are lightely to come anytime soon | T o provide support to CWP committee, the rarget unmployed and under employed people | SDBIP Quarterly Reports | Counting numbers of CWP meeting | None | Output | Cumulative | Quarterly | No | Creation of job opportunities | PED
| # of LIBRA education meeting held |  |  | SDBIP Quarterly Reports | Calculating number of LIBRA education meeting | None | Output | Cumulative | Quarterly | No |  | PED
400 | # Agricultural EXPO | Professional promotion and marketing for the agricultural sector in the municipal arrea focing expobitio n and other public initiative in the interest of agricultuaral role players, the government and and the public | Promotional agricultural activies under the municipal area | SDBIP Quarterly Reports | Calculating number of Agricultiral | None | Output | Cumulative | Quarterly | No | Promotional of the sector | PED
| Number active of jobs creared through municipal EPWP projects (NKPI)(Full time equivalent) | Failitate appointments & support programme | Creation of jobs | SDBIP Quarterly Reports | Number of work opportunities created through EPWP | Delay and dispute in appointments | Output | Cumulative | Quarterly | No | Job creation in order to improve quality of life of the people of the municipality | ESD
| # of committed investors attracted through GTEDA | Promote a conducive investment climate in the Greater Tzaneen Municipal area and attract suitable investors | Investment attraction to suport SMMEs or establishment of new ventures | SDBIP Quarterly Reports | Number of investors attracted through GTEDA | Lack of incentives and available recourses | Output | Non-cumulative | Annually | No | Facilitation of investment attraction | GTEDA
| # of SMME development and support | Support SMMEs with business registration, provide business training and capacity | Strengthen local economic development | SDBIP Quarterly Reports | Counting number of SMME | Poor attendance by SMMEs | Output | Cumulative | Quarterly | No | Empower SMMEs
5 | # of LED projects implemented through Agricultural Business Incubator | Establishment of an agricultural business incubator | The aim of the incubator is to support the development of SMMEs from the early stages and to cater for all smallholder and small commercial farmers located within the entire GTM | SDBIP Quarterly Reports | The number of SMMEs supported through the incubator | Incubatees lack of intake agreements | Output | Cumulative | Quarterly | No | To support SMMEs and provide training | GTEDA
| # Promotional events attended and exhibited | Facilitation of promotional events for SMMEs and providing exposure to marketing opportunities. | To create a marketing platform between key role players, promotion and showcasing of SMME products to specific audience/ target. To empower and promote the participation of youth entrepreneurs/ SMMEs | SDBIP Quarterly Reports | The number of promotional events facilitated | Lack of access to market opportunities. | Output | Cumulative | Quarterly | No | Providing marketing platforms for SMMEs | GTEDA
| Workplace Skills Development Plan (WSP) submitted to LG Seta by 30 April | Compile the organisational skills needs. Appoint service providers to conduct trainings. Facilitate LGSETA discretionary grant for employed and unemployed learners. Compile training reports | To ensure capacity building and skills development and training for both employed and unemployed | Annually | Number of employees trained inline with the WSP | None adherence to WSP | Output | Cumulative | Quarterly | No | Skilled and capacitated workforce in order to maximise performance | GTEDA
| Annual Report submitted to the municipality by 15 January | Table Annual Budget to Board and to Council at least 90 days before the start of the budget year in line wiuth MFMA regulations | To improve financial management and to ensure compliance of the MFMA | SDBIP Quarterly Reports | Counting number of budget reports submitted to council | None | Output | Cumulative | Quarterly | No | Sound financial management and Compliance to MFMA | GTEDA
| # of Submission of the GTEDA business plan to GTM | A written document describing a company's core business activities, objectives, and how it plans to achieve its goals | To identify, describe and analyze a business opportunity and/or a business already under way, examining its technical, economic and financial feasibility. | SDBIP Quarterly Reports | Counting number of business plan | None | Output | Cumulative | Quarterly | No | Sound financial management and Compliance to MFMA | GTEDA
| Number of Strategic Risk mitigated | Table Annual Budget to Board and to Council at least 90 days before the start of the budget year in line wiuth MFMA regulations | To improve financial management and to ensure compliance of the MFMA | SDBIP Quarterly Reports | Counting number of budget reports submitted to council | None | Output | Cumulative | Quarterly | No | Sound financial management and Compliance to MFMA | GTEDA
| Audited Financial Statement submitted to AGSA by 31 August | Compile the financial statements. Review the compiles AFS. Present the AFS to Audit Committee. Submit the AFS to AG for auditing by 31 August | To ensure that financial statements are submitted to AG within timeframes | SDBIP Quarterly Reports | Number of reports submitted within prescribed timeframes | Financial errors | Output and activity | Non-cumulative | Quarterly | N0 | Compliance to MFMA | GTEDA
| #Annual Budget Approved by May | Table Annual Budget to Board and to Council at least 90 days before the start of the budget year in line wiuth MFMA regulations | To improve financial management and to ensure compliance of the MFMA | SDBIP Quarterly Reports | Counting number of budget reports submitted to council | None | Output | Cumulative | Quarterly | No | Sound financial management and Compliance to MFMA | GTEDA
| # LED projects implemented Waste Management for SMMEs | Establishment of a Waste Management programme in rural communities | To promote environmental education and awareness in rural communities. To create sustainable livelihoods through waste management by identifying waste recycling projects and to support the use of environmentally friendly waste disposal technology. | SDBIP Quarterly Reports | The number of waste recycling businesses supported | Lack of funding to support rural waste recycling projects. | Output | Cumulative | Quarterly | No | To create job opportunities for the youth in the rural areas of the Greater Tzaneen and to support the use of environmentally friendly waste disposal/management. | GTEDA
| % Budget Spent | Monitor the expenditure of the budget | Strengthen the effectiveness and efficient of municipal financial management in line with MFMA regulations | SDBIP Quarterly Reports | Calculating percentage budgetexpenditure on quarterly basis. | None compliance to MFMA | Input and output | Cumulative | Quarterly | No | Improved management of municipal grants spending | GTEDA
| # of SMME's assisted with registration | Support SMMEs with business registration, provide business training and capacity | Strengthen local economic development | SDBIP Quarterly Reports | Counting number of SMME | Poor attendance by SMMEs | Output | Cumulative | Quarterly | No | Empower SMMEs
| # Internal Audits Conducted | Monitor implementation of internal audit action plan | To improve the entity's internal controls and systems | Internal audit Quarterly Reports | Number of queries resolved on the internal Audit Action Plan divide by number of findings | Delay in resolving internall audit findings | Output and activity | Non-cumulative | Quarterly | No | To promote accountability and responsibility | GTEDA
| # LED projects implemented Tzaneen Farmer Support Facility | Establishment of a farmer support facility to support local farmers in partnership with FABCO | Identify the number of farmers that can be supported in the area (both commercial and emerging), Identify one commodity to be supported (mango) and assess the level of support that can be provided/given to the identified commodity, conduct needs assessment and Commodity analysis. | SDBIP Quarterly Reports | The number of farmers supported through the farmer support facility | Lack of access to markets. Lack of available equipment to the farmers. High transportation costs of goods to the market as well as high production input costs. Lack of skills. | Output | Cumulative | Quarterly | No | Providing required support to emerging farmers to grow the indistry. | GTEDA
KPA 4:FINANCIAL VIABILITY
IDP Strategic Objective: Sound Financial Management
Vote No | Indicator title | Short defination | Purpose/importance | Source/collection of data | Method of calculation | Data limitations | Type of indicator | Calculation type | Reporting cycle | New indicator | Desired performance | indicator responsibility
| Number Annual Budget submitted to Council by 31 May | annual budget lays out a municipality's projected income and expenses for a 12-month period | Projection of the municipality revenue and expenditure in the financial year | SDBIP Quarterly Reports | Counting the annual budget | None | Output | Cumulative | Quarterly | No | Funded annual budget | CFO
| # of properties on Valuation roll billed for assessment rates | document that consists of property information of all rateable properties within the boundaries of a municipality | Generation of revenue | SDBIP Quarterly Reports | Counting valuation billed | None | Output | Cumulative | Quarterly | No | Complete and updated valuation roll | CFO
| Number of assets update schedules | Maintain assests register of assets additions with supportung documents | To ensure a copmlete updated assests register in term of GRAP | SDBIP Quarterly Reports | Counting number of Assests Schedules | None | Output | Cumulative | Quarterly | No | Efficetive assests management | CFO
| Number of Annual Asset Verification report concluded by 31 Aug | Receive new acquisation,bar code and capture into the asset register. Capture the expense of the project in progress. When project is completed the unbundling and capitalisation ito the asset register takes effect. | To ensure that the Asset Register is compiled according to the required standards so that it becomes credible. | SDBIP Quarterly Reports | Calculting number of asset verifications conducted | Unaccountated assets | Output | Cumulative | Quarterly | No | Asset GrRAP compliant in order to increase thr life span of municipal assets | CFO
| % Of adjudicated bids over closed bids that has been advertised | Competitive Bids that are awarded by the municipality must be awarded by a Bid Adjudication committee | Improved integrity | SDBIP Quarterly Reports | % bids adjuducated | None | Output | Cumulative | Quarterly | No |  | CFO
| Number of compliant in-year SCM reports submitted on time to Council and Treasury | Generate SCM quarterly and submit to council | To report to council compliance regarding SCM activities | SDBIP Quarterly Reports | Counting number of SCM reports submitted to council | None | Output | Cumulative | Quarterly | No | Effective utilization of fleet | CFO
Number of times that current interest payment can be covered with available operating income excluding depreciation and impairement
| % of revenue collected (revenue billed over revenue collected) | Protection and enhencement of revenue base of the municipality | To improve municipal liquidity status of the municipality | SDBIP Quarterly Reports | % of debt collected | None payment for services | Output | Cumulative | Quarterly | No | Improved revenue collection | CFO
| % of debt coverage ratio(operating income divided by debts service owing | Protection and enhencement of revenue base of the municipality | To improve municipal liquidity status of the municipality | SDBIP Quarterly Reports | % of debt collected | None payment for services | Output | Cumulative | Quarterly | No | Improved revenue collection | CFO
| Number of S71 reports submitted to the mayor and provincial treasury within 10 working days of start of the month | Generate monthly financial expenditure reports. Submit these reports to the Mayor and Treasury 10 working days after the start of the month | To ensure compliance of the MFMA | SDBIP Quarterly Reports | Counting number of reports submitted within 10 days of the start of the month | None | Output | Cumulative | Quarterly | No | Sound financial management | CFO
| Number of S52 reports submitted to Council within 30 days of the end of each quarter | Generate quarterly financial expenditure reports. Submit these reports to council every quarter | Financial accountability | SDBIP Quarterly Reports | Counting number of quarterly reports submitted to council | None | Output | Cumulative | Quarterly | No | Sound financial management | CFO
| Number of S72 reports submitted to Council and provincial treasury after assessment by the accounting officer by 25 january | Generate six month financial and performance reports and advice budget adjustment accordingly | Financial accountability | SDBIP Quarterly Reports | Counting number of mid-year financial reports submitted to council | None | Output | Cumulative | Quarterly | No | Sound financial management | CFO
| Number of Adjustment Budget reports submitted to Council in terms of S28 | Make budget adjustment as per section 72 report recommendations. Submit such to council | To improve financial management and service delivery | SDBIP Quarterly Reports | Counting number of budget adjustment reports submitted to council | None | Output | Cumulative | Quarterly | No | Sound financial management and improved service delivery | CFO
|  | Make budget adjustment as per section 72 report recommendations. Submit such to council | To improve financial management and service delivery | SDBIP Quarterly Reports | Counting number of budget adjustment reports submitted to council | None | Output | Cumulative | Quarterly | No | Sound financial management and improved service delivery | CFO
| Submission of annual financial statements to the A-G within the prescribed timeframes | Compile the financial statements. Review the compiles AFS. Present the AFS to Audit Committee. Submit the AFS to AG for auditing by 31 August 2019 | To ensure that financial statements are submitted to AG within timeframes | SDBIP Quarterly Reports | Number of reports submitted within prescribed timeframes | Financial errors | Output and activity | Non-cumulative | Quarterly | N0 | Compliance to MFMA | CFO
| Draft Annual Performance report submitted within regulated time | Compile the Draft Annual Report. Review the compiles DAR. Present the DAR to Audit Committee. Submit the DAR to AG for auditing by 31 August 2019 | To ensure that Annual Performance Report is submitted to AG within timeframes | SDBIP Quarterly Reports | Number of reports submitted within prescribed timeframes | Reliability of the data submitted. | Output and activity | Non-cumulative | Quarterly | No | Compliance to MFMA | Municipal Manager
| % of personnel budget spent | Monitor the expenditure of personnel budget | Strengthen the effectiveness and efficient of municipal financial management in line with MFMA regulations | SDBIP Quarterly Reports | Calculating percentage personnel budgetexpenditure on quarterly basis. | None compliance to MFMA | Input and output | Cumulative | Quarterly | New indicator | Improved management of municipal grants spending | CFO
| % of MIG Expenditure | Capture spending on MIG projects . Compile spending report in terms of section 71 reports | To ensure effective implementation of MIG projects in order to ensure acceleration of delivery of basic service (infrastructure development) | SDBIP Quarterly Reports | Calculating percentage MIG expenditure on quarterly basis. | None compliance to procurement plan | Input and output | Cumulative | Quarterly | No | Improved management of municipal grants spending | CFO
| % of maintenance budget spent | Monitor the allocation of operation and maintenance budget | Strengthen the effectiveness and efficient of municipal financial management in line with MFMA regulations | SDBIP Quarterly Reports | Calculating percentage operation and maintenance budget allocated | None compliance to MFMA | Input and output | Non-Cumulative | Quarterly | New indicator | Accelerated service delivery | CFO
| % of capital budget spent | Monitor the expenditure of capital budget | Strengthen the effectiveness and efficient of municipal financial management in line with MFMA regulations | SDBIP Quarterly Reports | Calculating percentagecapital budget expenditure on quarterly basis. | None compliance to MFMA | Input and output | Cumulative | Quarterly | New indicator | Improved management of municipal capital spending | CFO
KPA 5:GOOD GOVERNANCE AND PUBLIC PARTICIPATION
IDP Strategic Objective: Build capable institution and administration
Vote No | Indicator title | Short defination | Purpose/importance | Source/collection of data | Method of calculation | Data limitations | Type of indicator | Calculation type | Reporting cycle | New indicator | Desired performance | indicator responsibility
5.1 Auditing and Risk Management
200 | Number of Improved audit opinion | Auditor's opinion on whether a municipality's financial statements comply with GAAP and are free from material misstatement. | to form a view on whether the information presented in the financial report, taken as a whole, reflects the financial position of the municipality at a given date | Imprived audit opinion | Calcalating the audit opinion | None | Output and activity | Non-cumulative | Quarterly | No | To promote good governance and finincial viability | Municipal Manager
200 | Number of AG Action Plan submitted to Council by 31 Jannuary | Monitor the process of development and approval of AG action plan | To improve municipal internal controls and systems | AG Action plan | Recognised the Submitted AG action plan to Council | Delays on the development of AG action plan | Output and activity | Non-cumulative | Quarterly | No | To promote accountability and responsibility | Municipal Manager
| % of A-G quieries resolved | Monitor the implementation of AG Audit action plan | To improve municipal internal controls and systems | AG Action plan progress report | Divide the number of queries resolved by the number of queries raised | Delay in resolving AG Audit plan queries | Output and activity | Non-cumulative | Quarterly | No | To promote accountability and responsibility | Municipal Manager
| Number of Risk Based Internal Audit Plan approved | In a risk-based audit approach, the goal for the department is to address management's highest priority risks. | Audit that analyzes audit risks, sets materiality thresholds based on audit risk analysis and develops audit programs that allocate a larger portion of audit resources to high-risk areas | SDBIP Quarterly Reports | Calculating the achievements of the indicator through achievements of the quarterly targets. | None | Output and activity | Non-cumulative | Quarterly | No | To promote accountability and responsibility | Municipal Manager
| Number of PMS report submitted to council | Develop a reporting template and sent to departments, receive completed template and consolidate into one report.Submit the report to council for approval | The indicator seeks to ensure organisational reports are developed and submitted to council. To measure the performance of the IDP and budget. | SDBIP Quarterly Reports | Calculating the achievements of the indicator through achievements of the quarterly targets. | Delay in submission of reports by Directorarates and reports submitted without POE | Output | Cumulative | Quarterly | No | To improve municipal performance | Municipal Manager
| # of senior managers complying with the minimum competency levels (Municipal Finance Management Programme) | Monitor the fill of finance positions with financial minimum competency personnel | Strengthen the effctiveness and efficient of municipal financial management in line with MFMA regulations | SDBIP Quarterly Reports | Number of people appointed with the requisite skills | Unable to attract skillful people | Input and output | Cumulative | Quarterly | New indicator | Improved financial management in line with MFMA regulations | Corporate Services
| % of development of HR strategy | Articulate what an organization intends to do about its human resource management policies and practices now and in the longer term, | include recruitment, learning & development, performance appraisal, compensation, and succession planning | SDBIP Quarterly Reports | Calculating the achievements of the indicator through achievements of the quarterly targets. | None | Output | Cumulative | Quarterly | Yes | To improve municipal performance | Corporate Services
200 | Number of audit committee meetings held | Issue notices for Audit Committtee meetings. Invite stakeholders, prepare agendas and compile reports | To organise meetings of the Audit Committee | SDBIP Quarterly Reports | Counting number of audit committee meetings held | None | Output | Cumulative | Quarterly | No | Streghtened good governance | Municipal Manager
200 | Number of risk assessments conducted | To evaluate the effectiveness and suitability of existing control measures. | ultimately to improve workplace health and safety | SDBIP Quarterly Reports | Counting number of risk assessments conducted | None | Output | Cumulative | Quarterly | No | Streghtened good governance | Municipal Manager
| Number of board meetings held | the directors to talk about any issues that the company is facing, review the company's performance and discuss new policies to be enacted | to ensure the company's prosperity by collectively directing the company's affairs, while meeting the appropriate interests of its shareholders and relevant stakeholders | SDBIP Quarterly Reports | Counting number of board meeting held | None | Output | Cumulative | Quarterly | No | Streghtened good governance | Municipal Manager
| Number of Strategic Risk mitigated | Compile reports and submit to managemen, audit committee and council. | To measure progress regarding risk management in the municipality | Risks management Quarterly Reports | Number of risk reports submitted to council | Delay and lack of capacity to implement resolutions | Output and activity | Cumulative | Quarterly | No | Effective mitigation of risks in the municipality | Municipal Manager
| Number of Risk and compliance Committee meetings held | monitoring and approving the risk policies and associated practices of the Company | to provide objective review and oversight across the Group for all categories of risk, setting risk appetite and ensuring an appropriate risk framework | SDBIP Quarterly Reports | Counting Risk and compliance Committee | None | Output | Cumulative | Quarterly | No | Streghtened good governance | Municipal Manager
Safety and Security Management
| % of cases of theft of council items reported | Monitoring and Securing Council Infrastruture Assets | To improve Retention ofCouncil Assets | Cases reported and investigated internally and externally | Number of Cases reported each month | Unreported Cases by contracted service providers to avoid penalities | Output | Cummulative | Monthly | No | Reduced number of Thefts against Council assets | Community Services
5.2 Council and Oversight Structures (Putting people first)
200 | % of MPAC recommendated council resolution | Monitoring the implementation of MPAC resolutions | To promote good governance | MPAC resolutions register | Number of MPAC resolutions implemented divide by the total number of resolutions in the register | Delay and lack of capacity to implement resolutions | Output and activity | Non-cumulative | Quarterly | No | To promote accountability and responsibility | Municipal Manager
| Number of MPAC meetings held | Issue notices for MPAC meetings. Invite stakeholders, prepare agendas and compile reports | To ensure that oversight committee meetings are held | SDBIP Quarterly Reports | Counting number of MPAC meetings held | None | Output | Cumulative | Quarterly | No | Effective council oversight | Municipal Manager
10 | Number of council sitting held | Issue notices for council meetings. Invite stakeholders, prepare council agendas, compile minutes | To ensure that all council meetings are held in terms of statutory regulations | SDBIP Quarterly Reports | Counting number of council meetings held | None | Output | Cumulative | Quarterly | No | Effective and efficient functioning of council | Corporate Services
| % of GTM council resolutions implemented | Monitoring the implementation of council resolutions | To promote good governance | Council resolutions register | Number of Council resolutions implemented divide by the total number of resolutions in the register | Delay and lack of capacity to implement resolutions | Output and activity | Non-cumulative | Quarterly | No | To promote accountability and responsibility | Municipal Manager
| Number of schedule Executive committee meetings held | Issue notices for meetings. Invite stakeholders, prepare agendas and compile reports | To ensure that oversight committee meetings are held | SDBIP Quarterly Reports | Counting number of MPAC meetings held | None | Output | Cumulative | Quarterly | No | Effective council oversight | Municipal Manager
IDP Strategic Objective:Putting people first
5.4 Public Participation
200 | Number of public participation meetings (imbizos) held | Devlop public participaation progranm. Circulate the programme to stakeholders. Arrange all logistics for meetings. Compile reports and submit issues raised to the relevant epartments or stakeholders | To promote community participation and accountability | SDBIP Quarterly Reports | Number of public participation meetings held | Poor attendance by community members | Output and activity | Cumulative | Quarterly | No | To promote accountability
| Number of community feedback meetings held | Holding of ward meetings to monitor the frequency of providing feedback to communities | To promote community participation and accountability | SDBIP Quarterly Reports | Count the number of community feedback meetings held | None adherence to the schedule meetings and poor attendance by the community members | Output and activity | Cumulative | Quarterly | New indicator | To promote accountability
200 | % of compliants resolved | Monitor the number of compliants attended versus the number of compliants resolved | To promote accountability | Compliants management register | Count number of compliants attended divide by the number of compliants resolved | Delay and lack of capacity to resolve compliants | Output and activity | Cumulative | Quarterly | New indicator | To promote accountability
10 | Number of functional ward committees | Capacitate wards, receive reports from wards and submit those reports to the Office of the Speaker | To ensure functioning wards | SDBIP Quarterly Reports | Number of functional ward committees | None | Output | Cumulative | Quarterly | No | Effective and efficient community involvement | Corporate Services
10 | Number of monthly ward committees reports submitted | Develop ward reporting templates. Receive monthly reports, consolidate them and submit to the Office of the Speaker | To ensure accountability by ward committees | SDBIP Quarterly Reports | Counting number of ward committees reports received | None | Output | Cumulative | Quarterly | No | Good governance and accountability | Corporate Services
| # of monthly compliance assessments conducted on Licensing services (as set out in the SLA with Dpt of Transport) | Compile spreadsheed reports from conditions in SLA. Identify possible shortfalls. | Ensure that checklist be updated monthly and all reports be attached if received | SDBIP Quarterly Reports | Counting number of checklists or received inspection reports from Dept of Transport | None | Output and activity | Cumulative | Monthly | No | Improved service delivery and accessibility for all licensing clients | CSD
| % of development of IT strategy | a blueprint of how technology supports and shapes the organization's overall business strategy | to set overall goals for your business and to develop a plan to achieve them | SDBIP Quarterly Reports | % of IT strategy | None | Output | Cumulative | Quarterly | No | Good governance and accountability | Corporate Services
| Number of roadblocks conducted | Conduct a roadblock where all vehicles will be stopped and checked | To promote road safety and enforcement of road offenders. | SDBIP Quarterly Reports | Setup with proper raodblock with all roadblock signs and inspection sheet | None | Output and activity | Cumulative | Monthly | No | To promote road safety and enforcement of road offenders. | CSD
| % of disaster incidences responded to within 72 hours | Write a memorandum on the event to be held. Write invitations to the targeted stakeholders. Arrange all event logistics, stage the event and write a report. | To ensure that disaster risk management campaigns are held | SDBIP Quarterly Reports | Counting number of disaster risk management awareness campaigns held | None | Output | Cumulative | Quarterly | No | Appropriate response to disaster risk management | Municipal Manager
200 | Number disaster risks management awareness campaigns held | Write a memorandum on the event to be held. Write invitations to the targeted stakeholders. Arrange all event logistics, stage the event and write a report. | To ensure that disaster risk management campaigns are held | SDBIP Quarterly Reports | Counting number of disaster risk management awareness campaigns held | None | Output | Cumulative | Quarterly | No | Appropriate response to disaster risk management | Municipal Manager
KPA 6:MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
Vote No | Indicator title | Short defination | Purpose/importance | Source/collection of data | Method of calculation | Data limitations | Type of indicator | Calculation type | Reporting cycle | New indicator | Desired performance | indicator responsibility
IDP Strategic Objective: Build capable institution and administration
6.1 IDP
200 | Number of IDP/Budget adopted by Council by May | Compile IDP process plan and submit to Council for approval. Compile IDP analysis phase, organise IDP Rep.forums, conduct strategic planning session. Draft IDP/Budget completed and submitted to Council by 31 March. Conduct public participations. Final IDP/Budget submitted to council for adoption by 31 May. | The indicator seeks to ensure that IDP for financial year is reviewed | SDBIP Quarterly Reports | Calculating the achievements of the indicator through achievements of the quarterly targets. | None | Output | Non-cumulative | Quarterly | No | Improved municipal planning in order to improve service delivery | Municipal Manager
| Number of IDP Representative Forum meetings held | Compile IDP process plan and submit to Council for approval. Compile IDP analysis phase, organise IDP Rep.forums, conduct strategic planning session. Draft IDP/Budget completed and submitted to Council by 31 March . Conduct public participations. Final IDP/Budget submitted to council for adoption by 31 May. | The indicator seeks to ensure that IDP for financial year is reviewed | SDBIP Quarterly Reports | Calculating the achievements of the indicator through achievements of the quarterly targets. | None | Output | Non-cumulative | Quarterly | No | Improved municipal planning in order to improve service delivery | Municipal Manager
200 | Number of strategic planning session held | Write a memorandum on the event to be held. Write invitations to the targeted stakeholders. Arrange all event logistics, stage the event and write a report. | To ensure that IDP strategies are reviewed | SDBIP Quarterly Reports | Number of strategic planning sessions held | None | Output | Cumulative | Quarterly | No | Improved municipal planning in order to improve service delivery | Municipal Manager
IDP Strategic Objective: Build capable institution and administration
6.2 PERFORMANCE MANAGEMENT
200 | Number of senior managers ( section 54 and S56) with signed performance agreements within prescribed timeframe | Develop draft performance agreements for S54 & 56 Managers. Engage the relevant senior managers. Submit the final performance agreements for signing by the Mayor and Municipal Manager. Submit the signed agreements to MEC for Cooperative Governance, Human Settlements and Traditional Affairs. | The indicator seeks to ensure that S54 & 56 Managers signed performance agreements in terms of Section 57 of the MSA, Act 32 of 2000 | Signed performance agreements | Calculating the number of signed performance agreements | Delay in filling S56 Vvacant positions | Output | Non-cumulative | Quarterly | No | To improve municipal performance by holding Section 54 & 56 Managers accountable | Municipal Manager
200 | Number of formal assessements conducted (S54 & 56) | Set dates for individual S54 & S56 Managers for assessment. Establish panel and conduct assessments. Compile assements reports and submit to council. | The indicator seeks to achieve that formal performance assessment of S54 & 56 Managers are conducted | SDBIP Quarterly Reports | Calculating the number of formal performance assessments conducted | None adherence to the regulations | Output | Cumulative | Quarterly | No | Improved municipal individual performance that will enable them to accelerate the delivery of basic services | Municipal Manager
| Number of other officials other than S 56 managers with Performance Plans | Develop draft Performance Plans for officials other than S 56 managers. Engage the relevant officials. Submit the final Performance Plans for signing by the Official (Level 3 Manager) and Supervisor (The Director). | The indicator seeks to ensure that officials other than S 56 managers (Level 3 Managers) signed Performance Plans in terms of Municipal Systems Act (Section 67 (1) (d) ) and Schedule 2 of Code of Conduct for Municipal Staff (Section 3 (e )) | Signed performance Plans | Calculating the number of signed performance Plans | None adherence to the Municipal Systems Act (Section 67 (1) (d) ) and Schedule 2 of Code of Conduct for Municipal Staff (Section 3 (e )) | Output | Non-cumulative | Annually | No | Improved municipal individual performance that will ensure that the organisational strategic objectives are supported by the individual employee performance objectives and targets | Corporate Services
200 | Number of in-year performance management reports submitted to Council | Develop a reporting template and sent to departments, receive completed template and consolidate into one report.Submit the report to council for approval | The indicator seeks to ensure organisational reports are developed and submitted to council. To measure the performance of the IDP and budget. | SDBIP Quarterly Reports | Calculating the achievements of the indicator through achievements of the quarterly targets. | Delay in submission of reports by Directorarates and reports submitted without POE | Output | Cumulative | Quarterly | No | To improve municipal performance | Municipal Manager
| Number of Draft Annual Performance Report submitted to the AG, Audit Committee and Mayor by 31 August | Present the annual report to council for noting. Submit the report to AGSA and COGHSTA | To ensure that DAPR report is submitted to AGSA and Cogshta within prescribed time | SDBIP Quarterly Reports | Counting number of APR submitted to stakeholders | None | Output | Cumulative | Quarterly | No | Effective council oversight | Municipal Manager
| Number of Draft Annual Report | Present the annual report to council for noting.Conduct public participation on annual report, consolidate inputs, compile oversight report and able the report to council. | To ensure that oversight report is presented to council within prescribed time | SDBIP Quarterly Reports | Counting number of oversight reports tabled to council within prescribed time | None | Output | Cumulative | Quarterly | No | Effective council oversight | Municipal Manager
200 | Number of Final Annual and oversight reports adopted within stipulated timeframes | Present the annual report to council for noting.Conduct public participation on annual report, consolidate inputs, compile oversight report and able the report to council. | To ensure that oversight report is presented to council within prescribed time | SDBIP Quarterly Reports | Counting number of oversight reports tabled to council within prescribed time | None | Output | Cumulative | Quarterly | No | Effective council oversight | Municipal Manager
IDP Strategic Objective: Build capable institution and administration
6.3 Skils Development and Employment Equity
10 | Number of employees and councillors capacitated in terms of Workplace Skills plan | Conduct departmental skills audits. Compile municipal skills needs. Appoint service providers to conduct trainings. Compile training reports | The indicator seeks to ensure that capacity building of employees is done | SDBIP Quarterly Reports | Calculate the number of employees trained. | None adherence to work skills plan | Output | Cumulative | Quarterly | No | Skilled and capacitated workforce in order to accelerate service delivery | Corporate Services
10 | # of municipal personnel with technical skills/capacity (engineer & technicians (EED & ESD) | Monitor the filling of technical skills/capacity (engineer & technicians (EED & ESD) | Strenghten the capacity of the municipality to deliver on its mandate through appointment skillful and competent personnel | SDBIP Quarterly Reports | Number of people appointed with the requisite skills | Unable to attract skillful people | Input and output | Cumulative | Quarterly | New indicator | Accelerated delivery of basic services | Corporate Services
10 | Number of senior managers with financial minimum competency requirements | Monitor the fill of finance positions with financial minimum competency personnel | Strengthen the effctiveness and efficient of municipal financial management in line with MFMA regulations | SDBIP Quarterly Reports | Number of people appointed with the requisite skills | Unable to attract skillful people | Input and output | Cumulative | Quarterly | New indicator | Improved financial management in line with MFMA regulations | Corporate Services
10 | Number of people from employment equity target group employed in the three highest levels of the municipality (National indicator) | Compile employment equity report.Check the municipal vacancy rate rate (three highest levels).Set employment target for people from EE group. Identify possible positions to be occupied by people from this group. Advertise and appoint. | The indicator seeks to ensure that people from employment equity target are employed in the three highest levels of the municipality | SDBIP Quarterly Reports | Calculate the number of employeesevels from employment equity target employed from the three highest levels of the municipality | Unable to attract skillful people from EE group | Output | Cumulative | Quarterly | No | Implementation of the municipal employment equity plan in line with Employment Equity Act, 1998 (Act No.55 of 1998) | Corporate Services
IDP Strategic Objective: Build capable institution and administration
6.4. Human Resource Management, Legal Services & Occupational Health and Safety
10 | Amount actual spent( 1 % of the salary budget of municipality) on implementing workplace skills plan (National Indicator) | Set aside 1% of the wage bill to skills development | To ensure that 1% of the total municipal wage bill is utilized for skills development | SDBIP Quarterly Reports | Counting percentage of the wage bill set aside for skills development | None | Output | Cumulative | Quarterly | No | Skilled and capacitated workforce | Municipal Manager
10 | Number of Local Forum Meetings held | Organise LLF meetings and implement decisions agreed upon | To ensure that LLF meetings are held | SDBIP Quarterly Reports | Counting number of LLF meetings held | None | Output | Cumulative | Quarterly | No | Sound labour practice | Corporate Services
| # of workstations inspected for OHS contraventions | Conduct OHS inspections and generate quarterly compliance reports | To ensure that quarterly OHS compliance reports are generated | SDBIP Quarterly Reports | Counting number of OHS compliance reports generated | None | Output | Cumulative | Quarterly | No | Safe and health working environment | Corporate Services
10 | Number of in-year compliance reports on OHS generated | Conduct OHS inspections and generate quarterly compliance reports | To ensure that quarterly OHS compliance reports are generated | SDBIP Quarterly Reports | Counting number of OHS compliance reports generated | None | Output | Cumulative | Quarterly | No | Safe and health working environment | Corporate Services
IDP Strategic Objective: Build capable institution and administration
6.5 Policies and By-laws
10 | Number of by-laws developed/ reviewed | Identify by-laws to be developed and reviewed. Collect information. Call for inputs from stakeholders. Incorporate inputs and submit to council for approval. | To ensure enforcement of municipal regulations | SDBIP Quarterly Reports | Calculate the number of by-laws developed and reviewed | Delay in review and promuligation | Output | Cumulative | Quarterly | No | Improved municipal regulatory compliance | Corporate Services
| Number of policy workshops held | Design and implementation. Workshop Overview. This background note is designed to help orient and structure the preparation of training. | Spurring participants to investigate it further on their own, or can demonstrate and encourage the practice of actual methods | SDBIP Quarterly Reports | Calculate the number of policy workshop held | None | Output | Cumulative | Quarterly | No | Improved municipal governance through regulatory enviroment | Corporate Services
| Number of policies developed/reviewed | Identify policies to be developed and reviewed. Collect information. Call for inputs from stakeholders. Incorporate inputs and submit to council for approval. | To strengthen municipal governance | SDBIP Quarterly Reports | Calculate the number of policies developed and reviewed | Delay in review and development | Output | Cumulative | Quarterly | No | Improved municipal governance through regulatory enviroment | Corporate Services

## APPROVAL
Approval by the Mayor | In terms of section 54c of the MFMA the municipality should consider and,if necessary, make any revisios to the service delivery and budget implentation plan,provided that revisions to the service delivery targets and performance indicators in the plan may only be made with the approval of the council following approval of an adjustment budget
Monitoringt and Implementation of SDBIP | Progress against the objectives set out in the SDBIP will be monitored and reported on a monthly, quarterly, half-yearly and annual basis.
Signatures | Adjusted SDBIP Compiled by:
Adjusted SDBIP Approved by: